# United Nations Development Group Iraq Trust Fund

# Project #:B1-13

# Date and Quarter Updated: 22nd June 2008 (2nd Quarter)

# Operationally Closed

| Participating UN Organisation: UNESCO | Cluster: B |
| --- | --- |
| Govt of Iraq Line Ministry Responsible: Ministry of Education – Baghdad, Iraq |

# Programme/Project Number:

| Title | Education Management Information System (EMIS) |
| --- | --- |
| Location | MoE and 23 Directorates of Education in 18 Governorates, as follows: Baghdad (Karkh), Nainawa (Mosul), Al-Muthanna (Samawa), Ta'meem (Kerkuk), Salah Eddin (Tikrit), Al-Anbar (Rumadi), Karbala (Karbala), Najaf (Najaf), Babylon (Hilla), Qadisya (Diwanya), Basra (Basra), Thiqar (Nassirya), Wasit (Kut), Missan (Al-Amara), Erbil (Erbil), Sulaimanya (Sulaimanya), Dohuk (Dohuk) and Dyala (Baqouba). |
| Project Cost | US $ 1,500,000 |
| Duration | 11 November 2004 – 30 July 2005 (Extended 4 times: (1) Until 31st March 2006, (2) Until 30 June 2006, (3) Until 30 September 2006 and (4) Until 31st December 2006. |
| Approval Date (SC) | 11-Nov-04 | Starting Date | 11-Nov-04 | Completion Date | 31-Dec-06 |
| Project Description | The EMIS Project aimed at assisting the central Ministry of Education (MoE) and the Directorates of Education (DoEs) in Iraq to improve the accessibility, relevance, quality and efficiency of education through the institutionalization of a system to support informed decision making. It aimed to establish basic infrastructure for data entry, data analyses, and preparation of statistical reports at the central MoE and at the 23 DoEs. |

# Development Goal and Immediate Objectives

Development goal is empowering MoE and the Directorates of Education at the Governorate level to enter data, analyze results, develop educational indicators, solve educational problems, rationalize the use of resources and reduce inefficiencies in the education system

# Outputs, Key activities and Procurement

| Outputs | Development and customizing of EMIS software for MoE. Training of staff and capacity building for MoE and DoEs to utilize the newly established system. Decentralization of data entry of all school census forms at the DoEs. Provision of basic IT infrastructure and equipment needed for MoE and DoEs to establish an EMIS. |
| --- | --- |
| Activities | Development of software and related capacity building for MOE staff (UNESCO Train schools to fill out new school census forms (UNICEF) Procurement of needed equipment and installation of hardware and software at MOE and DOEs (UNESCO and MOE) Distribution of data forms to schools and data collection (UNICEF and MOE) Data entry (UNESCO and MOE) Data consolidation into a national database (MOE) |
| Procurement (major items) | IT Equipment (25 servers, 510 PCs, 124 printers, 44 UPSs, 50 scanners, LAN Accessories) Office Equipment VSAT Satellite Terminal |

# Part Two: Situation as of 22nd June 2008

| Funds Committed | $1,453,753 | % of approved | 96.92% |
| --- | --- | --- | --- |
| Funds Disbursed | $1,444,575 | % of approved | 96.31% |
| Forecast final date |  | Delay (months) |  |

# Quantitative achievements against objectives and results

| Development and customizing of EMIS software for MoE. | UNESCO contracted a private company to develop the EMIS software. A Workshop was conducted in Beirut for the Director-General of Planning and 5 officials from the respective Directorate to design and develop the school census forms. | % of planned | 100% |
| --- | --- | --- | --- |
| Training of staff and capacity building for MoE and DoEs to utilize the newly established system. | Technical Training for 2 programmers and system analysts was conducted in Beirut on various programming languages and tools. Two Training workshops on LAN Administration were organized in Baghdad and Alexandria for 50 LAN administrators at the MoE and DoEs. Training workshops were also organized for MoE and DoE staff on data entry and training of 5 key IT personnel on SQL Reporting. Training of 33 statisticians on EFA statistics organized in Dead Sea/Jordan during 1 – 13 April 2006 in collaboration with UNICEF. Training of another 30 statisticians organized during August 2006. Training of 30 MoE and DoE high level officials on the Planning and Management of the Education Sector held in Amman from 15 – 27 April 2006. Another group of 30 officials were trained during August 2006 in Aqaba – Jordan. Training of a Core Team of 5 Officials from MoE on the management and maintenance of Microsoft SQL Server 2000, the database structure of the EMIS Software, and the use of queries and Reporting Services to extract reports and output out of the database. Training workshop targeting 17 Statisticians from DoEs and the core team from MoE on the use of SPSS in the production of statistical reports and indicators from the EMIS database. Training workshop in Baghdad on the use of the SPSS Software for 21 Statisticians following the previous one in Amman, and undertaken by MoE staff who were trained in Amman. | % of planned | 100% |
| Decentralization of data entry of all school census forms at the DoEs. | Data entry for the educational data of 2004-2005 was completed by all DoEs in Iraq. UNESCO is assisting the Ministry of Education in issuing the annual statistical report for the school year 2004-2005. The DoEs are currently finalizing the data entry for the school year 2007-2008 into the system. | % of planned | 95% |
| Provision of basic IT infrastructure and equipment needed for MoE and DoEs to establish an EMIS. | UNESCO provided and installed IT equipment and servers in addition to some generators (20PCs per DoE) to establish LANs in all 23 DoEs throughout Iraq. | % of planned | 100% |

# Qualitative achievements against objectives and results

Depending on the collected information, the actual tangible qualitative outcomes will be achieved in the future. However, on the short-term, the project was successful in realizing the decentralization of data entry to the governorates' level. The project also guarantees quality information collection and entry into the system.