# United Nations Development Group Iraq Trust Fund

# Project #:B1-14

# Date and Quarter Updated: October 2008 (3rd Quarter)

| Participating UN Organisation: UNESCO | Cluster: B |
| --- | --- |
| Govt of Iraq Line Ministry Responsible: Ministry of Education – Baghdad, Iraq |

# Programme/Project Number:

| Title | REVITALIZATION OF TECHNICAL AND VOCATIONAL EDUCATION (PHASE II) |
| --- | --- |
| Location | Governorates of Baghdad (Resafa and Karkh), Babylon (Hilla), Waset (Kut), Thiqar (Nassirya), Basra (Basra), Salaheddin (Tikrit), Al Anbar (Rumadi), Ta'meem (Kerkok), Dyala (Baqouba), Karbala (Karbala), Najaf (Najaf - Kufa), Qadissya (Diwanya) and Missan (Al-Amara) in 37 Vocational and technical Schools |
| Project Cost | US$ 3,000,000 |
| Duration | 1st September. 2005 to 31 December 2006. A project extension was approved from December 2006 to end the project by June 2007 (additional 6 months). Another extension was approved to end of September 30, 2007 ( additional 3 months) |
| Approval Date (SC) | 29/08/2005 | Starting Date | 1 Sept. 2005 | Completion Date | 30 September 2007 |
| Project Description | The project aims at providing quality education through the provision of basic workshop equipment, computers and training materials to a selected number of TVET institutions as well as IT facilities and networking. |

# Development Goal and Immediate Objectives

Improved quality of teaching and training for vocational students in the 37 vocational schools in Governorates of Baghdad, Babylon, Waset, Thiqar, Basra, Salaheddin, Al Anbar, Kerkok, Dyala, Karbala, Najaf, Diwanya and Missan through the delivery of new vocational specialized equipment, acquisition of IT skills and the production of new training materials in Arabic for 9 vocational disciplines. The key immediate objectives of the project are to: Providing essential and basic workshop equipment, computers and training materials for nine vocational high priority disciplines; Providing computer labs for students and computers for improving IT skills for teaching staff; Producing training material in nine vocational disciplines in Arabic and training master instructors on the design review and delivery of the new training material Training senior managers in vocational education directorate at MOE on Leadership and Management and conducting selected study visits.

# Outputs, Key activities and Procurement

| Outputs | Equipment Procurement: The program outlines for nine vocational disciplines were fully prepared in order to identify the specification for the equipment. A workshop for the finalization of the equipment specifications was conducted in May 2006. Specifications were all endorsed by experts and by Iraqi partners for nine vocational disciplines. Tenders were launched in July –August 2006. Tenders were studied by UNESCO and finalized by end of September 2006. Delivering IT equipment to MOE. In addition to The Food Service, Electronics, and Sewing, Food production, Electrical, Telecommunications and Mechanical. Automotive, construction and second workshop for sewing and electronics are under delivery and expected to be delivered within the 4th quarter of 2007. Organizing study visits to provide hands-on experiences in the planning and management of TVET: The study visits were all completed in November 2006. Updating nine vocational and technical disciplines to meet the new needs of Iraq labour market and to be in line with international practices: MOE has prepared an initial outline of the vocational disciplines needed to be updated. UNESCO has prepared the final draft outline for the vocational disciplines. A workshop to finalize and update the content of the vocational disciplines was organized in December 2006. Setting up of the TVET Staff Development Unit and provide training to a core team of 30 trainers to be deployed as Master Vocational Trainers nation-wide to plan and organize continuing staff training: MOE has identified the management team and the core staff for the Development Unit and established the Unit. Producing training materials in Arabic language: The outline of the training material in Arabic was jointly discussed with the MOE during a workshop conducted in December 2006 on training 30 master instructors of TVET. All training manuals were finalized and sent to MOE-Iraq by the end of December 2006. |
| --- | --- |
| Activities | Specifications for equipment for nine vocational disciplines have been prepared. MOE instructors were trained on the design and review of equipment specifications in December 2006. MOE staff has attended a TVET forum held in Cairo in July 2006. The forum was entitled "Re-alignment of TVET with Employment Requirements". MOE has designed program outlines for nine vocational disciplines in cooperation with international experts. MOE has cooperated with UNESCO in the preparation of the training manuals in Arabic for nine vocational disciplines. MOE has established the staff development unit at MOE for Master Instructors Training. Tenders for equipment procurement have been launched by UNESCO end of August 2006. Study and analysis of equipment tenders have been finalized by UNESCO by September 2006. Delivery of all equipment is expected to be finalized by the end of December 2007. Twenty eight (28) training handbooks (in Arabic) belonging to the nine vocational disciplines for grades 10, 11 and 12 in addition to books and manuals have been prepared by international experts in Electronics, Sewing, Agriculture, Communication, Electrics, Automotive, Mechanics, Food service and production, Construction. A training workshop for 30 Master Instructors in nine vocational disciplines has been organized in December 2006. |
| Procurement (major items) | Workshop equipment for 36 workshops distributed over 37 MOE vocational schools as follows: Thirteen (13) IT and computer labs. Three (3) communication workshops. Three (3) construction workshops. Four (4) sewing workshops. Four (4) food Service workshops. Three (3) food production workshops. Two (2) mechanics Workshops. Three (3) electric workshops. Two (2) automotive workshops. Two (2) electronics workshop. |

# Part Two: Situation as of 16th April 2008

| Funds Committed | $2,976.637 | % of approved | 99.22% |
| --- | --- | --- | --- |
| Funds Disbursed | $2,893,807 | % of approved | 96.46% |
| Forecast final date | 31st March 2008 | Delay (months) |  |

# Quantitative achievements against objectives and results

| Workshop equipment | Thirty seven (37) vocational schools at MOE will be equipped with 36 workshop equipment), total value 1,918,000 $ US. (equipment under delivery) | % of planned | 100% |
| --- | --- | --- | --- |
| IT equipment | Thirteen (13) schools will be equipped (10 in 10 different governorates , 3 in Baghdad), total value 250,000 $ US (equipment under delivery) | % of planned | 100% |
| Training of Vocational Trainers, Master Instructors and Senior Managers. | Three (3) sessions organized, (2 in Amman, 1 in Egypt), 70 attendants | % of planned | 100% |
| Revision and update of training material | Nine (9) manuals in Arabic designed, revised and printed for grades 1, 2 and 3 in secondary vocational education in 9 vocational disciplines. | % of planned | 100% |

# Qualitative achievements against objectives and results

Training of staff of the MOE General Directorate for Vocational Education has allowed the creation of a Staff Development Unit (SDU), capable of ensuring the continuing staff training on new technologies. This SDU is composed of 10 trainers, located in Baghdad but covering the whole country according to training needs. Training material developed for nine vocational disciplines will represent a very good step toward the reform of the vocational education and training curricula at MOE. The manuals were adopted by MOE and will be in classroom starting the year 2007-2008. Training of the senior manager of TVET at MOE on leadership and management of the TVET system will allow MoE to achieve better performance and quality in TVET education and training on the national level.