# United Nations Development Group Iraq Trust Fund

# Project #:B1-17

# Date and Quarter Updated: December 2007/4th Quarter 2007

# Part One: Summary

| Participating UN Organisation: UNESCWA | Sector: Education |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Higher Education |

| Title | Iraqi Networking Academies Project – Phase II |
| --- | --- |
| Geographic Location | Baghdad, Basra, Mosul and Erbil, as well as other cities and towns in Iraq |
| Project Cost | $3,780,000 |
| Duration | 36 months (project extension until 30 June 2008) |
| Approval Date (SC) | 29 Aug 2005 | Starting Date | 25 August 2004 | Completion Date | 30 June 2008 |
| Project Description | The main goal of the project is to provide Iraqis the opportunity to receive networking education and thus empower them to actively contribute to the development of a robust ICT education sector that will help towards the rebuilding of their country. |

# Development Goal and Immediate Objectives

Establishing 5 Regional and 39 Local Networking Academies in Baghdad, Mosul, Basra and Erbil to train Iraqi university students on the basic and advanced Cisco networking courses.

# Outputs, Key activities and Procurement

| Outputs | Phase II of the project is being implemented. It involves the establishment of 1 Regional Networking Academy in Erbil and 33 Local Networking Academies throughout Iraq. |
| --- | --- |
| Activities | Two Iraqi participants attended the Cisco International Academy Conference in Istanbul in October 2007. The conference introduced the new version of the CCNA and IT Essentials curricula, assisted the Iraqis in planning for the migration to the new version, and informed them about new technologies, best practices, and teaching methodologies; Shipment of all IT equipment which were originally stored in Beirut was completed during the 4th quarter of 2007. |
| Procurement (major items) | Purchase of 44 Cisco Wireless and Security bundles for the Cisco Advanced Technology courses at the academies. The total cost of the bundles is just above $450,000. |

# Part Two:

| Funds Committed | 3,505,948 | % of approved | 93 |
| --- | --- | --- | --- |
| Funds Disbursed | 2,757,318 | % of approved | 73 |
| Forecast final date | 30 June 2008 | Delay (months) | 6 |

# Quantitative achievements against objectives and results

| Training of students | Up until end of December 2007, Cisco reports that 1629 students and instructors were trained in the Iraqi academies since the start of the implementation of the project. | % of planned | 80 |
| --- | --- | --- | --- |
| Training of trainers | 3 training-of-trainer sessions were completed in 2004, 2006, and 2007. | % of planned | 100 |
| Purchase of IT equipment | All IT equipment have been purchased, except for the latest version of books, which will be purchased in 2008 | % of planned | 95 |
| Shipment of IT equipment | All IT equipment previously stored in Lebanon was shipped to Iraq. The lately purchased Cisco bundles are being shipped from the USA (currently awaiting for customs clearance documents), and books will be shipped once the purchasing process is completed. | % of planned | 95 |

# Qualitative achievements against objectives and results

The impact of the project is receiving global recognition. During the team’s stay in Istanbul, all conference participants admired the courage the Iraqis in operating under the severe living and security conditions in their country. Also, CNN approached the project team, through Cisco, to conduct a broadcast event describing the success of the Cisco Networking Academy Program through ESCWA’s learning initiative in Iraq. This invitation was rejected due to the obvious security threat that this broadcast opportunity brings to the academy instructors and students.