# United Nations Development Group Iraq Trust Fund

# Project #:B1-19

# Date and Quarter Updated: 31 Dec 2007

# Part One: Summary

| Participating UN Organisation: UNICEF&WHO | Sector: Education |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Education in collaboration with MOH, MMPW, MOB & MOLSA |

| Title | Education; Rehabilitation/Upgrading of Basic Social Services around Child-Friendly Schools |
| --- | --- |
| Geographic Location | 1. governorates; Basrah, Missan, Thiqar, Wasit, Erbil and Baghdad 2. Districts: Adhamiya, Al-Hay, Ali Al-Gharbi, Basra, Erbil, Kadhumiya, Kahla', Kut, Makhmour, Nasiriya, Nu'maniya, Qurna, Rifaee, Risafa 2, Shatra & Zubair, Baghdad city, Risafa 3. Town/Village: Fahama, Hay Al Shaab, Zuair centre, Qurna centre, Nu'maniya centre, That Al Salasel, Baghdad Al Jadida, |
| Project Cost | Total 12,900,360 , (WHO: 300,000) |
| Duration | Six months |
| Approval Date (SC) | 1 Sept. 2005 | Starting Date | 1 Sept 2005 | Completion Date | Sept 2006 (Pending Extension requested until 31/03/08) |
| Project Description | With schools as the nucleus, the project will enhance the quality of basic social services in communities around through coordinated interventions in education, health and water & sanitation |

# Development Goal and Immediate Objectives

Goal: Using school as a community entry point, the developmental goal of the project is to demonstrably improve, within a period of six months, the access and quality of basic social services, including education (especially that of girls), health/nutrition and water & sanitation in the disadvantaged communities around the selected 110 schools, through the implementation of an integrated approach. This integrated approach will result in a synergistic impact on all sectors and contribute to overall efforts to enhance social development and reduce morbidity and mortality, especially of children, in the selected areas. Objectives: To promote the up-gradation of 110 schools to child friendly schools in 6 governorates. To improve access to potable water and sanitation services in the communities around the selected school. To ensure basic health services in the communities around the selected schools

# Outputs, Key activities and Procurement

| Outputs | -90 schools upgraded to child-friendly standards. -To assure basic health services in the communities around schools. -Increased availability and improved quality of water through rehabilitated treatment plants and water distribution networks and improved collection of wastewater through rehabilitated sewer networks and sewage pumping stations |
| --- | --- |
| Activities | -Support rehabilitation of WES facilities and playgrounds in the 110 selected schools and provide essential education supplies to 110 underprivileged schools -Provide PHC (primary health care)/MCH (Maternal child health) units with essential vaccines, basic medicines, and medical supplies/equipment and support rehabilitation of PHC/MCH units where needed -Support rehabilitation of water treatment plants and water distribution networks, procure/distribute chlorine and support rehabilitation of sewer network and sewage pumping stations. |
| Procurement (major items) | Essential education supplies; sanitation kits, school furniture & recreational kits Essential vaccines, basic medicines, medical supplies/equipment for PHC/MCH units and procurement of chlorine for water treatment plants |

# Part Two:

| Funds Committed | US$ 12.600,360 million | % of approved | 100 |
| --- | --- | --- | --- |
| Funds Disbursed |  | % of approved |  |
| Forecast final date |  | Delay (months) |  |

# Quantitative achievements against objectives and results

| Schools rehabilitation, school furniture and Education supplies | WES facilities and playground in 90 primary/intermediate schools rehabilitated. However, 20 schools in Thiqar are in different stages of rehabilitation. UNICEF and Thiqar Governorate council made a number of attempts to urge the contractor to meet his obligation and complete the rehabilitation work, but to no avail. Finally it became apparent that the contractor is not able to finish the remaining work and UNICEF cancelled the contract. UNICEF is now considering completing the remaining work in these 20 schools through other means. | % of planned | 90 |
| --- | --- | --- | --- |
|  | -Procured/distributed 47,000 student’s chairs and 23,500 students’ desks for 110 selected schools. -Procured/distributed 1000 blackboards for 110 selected schools. | % of planned | 100 |
|  | -Procured/distributed sanitation kits for 110 selected schools. -Procured/distributed recreational kits for 110 selected schools. | % of planned | 100 |
| 2. To assure basic health services in the communities around schools. | Further to the selection of schools, 25 primary health centres (PHC) were selected and an initial assessment of rehabilitation needs was carried out. The assessment indicated that only 9 PHCCs required renovations which were carried out in the 1st half of 2006, benefiting over 350,000 people. On the basis of the needs assessment, the required medical supplies and equipment were procured and delivered to the PHCCs. In addition, 456 health workers of selected districts as well as selected PHCCs staff were trained in PHC/MCH services, using other UNICEF (non-ITF) resources. To strengthen logistical/ operational capacity of outreach services of selected districts, contributing to about 20-25% people leaving outside direct access to PHC and 17 vehicles were procured and distributed to all districts under this project which strengthened the PHC outreach immunization services for over 1,000,000 people living in remote areas and having no access to basic health services. | % of planned | 100 |
| 3. Increased availability and improved quality of water through rehabilitated treatment plants and water distribution networks and improved collection of wastewater through rehabilitated sewer networks and sewage pumping stations | All the 14 sewerage projects comprising the rehabilitation/ extension of sewer networks (SNW), Sewage Pumping Stations (SPS) were physically completed as of end June 2007, enhancing access to improved sanitation for over 307,000 people residing in the governorates of Baghdad, Wasit, Thiqar, Missan and Basrah. |  | 100 |
|  | Equipment such as Spectrophotometer, incubator, water bath and different types of glassware and accessories have been provided to the wastewater quality control laboratories in Baghdad, Basrah, Missan and Thiqar governorate enabling them to conduct testing of Biochemical Oxygen Demand (BOD), Chemical Oxygen Demand (COD) and other basic waste water parameters. |  | 100 |
|  | 1,890 tones of chlorine have been delivered to the respective warehouses in Baghdad, Basrah, Wasit and Erbil governorates, thereby ensuring adequate availability of chlorine at almost all treatment plants within the IBSP area. The remaining 50 tonnes are yet to be delivered to the project sites. The consignment is held by the Ministry of Interior, Baghdad due to the current insecurity. UNICEF is following-up with the relevant Ministries to get the supplies released as soon as possible |  | 99 |

# Qualitative achievements against objectives and results

Results of an evaluation conducted in 2007 show that: The IBSP made a significant contribution to enabling the selected schools to support children’s rights. Most stakeholders said that school attendance and hygiene practices had improved. Children were happier to come to school due to the presence of new furniture, playgrounds, recreation and sanitation items, and improved toilets and water quantity and quality. New equipment and increased distribution of basic medicines were key reasons for increased satisfaction with the PHC services. Health services to schools generally increased. Mothers and pregnant women were more aware of the importance of regular visits to the PHC. Provision of vehicles for health districts although late in arriving addressed pressing needs for outreach to remote populations. Communities appreciated improvements in water and sanitation services. The WHO-implemented basic health screening for visual, hearing and musculoskeletal problems was limited due to shortages of time and resources. PHC staff trained in usage of screening instruments examined a sample of children. Follow-up through provision of glasses and hearing aids met with obstacles. Results flagged a need for all children to be screened at the school entry level and for close follow-up on needed interventions. Some smaller and complementary activities produced positive results such as motivating greater participation in the PTAs, and training activities for PHC and school staff, although training had mixed impact in promoting hygiene education. Data was collected regarding youth in communities and children’s rights issues. A positive effect was noted in awareness of the rights of children from all combined inputs.

Annex 1:	List of schools rehabilitated under this project

|  | Project: B1-19 (IBSP) |
| --- | --- |
| No | Governorate | District | School |
| 1 | Misan | Ali Al-Gharbi | Al-Ta'awon |
| 2 | Misan | Kahla' | Al-Mi'raj |
| 3 | Misan | Kahla' | Al-Zahrawi |
| 4 | Misan | Kahla' | Al-Khalil |
| 5 | Misan | Kahla' | That Al-Salasil |
| 6 | Misan | Kahla' | Ibn Al-Haythem |
| 7 | Misan | Kahla' | Al-Masjed Al-Aqsa |
| 8 | Misan | Kahla' | Ajnadeen |
| 9 | Misan | Ali Al-Gharbi | Al-Afrah |
| 10 | Misan | Ali Al-Gharbi | Al-Ensaneyah |
| 11 | Misan | Ali Al-Gharbi | Ali Al-Gharbi Sec. Sch. |
| 12 | Misan | Ali Al-Gharbi | Tadmur |
| 13 | Misan | Ali Al-Gharbi | Al-Hussain |
| 14 | Misan | Ali Al-Gharbi | Ali Al-Gharbi Sec. Sch. |
| 15 | Wasit | Kut | Al-Najah |
| 16 | Wasit | Kut | Al-Asala |
| 17 | Wasit | Kut | Al-qhuwan |
| 18 | Wasit | Kut | Al-Kaead Al-Muntathar |
| 19 | Wasit | Kut | Khalid Bin Al-Waleed |
| 20 | Wasit | Kut | Al-Kut Fundemental Stage 2 |
| 21 | Wasit | Kut | Al-Najah |
| 22 | Wasit | Al-Hay | Al-Shabab |
| 23 | Wasit | Al-Hay | Al-Hay(Wasit before) |
| 24 | Wasit | Al-Hay | Al-Ta'akhi |
| 25 | Wasit | Al-Hay | Beirut |
| 26 | Wasit | Nu'maniya | Said Al-Shuhada'a |
| 27 | Wasit | Nu'maniya | Al-Ikhlas |
| 28 | Wasit | Nu'maniya | Al-Nu'maniya |
| 29 | Wasit | Nu'maniya | Al-Frahidi |
| 30 | Wasit | Nu'maniya | Al-Talea'a |
| 31 | Erbil | Erbil | Giwi Mukriani |
| 32 | Erbil | Erbil | Shanadar |
| 33 | Erbil | Erbil | Dli Kurdistan |
| 34 | Erbil | Erbil | Democracy |
| 35 | Erbil | Erbil | Hersh |
| 36 | Erbil | Makhmour | Kurdistan |
| 37 | Erbil | Makhmour | Dldar |
| 38 | Erbil | Makhmour | Bazarka |
| 39 | Erbil | Makhmour | Qaraj |
| 40 | Erbil | Makhmour | Makhmur |
| 41 | Baghdad | Kadhumiya | Al-Makarim |
| 42 | Baghdad | Kadhumiya | Ja'far Al-Tayyar |
| 43 | Baghdad | Kadhumiya | Al-Salam |
| 44 | Baghdad | Kadhumiya | Al-Naba' |
| 45 | Baghdad | Kadhumiya | Al-Fadha'il |
| 46 | Baghdad | Kadhumiya | Al-Dhafar |
| 47 | Baghdad | Kadhumiya | Al-Mi'raj |
| 48 | Baghdad | Kadhumiya | Al-Bahreen |
| 49 | Baghdad | Kadhumiya | Fatimah Bint Asad |
| 50 | Baghdad | Kadhumiya | Al-Maqasid |
| 51 | Baghdad | Kadhumiya | Al-Qastal |
| 52 | Baghdad | Kadhumiya | Al-Shahama |
| 53 | Baghdad | Kadhumiya | Al-Ghadeer |
| 54 | Baghdad | Adhamiya | Al-Masarra |
| 55 | Baghdad | Adhamiya | Maghaweer |
| 56 | Baghdad | Adhamiya | Hamat |
| 57 | Baghdad | Adhamiya | Wisam Al-Ma'refah |
| 58 | Baghdad | Adhamiya | Youm Al-Khier |
| 59 | Baghdad | Adhamiya | Al-Khalil |
| 60 | Baghdad | Risafa 2 | Al-Sa'adah Basic Sch. /2 |
| 61 | Baghdad | Risafa 2 | Dar Al-Salam Basic Sch. /1 |
| 62 | Baghdad | Risafa 2 | Hamorabi |
| 63 | Baghdad | Risafa 2 | Saif Al-Jihad |
| 64 | Baghdad | Risafa 2 | Al-Khandaq |
| 65 | Baghdad | Risafa 2 | Al-Khawarezmi |
| 66 | Basra | Basra | Al-Mayamin |
| 67 | Basra | Basra | Al-Shaheed Ahmed Yaser Al-Ka'bi |
| 68 | Basra | Basra | Al-Shaheed Iyad Ali Al-Ghareeb |
| 69 | Basra | Basra | Al-Shaheed Nuwras Ahmad Al-Asadi |
| 70 | Basra | Basra | Al-Shaheed Firas Mujeed Al-Myahi |
| 71 | Basra | Basra | Al-I'mar |
| 72 | Basra | Basra | Al-Estabraq |
| 73 | Basra | Qurna | Kufa |
| 74 | Basra | Qurna | A'ahid Jadeed |
| 75 | Basra | Qurna | Sanabul |
| 76 | Basra | Qurna | Sukaina Bint Al-Hussain |
| 77 | Basra | Zubair | Al-Ya'robeyah |
| 78 | Basra | Zubair | That Al-Nitaqain |
| 79 | Basra | Zubair | Ibn Rushd |
| 80 | Basra | Zubair | Ahram |
| 81 | Basra | Basra | Al-Dahab Al-Aswad |
| 82 | Basra | Basra | Al-Muhlab Bin Abi Sufrah |
| 83 | Basra | Zubair | Al-Saraha |
| 84 | Basra | Basra | Al-Shaheed Abdull Qader Saed |
| 85 | Basra | Qurna | Farazdaq |
| 86 | Basra | Basra | Lathiqiya |
| 87 | Basra | Qurna | Malahim |
| 88 | Basra | Qurna | Ruqaiya |
| 89 | Basra | Qurna | Sana |
| 90 | Basra | Basra | Shuhadaa' |
| 91 | Thiqar | Nasiriya | Jabir Al-Ansari |
| 92 | Thiqar | Nasiriya | Al-Mustafa |
| 93 | Thiqar | Nasiriya | Fateh |
| 94 | Thiqar | Nasiriya | Al-Rasool Al-Adheem |
| 95 | Thiqar | Nasiriya | Mandili |
| 96 | Thiqar | Nasiriya | Al-Khartoum |
| 97 | Thiqar | Rifaee | Al-Nwadhem |
| 98 | Thiqar | Nasiriya | Al-Shaheed Habeeb Bn Muthaher |
| 99 | Thiqar | Rifaee | Yaa'robiya |
| 100 | Thiqar | Nasiriya | Al-Zawraa' |
| 101 | Thiqar | Nasiriya | Ukadh |
| 102 | Thiqar | Rifaee | Al-Rafidain |
| 103 | Thiqar | Nasiriya | Madenet Al-Mudon |
| 104 | Thiqar | Shatra | Al-Fatimiya |
| 105 | Thiqar | Rifaee | Al-Sayyab for girls |
| 106 | Thiqar | Shatra | Al-Shatra |
| 107 | Thiqar | Shatra | Al-Rabee' |
| 108 | Thiqar | Rifaee | Saif Bin Di Yazan |
| 109 | Thiqar | Shatra | Al-Yamen |
| 110 | Thiqar | Shatra | U'mar Bin Abdul Azziz |