# United Nations Development Group Iraq Trust Fund

# Project #: B1-22 (a+b)

# Date and Quarter Updated: October - December 2008 (4th Quarter)

| Participating UN Organisation: UNICEF and UNHABITAT | Sector: Education |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Education |

| Title | School rehabilitation and capacity building for school maintenance |
| --- | --- |
| Geographic Location | 18 governorates (later Anbar was removed, reducing the number of governorates covered by this project to 17, as per the list attached) |
| Project Cost | UNICEF US$ 9,029,120 UNHABITAT US$ 6,631,818 |
| Duration | Original: 17 months 1st Revision: 24 months 2nd Revision: 32 months |
| Approval Date (SC) | 16 Jul 06 | Starting Date | 24 Jul 06 | Completion Date | Original: 13 Dec 07 1st Ext: 30 Jun 08 2nd Ext: 31 Mar 09 |
| Project Description | The project will support the rehabilitation of 160 schools in 18 Iraqi Governorates (90 schools in 15 governorates by UNICEF; 70 schools in 3 governorates by UNHABITAT), as well as capacity building for school maintenance and School Sanitation and Hygiene Education. The project will be implemented in 2 phases. |

# Development Goal and Immediate Objectives

Goal: The main objective of the project is to increase access to primary, intermediate and secondary education for school age children (grades 1 to 12) with emphasis on rural areas and girls’ education, and enhance the capacity of Directorates of Education (DoEs) in school maintenance, and school sanitation and hygiene promotion. Objectives: 1. Improvement of physical environment of 160 schools in 18 governorates, including water and sanitation (WES) facilities. 2. Enhance the capacity of DoEs to undertake the maintenance of schools and promote hygiene practices. 3. Reduce the number of shifts as well as the number of students in crowded classrooms by adding new classrooms. 4. Building capacity of local contractors under several categories and using local material, which will improve economical conditions of local communities. 5. Reduce unemployment in local remote communities.

# Outputs, Key activities and Procurement

| Outputs | Rehabilitation of 160 schools in 18 governorates benefiting about 80,000 school age children Train 55 DoE technical staff, 160 head teachers and 320 Parent Teacher Association (PTA) representatives of the rehabilitated schools on best practices in school maintenance (including use of public-private partnerships) and on promotion of improved sanitation and hygiene practices in schools. Develop a manual on management of school building and maintenance and guidelines on school sanitation and hygiene practices. |
| --- | --- |
| Activities | Contracting about 100 local Iraqi contractors for implementing the comprehensive rehabilitation of 160 schools in 18 governorates. Hiring engineers/monitors to provide technical assistance and to undertake the monitoring of rehabilitation activities. Engage International and Iraqi consultants to conduct training workshops and to work with UN and Ministry of Education (MoE)/DoE staff in developing manuals and guidelines on school maintenance and school sanitation and hygiene practices, including an information dissemination programme to promote awareness among students, parents and teachers on these practices. |
| Procurement (major items) | None |

UNHABITAT

| Funds Committed | $6,494,845 | % of approved | 98 % |
| --- | --- | --- | --- |
| Funds Disbursed | $6,494,845 | % of approved | 98 % |
| Forecast final date | June 2008 | Delay (months) |  |

# UNICEF

| Funds Committed | $ 9,029,118.5 | % of approved | 100% |
| --- | --- | --- | --- |
| Funds Disbursed | $ 8,949,874 | % of approved | 99.5% |
| Forecast final date | March 2009 | Delay (months) |  |

# Quantitative achievements against objectives and results

| Rehabilitation of 160 schools in 18 governorates benefiting about 80,000 school age children. [This plan was changed – please see next column for details] | The original plan was to rehabilitate 160 schools in 18 governorates (90 schools in 15 governorates by UNICEF; 70 schools in 3 governorates by UNHABITAT). Some project modifications had to be made to the original plan as follows: 6 schools in Anbar were replaced by 6 schools in Baghdad due to insecurity. Those schools were later included in the schools to be rehabilitated under another ITF project (B1-29). 2 schools in Ninevah were destroyed in the middle of the rehabilitation process and works had to be terminated. Based on the request of the DoE of Nineveh, the remaining funds planned for the comprehensive rehabilitation of the 2 schools were used for the construction of additional classrooms in another 2 schools covered by this project. Rehabilitation of 13 schools (3 schools in Wasit for comprehensive rehabilitation; 10 schools in Kirkuk for WES rehabilitation) was additionally included in this project based on requests from the DoEs of Kirkuk and Wasit. These modifications to the project changed the number of schools to be rehabilitated by UNICEF from 90 (comprehensive) to 101 (91 comprehensive; 10 WES). This change in scope was reported in the 3rd Quarter fiche, as well as being acknowledged by SCSO through the approval of UNICEF’s request for time extension/change of scope in Nov 08. Comprehensive rehabilitation of 157 (87 by UNICEF and 70 by UNHABITAT) schools and rehabilitation of WES facilities in 10 schools was completed. Around 99,860 students (56% girls) and 4822 teachers (67% female) are benefiting from an improved school environment in these 157 schools. During the reporting period, UNICEF terminated a contract for rehabilitation of 4 schools in Muthanna after the contractor failed to complete these schools within the agreed timeframe. UNICEF is in the process of re-bidding for these schools, to complete remaining work. Request for extension of the project until 31 March 2009 was approved in November 2008. | % of planned | 97.7% |
| --- | --- | --- | --- |
| Train 55 DoE technical staff, 160 head teachers and 320 PTA representatives of the rehabilitated schools on best practices in school maintenance (including use of public-private partnerships) and on the promotion of improved sanitation and hygiene practices in schools. | Training of DoE technical staff (Baghdad and KRG) on school maintenance is expected to take place in the first or second quarter of 2009, followed by development of a school management and maintenance manual. 459 teachers and head masters received training on school sanitation, Avian Influenza, HIV/AIDS and Cholera. 3,000 School Sanitation and Hygiene manuals in Kurdish were printed and distributed; 3,000 copies of the manual in Arabic will be printed soon. | % of planned | 95% |
| Develop a manual on management of school building and maintenance and guidelines on school sanitation and hygiene practices. | A draft manual for school management and maintenance was developed by MoE with financial support of UNICEF in 2008. The draft manual will be reviewed and finalized by an international consultant, expected to be on board in the first quarter of 2009. | % of planned | 60% |

# Qualitative achievements against objectives and results

Post rehabilitation data collected from 24 schools (out of 56 completed in 2007) reveal that the improved environment is having a positive contribution towards the achievement of project objectives. The construction of 80 new classrooms and 122 additional toilets for girls has helped in reducing overcrowding in classrooms and improved access to proper sanitation. Enrolment in these schools has increased from 11,481 to 13,023 (13%) for all students, with 14% increase for girls. Attendance rates also jumped from 71.88% to 81.83%.

Summary of school rehabilitation by governorate

| Governorate | # of schools completed | Ongoing | Remark |
| --- | --- | --- | --- |
| Al Muthanna | 2 | 4 (under bidding) |  |
| Babil | 6 |  |  |
| Baghdad | 13 |  |  |
| Diyala | 5 |  |  |
| Dohuk | 6 |  |  |
| Erbil | 6 |  |  |
| Kerbala | 6 |  |  |
| Najaf | 6 |  |  |
| Ninevah | 2 |  | Another 2 schools terminated due to insecurity |
| Qadissiyah | 6 |  |  |
| Salaheldin | 6 |  |  |
| Suleimaniyah | 6 |  |  |
| Kirkuk | 16 |  | 10 WES facilities |
| Wasit | 9 |  |  |
| Basra | 14 |  | By UNHABITAT |
| Missan | 40 |  |  |
| Thiqar | 16 |  |  |
| Total | 173 | 4 |  |

Annex 1: List of schools (Project B1-22 a)

| No | Governorate | District | School | Status |
| --- | --- | --- | --- | --- |
| 1 | Al Muthanna | Al Samawa | Al Kheer | 100% |
| 2 | Al Muthanna | Al Samawa | Al Salam | 100% |
| 3 | Babil | Hilla | Al Rasool | 100% |
| 4 | Babil | Hilla | Al Tatbekat | 100% |
| 5 | Babil | Hilla | Ma'rifa | 100% |
| 6 | Babil | Hilla | Al Addil | 100% |
| 7 | Babil | Hilla | Al Emam Al Husain | 100% |
| 8 | Babil | Hilla | Al Qabas | 100% |
| 9 | Baghdad | Al Resafa | Al Aqoli | 100% |
| 10 | Baghdad | Al Resafa | Al Ardun | 100% |
| 11 | Baghdad | Al Resafa | Al In Bi'aath | 100% |
| 12 | Baghdad | Al Resafa | Darb Al Shahada' | 100% |
| 13 | Baghdad | Al Resafa | Al Shaheed Adil Nasir- Wadi Al Thahab | 100% |
| 14 | Baghdad | Taji | Muslim Bin A'qeel- AL Thair Al Arabi | 100% |
| 15 | Baghdad | Taji | Al Ahwaz | 100% |
| 16 | Baghdad | Taji | Saeed Bn Al Museeb | 100% |
| 17 | Baghdad | Al Resafa | Al Ihsan | 100% |
| 18 | Baghdad | Al Resafa | Al Khalij Al Arabi | 100% |
| 19 | Baghdad | Al Resafa | Al Nasriya | 100% |
| 20 | Baghdad | Al Resafa | Al Rifa' | 100% |
| 21 | Baghdad | Al Resafa | Al Talai | 100% |
| 22 | Diyala | Ba'quba | Al Qurna | 100% |
| 23 | Diyala | Ba'quba | Abu Al Ataheyah | 100% |
| 24 | Diyala | Ba'quba | Al Hera | 100% |
| 25 | Diyala | Baladrooz | Al Kifel | 100% |
| 26 | Diyala | Khanaqeen | Makarm Al Akhlaq | 100% |
| 27 | Dohuk | Dahuk | Beshbooreen (Payman) | 100% |
| 28 | Dohuk | Dahuk | Rezan | 100% |
| 29 | Dohuk | Dahuk | Shiladze | 100% |
| 30 | Dohuk | Dahuk | Sararm | 100% |
| 31 | Dohuk | Sumel | Sharya | 100% |
| 32 | Dohuk | Aqre | Devery | 100% |
| 33 | Erbil | Choman | Qasrey | 100% |
| 34 | Erbil | Choman | Razan/Meehraban | 100% |
| 35 | Erbil | Choman | Shirkwa | 100% |
| 36 | Erbil | Choman | Rostey | 100% |
| 37 | Erbil | Choman | Smailawa | 100% |
| 38 | Erbil | Choman | Smilan | 100% |
| 39 | Kerbala | Al Hindiya | Al Entisar | 100% |
| 40 | Kerbala | Al Hindiya | Al Sayab | 100% |
| 41 | Kerbala | Karbala | Um Al Kura | 100% |
| 42 | Kerbala | Karbala | Al Hadba'a | 100% |
| 43 | Kerbala | Karbala | Al Sayida Nafisa | 100% |
| 44 | Kerbala | Karbala | Al Ghranada | 100% |
| 45 | Najaf | Najaf | Al Shaimaa | 100% |
| 46 | Najaf | Najaf | Al Taaef | 100% |
| 47 | Najaf | Najaf | Saa’d bin jouber | 100% |
| 48 | Najaf | Najaf | Al Ansaf | 100% |
| 49 | Najaf | Najaf | Al Nahdha | 100% |
| 50 | Najaf | Kufa | Al Ezdihar | 100% |
| 51 | Ninevah | Mosul | Hafsah | 100% |
| 52 | Ninevah | Mosul | Al Jomhoreyaih | 100% |
| 53 | Ninevah | Mosul | Al Waleed | 100% |
| 54 | Ninevah | Mosul | Dar Al Salam | 100% |
| 55 | Qadissiyah | Al Shamiya | Manar | 100% |
| 56 | Qadissiyah | Al Shamiya | Risafi | 100% |
| 57 | Qadissiyah | Al Shamiya | Shama'el | 100% |
| 58 | Qadissiyah | Dewania | 14 Tamooz | 100% |
| 59 | Qadissiyah | Afaq | Al Ukdah | 100% |
| 60 | Qadissiyah | Dewania | Haifa | 100% |
| 61 | Salaheldin | Tooz | Al Ghzali | 100% |
| 62 | Salaheldin | Tooz | Al Shula'a | 100% |
| 63 | Salaheldin | Tooz | Al Wathba | 100% |
| 64 | Salaheldin | Al Faris | Al Basma | 100% |
| 65 | Salaheldin | Al Faris | Al Bayraq | 100% |
| 66 | Salaheldin | Al Faris | Ja'far Al Sadiq | 100% |
| 67 | Suleimaniyah | Halabja | Harez | 100% |
| 68 | Suleimaniyah | Sulaimania | Kalakn | 100% |
| 69 | Suleimaniyah | Sulaimania | Waluba | 100% |
| 70 | Suleimaniyah | Koisanjaq | Kurdistan | 100% |
| 71 | Suleimaniyah | Koisanjaq | Nazanin | 100% |
| 72 | Suleimaniyah | Raniya | Titoka | 100% |
| 73 | Kirkuk | Kirkuk | Al Khalidya | 100% |
| 74 | Kirkuk | Kirkuk | Al Ma'rifa' | 100% |
| 75 | Kirkuk | Kirkuk | Al Mutawakel | 100% |
| 76 | Kirkuk | Kirkuk | Jerdee Peroz | 100% |
| 77 | Kirkuk | Kirkuk | Khabat | 100% |
| 78 | Kirkuk | Kirkuk | Al Rezgaree | 100% |
| 79 | Kirkuk | Kirkuk | Al Watan | 100% |
| 80 | Kirkuk | Kirkuk | Al Rafedeen | 100% |
| 81 | Kirkuk | Kirkuk | Hure'at | 100% |
| 82 | Kirkuk | Kirkuk | Anstans Al Karmaly | 100% |
| 83 | Kirkuk | Kirkuk | Mishkhel | 100% |
| 84 | Kirkuk | Kirkuk | Rouz Awah | 100% |
| 85 | Kirkuk | Kirkuk | Al Nabi Younis | 100% |
| 86 | Kirkuk | Kirkuk | Al Aqa’ad | 100% |
| 87 | Kirkuk | Kirkuk | Al Shaheed Qasim Khadim | 100% |
| 88 | Kirkuk | Kirkuk | Mohammad Sadiq | 100% |
| 89 | Wasit | Al Nu'maniya | Al Dar Al Baydhaa | 100% |
| 90 | Wasit | Al Suwaira | Al Qadsiya | 100% |
| 91 | Wasit | Al Nu'maniya | Sumar | 100% |
| 92 | Wasit | Kut | Al Bara'em | 100% |
| 93 | Wasit | Kut | Al Iffa | 100% |
| 94 | Wasit | Kut | Al Shumookh | 100% |
| 95 | Wasit | Kut | Al Farooq | 100% |
| 96 | Wasit | Kut | Ishtar | 100% |
| 97 | Wasit | Kut | Al Khalida | 100% |
| 98 | Al Muthanna | Al Rumaitha | Bilat Al Shuhadaa' | Re-Bidding |
| 99 | Al Muthanna | Al Rumaitha | Muhammadia | Re-Bidding |
| 100 | Al Muthanna | Al Rumaitha | Al Adala | Re-Bidding |
| 101 | Al Muthanna | Al Rumaitha | Al Khansa' | Re-Bidding |
| 102 | Ninevah | Mosul | Saqar Quraish | 50% |
| 103 | Ninevah | Mosul | Al Hadi | 80% |

List of schools (Project B1-22 b)

| No | Governorate | District | School | Status |
| --- | --- | --- | --- | --- |
| 1 | Basra | Al-Zubair center | Al-Tabaree (P) | 100 % |
| 2 | Basra | Al-Qurna Al-Sharsh | Al-Farazdaq (S) | 100 % |
| 3 | Basra | Al-Zubair Al-Shuiba | Ajnadeen (P) | 100 % |
| 4 | Basra | Basrah center Ashar | Al-Hadbaa (p) | 100 % |
| 5 | Basra | Al-Magel Qtr; Al-Hadi Hay | Al-Fettawa (I) | 100 % |
| 6 | Basra | Al-Magel Qtr; Al-Hadi Hay | Shuhadaa Al-Intifadaa Industrial (S) | 100 % |
| 7 | Basra | Al-Zubair; Al-Burjisiah Area; Al-Kartiat | Al-Furqan (P) | 100 % |
| 8 | Basra | Al-Zubair; Al-Burjisiah Area; Factories Region | Al-Burjisiah (P) | 100 % |
| 9 | Basra | Safwan; South Najemi Farms | Beni Hashim (P) | 100 % |
| 10 | Basra | Tewasah Hay | Al-Arqam (P) | 100 % |
| 11 | Basra | Al-Saai hay | Ibn Khaldoon (P) | 100 % |
| 12 | Basra | Zubair; Mahalt Al-Arab | Fatama Bint Al-Rasool (P) | 100 % |
| 13 | Basra | Basrah Center; Al-Hadi | Hutten (P) | 100 % |
| 14 | Basra | Al-Faw; Northern Faw | Al-Faw (S) | 100 % |
| 15 | Thiqar | Nassiriya; Thawra Hay | Maka Al-Mukarama (P) | 100 % |
| 16 | Thiqar | Al-Qal'a; Albo Ali Village | Al-Nahrawan (P) | 100 % |
| 17 | Thiqar | Nassiriya Ur Company Residential Complex | Al-Ghasasinah (P) | 100 % |
| 18 | Thiqar | Nassiriya Mouannis Village | Al-Adab (p) | 100 % |
| 19 | Thiqar | Al-Nassiriya ; Al-Saray Hay | Al-Talee'a (I) | 100 % |
| 20 | Thiqar | Al-Nassiriya; Sumir Hay | Amir Salim (K) | 100 % |
| 21 | Thiqar | Al-Nassiriya; Shuhadda Hay | Ghazwat Haneen (P) | 100 % |
| 22 | Thiqar | Al-Nassiriya; Shuhadda Hay | Abdulla Bin Khabab (P) | 100 % |
| 23 | Thiqar | Al-Nassiriya; Al-Tadhehiya Hay | Habib Bin Madhaher (P) | 100 % |
| 24 | Thiqar | Al-Nassiriya; Ur Hay | Al-Hikma (P) | 100 % |
| 25 | Thiqar | Al-Nassiriya; Ur Hay | Al-Meseera (P) | 100 % |
| 26 | Thiqar | Al-Nassiriya; Al-Sader Hay | Ibn Majed (P) | 100 % |
| 27 | Thiqar | Al-Nassiriya; Aredu Hay | Thi Al-Noon (P) | 100 % |
| 28 | Thiqar | Al-Nassiriya; Al-Sader Hay | Haber Al-Emmah (P) | 100 % |
| 29 | Thiqar | Al-Shatra; Al-Hawi Village. | Aswan (P) | 100 % |
| 30 | Thiqar | Al-Bat-ha'a | Al-Bat-Ha'a (S) | 100 % |
| 31 | Missan | Aummara; Jedada | Ibn Al-Nafees (P) | 100 % |
| 32 | Missan | Aummara; Al-Hussain Old Haee | Al-Fateh Al-Arabi (P) | 100 % |
| 33 | Missan | Aummara; Al-Risala Haee | Al-Warkaa (P) | 100 % |
| 34 | Missan | Aummara; Al-Askari Haee | Um Al-Baneen (P) | 100 % |
| 35 | Missan | Koumit | Al-Thaqeleen (P) | 100 % |
| 36 | Missan | Ali Al-Gharbi | Al-Hassaneen (P) | 100 % |
| 37 | Missan | Aummara; Al-Magharba Haee | Al-Yamama (P) | 100 % |
| 38 | Missan | Aummara; Al-Qadissiya Haee | Al-Beraq (P) | 100 % |
| 39 | Missan | Aummara; Al-Dibassat Haee | Asmaa (P) | 100 % |
| 40 | Missan | Aummara; Al-Moaalmeen New Haee | Bint Al-Hodaa (S) | 100 % |
| 41 | Missan | Aummara; Al-Amel Haee | Al-Emam Al-Sadeq (P) | 100 % |
| 42 | Missan | Aummara; Al-Jedada | Al-Tahreer (S) | 100 % |
| 43 | Missan | Aummara; Al-Magharba Haee | Al-Ghazali (P) | 100 % |
| 44 | Missan | Aummara; Al-Moaalmeen New Haee | Dejalah (S) | 100 % |
| 45 | Missan | Al-Mosherah | Al-Farooq (P) | 100 % |
| 46 | Missan | Aummara; Al-Rawaba Haee | Ghareeb Karbala (P) | 100 % |
| 47 | Missan | Al-Mamona; Al-Qodes | Al-Emam Mossa Al-Kadhem (P) | 100 % |
| 48 | Missan | Al-Mujer; Al-Qadissiya | Al-Naser (S) | 100 % |
| 49 | Missan | Aummara; Al-Qataa Haee | Janeen (P) | 100 % |
| 50 | Missan | Aummara; Al-Qataa Haee | Al-Ghosoon (P) | 100 % |
| 51 | Missan | Aummara; Al-Qahera Haee | Qahera (P) | 100 % |
| 52 | Missan | Aummara; Al-Thawra | Al-Hawraa (P) | 100 % |
| 53 | Missan | Aummara; Al-Qataa Haee | Al-Yamama (S) | 100 % |
| 54 | Missan | Aummara; Abo Rummanah Haee | Al-Shaheed Mohamed Baqer Al-Sader (P) | 100 % |
| 55 | Missan | Al-Mosherah | Al-Moshreh (S) | 100 % |
| 56 | Missan | Al-Mosherah | Al-Hadebaa (K) | 100 % |
| 57 | Missan | Aummara; Al-Zuzoot Haee | Al-Jawaheri (P) | 100 % |
| 58 | Missan | Al-Mamona; Al-Hussainiya | Al-Ameen (P) | 100 % |
| 59 | Missan | Aummara; Saad Haee | Yareb (P) | 100 % |
| 60 | Missan | Aummara; Al-Majediya | Al-Emam Al-Hussain (P) | 100 % |
| 61 | Missan | Aummara; Al-Thawra | Al-Zaheraa (P) | 100 % |
| 62 | Missan | Aummara; Al-Amarat | Ibraheem Al-Khaleel (P) | 100 % |
| 63 | Missan | Qalaat Saleh (S) | Qalaat Saleh (S) | 100 % |
| 64 | Missan | Aummara; Baghdad Road | Al-Awali (P) | 100 % |
| 65 | Missan | Aummara; Al-Askari Haee | Al-Rasool (S) | 100 % |
| 66 | Missan | Aummara; Al-Askari Haee | Al-Thagher (P) | 100 % |
| 67 | Missan | Qalaat Saleh Al-Ghadeer Haee | Al-Naaman (P) | 100 % |
| 68 | Missan | Qalaat Saleh | Al-Rayaheen (K) | 100 % |
| 69 | Missan | Koumit | Al-Shamael (K) | 100 % |
| 70 | Missan | Ali Al-Gharbi | Al-Maali (K) | 100 % |