# United Nations Development Group Iraq Trust Fund

# Project #:B1-24

# Date and Quarter Updated: 31 Dec 2007

# Part One: Summary

| Participating UN Organisation: UNICEF | Sector: Education |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: |

| Title | Essential materials for improved learning for all primary level students in Iraq |
| --- | --- |
| Geographic Location | All Primary schools in all governorates in Iraq |
| Project Cost | US$ 18,172,619 |
| Duration | 24 months |
| Approval Date (SC) | 28 Sept. 2006 | Starting Date | 02 October 2006 | Completion Date | 02 April 2007 |
| Project Description | The overall objective of this project is to enhance the access to and quality of primary level education by providing essential learning materials to about 4.7 million students |

# Development Goal and Immediate Objectives

Goal: To ensure the right to quality education of children through providing basic learning material to all primary level school children throughout the 18 Iraqi governorates, thus ensuring maximum enrolment and attendance in 2006/2007 scholastic year. Objectives: To alleviate the effects of economic hardship on Iraqi families and thus promote the enrolment of age 6 children to primary schools while ensuring participation of children age 7-12 in primary schools.

# Outputs, Key activities and Procurement

| Outputs | 4.7 million Iraqi children aged 6-12 provided with the necessary learning materials for the 206/2007 scholastic year. All 3,342,000 grades 1-4 students will each receive 7 exercise books, 12 pencils, 3 sharpeners, 3 erasers, 1 ruler, 1 drawing book and 1 colour pencils set while 1,358,000 students of grades 5 and 6 will receive 12 exercise books, 1 English language exercise book, 1 laboratory exercise book, 12 pencils, 3 sharpeners, 3 erasers, 1 ruler, 1 drawing book and 1 water colour paint box. In addition to that 1,200,000 newly enrolled grades 1 student will each receive one school bag. |
| --- | --- |
| Activities | Provide/distribute learning materials for 4.7 million primary level students in about 14,000 primary schools Monitor distribution of learning materials to primary schools and primary level students |
| Procurement (major items) | - Leaning materials & school bags |

# Part Two:

| Funds Committed | 18,172,619 | % of approved | 100% |
| --- | --- | --- | --- |
| Funds Disbursed | 18,172,619 | % of approved | 100% |
| Forecast final date | Closed | Delay (months) | 0 |

# Quantitative achievements against objectives and results

| Procurement, delivery and distribution of the learning materials for 4.7 million. Iraqi children in about 14,000 primary level schools | 100% of the essential learning materials were delivered to all Directorates Of Education (DOEs) warehouses and onward to 4.7 million Iraqi children aged 6 – 12 who received them. Each child is received 8 exercise books of 194 pages each, a box of 10 pencils, 2 pencil sharpeners, 2 erasers, 1 ruler, one drawing book and one box of colour pencil. In addition to that, 1.1 million newly enrolled grade 1 students are received one school bag each. | 100% of planned | 100 |
| --- | --- | --- | --- |

# Qualitative achievements against objectives and results

Anecdotal evidence (from UNICEF monitors and MOE key officials and responsible staff of Directorates of education) indicates that the delivery of essential learning materials have contributed directly to increase the overall enrolment and attendance rates of primary level students especially in rural areas by reducing economic burdens on the most deprived families. The staff of directorates of education in the 18 governorates, schools’ principals and parents were closely involved in the distribution process.