# United Nations Development Group Iraq Trust Fund

# Project: B1-25

# Date and Quarter Updated: April- June 2009

| Participating UN Organisation: WHO | Sector: B-Education |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Health |

| Title | Strengthening school health services at Primary School level through implementation of the Health Promoting Schools |
| --- | --- |
| Geographic Location | -All governorates -The School health screening component is conducted only in 8 governorates |
| Project Cost | US$ 1,757,280 |
| Duration | 12 months |
| Approval Date (SC) | 27th February 2007 | Starting Date | April 2007 | Completion Date | -First Extension till 31 September 2008 - 2nd extension till 31 March 2009 |
| Project Description | The aim of the project is to assist the Ministries of Health and Education/ Iraq to strengthen the school health services at primary level through updating the health education concepts into school curriculum, school health screening for students for visual and hearing problems and detection of musclo-skeletal abnormalities; and to adopt school health policies which aim to create a healthy physical and psychosocial environment for all students and staff, and to make the school a model of best practice for the whole community. This proposal will build on previous achievements of WHO in this area through its core budget and under the Integrated Basic Project funded under the UNDG ITF and support the Focusing Resources Effective School Health (FRESH) initiative launched by UN partners. |

# Development Goal and Immediate Objectives

Key immediate objectives: 1- Health promoting schools programme (life skills education and psychological first aid) implemented in 46 schools in 18 governorates (2 schools in each governorate except for Baghdad governorate 12 schools in Karch and Rasafa). 2- Increase capacity of MoH officials to take over the health promoting school initiative and continue the activity of school health screening for primary school children as part of the Strengthening Primary Health Care system and improve the health of students. 3- Raise awareness among communities on Health Promoting Schools initiative and the role of parent teachers’ association (PTA) meetings strengthened 4- Hearing aids and eyeglasses provided for needy students and those with musclo-skeletal abnormalities referred to specialists. 5-Effective partnerships between all stakeholders including the community to build public awareness and strengthen demand for the school health services.

# Outputs, Key activities and Procurement

| Outputs | 100 teachers and school staff trained on health promoting school initiative in 46 schools in all governorates. School health including psychological first aid services strengthened and maintained at all levels through successful coordination approaches between schools and primary health care centres. MoH officials informed about health promoting school initiative. 50 MoH health professionals trained on school health screening activities. 100 Community leaders trained on health promoting schools initiative. Health screening of randomly selected students in the 150 schools at 8 governorates completed (screening for visual, hearing problems and musclo-skeletal abnormalities). 300 teachers trained on detection of visual, hearing defects and musclo-skeletal abnormalities in 150 schools in 8 governorates involved in Health screening. Provision of eyeglasses and hearing aids to school children with visual and hearing difficulties and those with musclo skeletal abnormalities referred to specialists completed. Community committees established to build public awareness in demanding for school health services. |
| --- | --- |
| Activities | Support MoH and Ministry of Education in the implementation of the health promoting schools initiative through conducting orientation workshops for head masters, training of health professionals, teachers and health workers. Provided skill-based health education that focuses on the development of knowledge, attitude, values and life skills needed to make and act on the most appropriate and positive decision concerning health. Training of (200) teachers and health personnel working at primary health care centres on providing first aid psychological and basic mental health care for children with psychosocial problems. Advocacy and communication meetings for MoH/ MoE officials and local communities on health promoting schools initiative. Training of 50 MoH health professionals on school health screening. Increasing the coordination between all sectors and establishing systems for monitoring and evaluation of HPS initiative. Training of community leaders on health promoting school initiative. Capacity building of national trainers from MoH and MOE (school health programme managers, health workers and teachers) to improve their skills on early detection of eye and ear problems, and musclo-skeletal abnormalities. 10. Training of teachers on examination of visual acuity and detection of visual errors, hearing difficulties and musclo- skeletal abnormalities. 11.Provision of supplies and equipments as audiometers, ophthalmoscopes and Snell’s charts for the health screening activities at schools. Provision of eyeglasses and hearing aids to students in need. Advocacy among community and religious leaders through training and distribution of educational materials and strengthening the Parent Teachers Association (PTA) meeting |
| Procurement (major items) | - Printing of 10,000copies of Brochure and 10,000 note book on health promoting schools - Procurement of 20 eyeglasses and 10 hearing Aids for students with visual and hearing difficulties. - Procurement of 46 desktops and printers for the 46 health promoting schools - Procurement of 46 screening Audiometers - Procurement of 10,000 school bags and 5,000 Hygiene kits for students - procurement of 100 white boards with accessories |

| Funds Committed | US$ 1,668,026.00 | % of approved | 66% |
| --- | --- | --- | --- |
| Funds Disbursed | US$ 714,576.00 | % of approved | 41% |
| Forecast final date | 30 July 2009 | Delay (months) |  |

# Quantitative achievements against objectives and results

| Objective (1) | Health promoting schools programme (life skills education and psychological first aid) implemented in 46 schools in 18 governorates (2 schools in each governorate except for Baghdad governorate 12 schools in (Karch and Rasafa). | 100 % of planned |  |
| --- | --- | --- | --- |
| Objective (2) | Increase capacity of MoH officials to take over the health promoting school initiative and continue the activity of school health screening for primary school children as part of the Strengthening Primary Health Care system. | 100 % of planned |  |
| Objective (3) | Raise awareness among community on Health Promoting Schools initiative and the role of parent teachers association (PTA) meetings | 95 % of planned |  |
| Objective (4) | Hearing aids and eyeglasses provided for needy students and those with musclo- skeletal abnormalities referred to specialists. | 90 % of planned |  |
| Objective (5) | Effective partnerships between all stakeholders including the community to build public awareness and strengthen demand for the school health services. | 90% of planned |  |

# Qualitative achievements against objectives and results

As part of the Health promoting schools project, WHO conducted the school health screening of primary school students and environmental assessment in 150 schools in 8 governorates. Monitoring on the implementation of HPS initiative and maintenance of health and hygiene education in the 150 schools revealed poor environmental indicators. Launching of the results of study on students health status and environmental assessment was conducted in Iraq on the 11 May 2009 with the participation of representatives from MoH,MoE ,MoHE and Ministry of Environment and other stakeholders Four refreshing training courses were conducted in Baghdad, Anbar and Wasit for 62 teachers (36 males and 26 females) on psychosocial support to update their knowledge on health education and key health massages, communication skills and psychological first aid services Procurement of 46 desktops and printers for the 46 health promoting schools, 46 screening Audiometers , 100 white boards with accessories and 10,000 school bags and 5,000 Hygiene kits for students 2 refreshing training courses were conducted in Suliamania and Basrah in the LADP areas on HPS and psychosocial support to update their knowledge on health education and key health massages, communication skills and psychological first aid services. Two awareness campaign conducted in Missan and suliamania in 2 schools in LADP areas in which 65 community leaders and teachers within the school community attended ,and IEC materials were distributed. Also , two awareness campaigns conducted in Babil in which 64 community leaders and teachers within the school community were oriented on Health Promoting Schools (HPS) initiative and psychosocial support for students. Monitoring and evaluation of the implementation of HPS initiative and maintenance of health and hygiene at primary schools was conducted through 4 supervisory visits by MoH and MoE focal points in Wasit, Missan, Erbil and suliamania governorates Provision of 20 eye glasses and 5 hearing aids to students with visual and hearing difficulties Printing of IEC materials on health promoting Schools.( 10,000copies of Brochures and 10,000 note books on health promoting schools) and 1000 copies of the school health report in Arabic. The printing of the English version is in process. Monthly evaluation report is submitted by the project focal points on the progress of the implementation of the projects at governorate level besides the daily communication with MoH and MoE focal point to provide technical assistance and solutions for most of the difficulties facing the implementation process.