# United Nations Development Group Iraq Trust Fund

# Project #: B1-32

# Date and Quarter Updated: January - March 2009 (1st Quarter)

| Participating UN Organisation: UNICEF | Sector: Education |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Basra Directorates of Education in close collaboration with Ministries of Education Baghdad |

| Title | Integrated Community-based Services Project Basra |
| --- | --- |
| Geographic Location | Governorate: Basra Basra District (Hai Al Hadi, Hai Al Tanoma, Hai Al Qibla, Hai Al Zubair, Shat-al-Arab, Hai Al Qiblah, Kut Al Hajjaj, 5 mile) Al Qurnah District ( Hai Al Sharash, Hai Al Nussayr, Hai Al Salaam, Al Qurnah Centre) |
| Project Cost | US$ 1,755,155 |
| Duration | Original: 15/Oct/07 – 15/Oct/08 (12 months) 1st Extension: 15/Oct/08 – 31/Dec/08 2nd Extension: 31/Dec/08 – 15/Apr/09 3rd Extension: 15/Apr/09 – 30/Jun/09 |
| Approval Date (SC) | 4/Oct/07 | Starting Date | 15/Oct/07 | Completion Date | Original: 15/Oct/08; 1st Extension: 31/Dec/08; 2nd Extension: 15/Apr/09; 3rd Extension: 30/Jun/09 |
| Project Description | Provide an integrated package of community-based interventions to increase availability, quality and access to basic services in selected communities in Basra. Schools are identified in communities of Basra governorate as entry points for coordinated interventions in education, health and water and sanitation. |

Development Goal and Immediate Objectives

Improving access and quality of basic social services in disadvantaged communities through an integrated community approach. In selected communities in Basra governorate, Iraqi authorities will be able to fulfil their obligations towards vulnerable populations in terms of responding to their immediate needs for basic social services in a transparent and equitable manner in line with democratic principles and international human rights standards, contributing to the achievement of the following MDGs: enrolling all children in primary school (MDG-2), eliminating gender disparities in primary and secondary education (MDG-3), reducing by half the proportion of people without access to safe drinking water (MDG-7), reducing child mortality (MDG-4) and poverty reduction (MDG-1). Immediate Objectives are: Improve participation and retention as well as access to and quality of education in 13 schools in Basra Governorate; Improve access to potable water and sanitation services in the communities around the selected schools; Improve the quality of basic primary health and nutrition services in the communities around the selected schools; Assist parents, teachers, health workers, youth volunteers and other community members to provide psychosocial wellbeing for children.

| Outputs, Key activities and Procurement |
| --- |
| Outputs | The overarching output will be to upgrade 13 schools to Child-Friendly status; School participation and retention as well as access of primary school children will improve; Availability and improved quality of water and wastewater disposal will increase; Sanitary facilities for school children, especially for girls will be available; Selected Primary Health Care (PHC)/Maternal Child Health (MCH) units will be equipped with essential vaccines, basic medicines, and medical supplies/equipment; 2 PHC Centres (PHCCs) serving the 13 local communities will be rehabilitated; The quality of health and nutrition services will be enhanced through high quality training courses for 100 health workers serving the local communities; Quality psychosocial interventions will be available in child friendly spaces to support the holistic well-being of children in 13 communities; Local authorities’ capacities for planning, managing and monitoring the project will be strengthened, and communities are exercising ownership of the project. Parent Teacher Associations (PTAs) will be engaged in project implementation. |
| Activities | Improved school participation and retention of primary school children Procurement from inside Iraq and distribution of school furniture, recreational materials, school sanitation kits and garden kits to all selected schools; Establishment of safe recreational areas in all selected schools; Creation of school gardens at all selected schools. Availability and improved quality of water and wastewater disposal as well as sanitary facilities for school children, especially for girls will increase through: Training of all teachers in the selected schools in health and hygiene promotion; Hygiene promotion and community awareness campaigns in select communities. Sanitary facilities for school children, especially for girls will be available Rehabilitation/ construction of water and sanitary facilities in schools where required. Selected PHC/MCH units will be equipped with essential vaccines, basic medicines, and medical supplies/equipment Procurement and distribution of essential/basic medical supplies and equipment for PHCCs/ MCH units. 2 PHCCs serving the 13 local communities will be physically rehabilitated through: Physical rehabilitation of some PHCCs if required (based on the preliminary assessment of the facilities considered for this project); Training of PHC health workers on basic health and nutrition services, including growth monitoring and counselling activities for parents of children suffering from malnutrition, as well as systematic referral of all severe cases of malnutrition to nutrition rehabilitation centres. The quality of health and nutrition services will be enhanced through high quality training courses for 100 health workers serving the local communities Support community health and nutrition programmes through community volunteers (former community child care units), in order to strengthen growth monitoring, health and nutrition promotion and referral to PHCCs. This output will also be supported by UNICEF national country programme. Quality psychosocial interventions will be available in child friendly spaces to support the holistic well-being of children in 13 communities through; Supporting psychosocial training for teachers, health workers, parents, youth and other community members in psychosocial intervention and care for children and youth, as well as providing supplies for use in existing spaces (such as schools, PHCCs and youth centres) and in establishing child friendly spaces/psychosocial activities. Local authorities’ capacities for planning, managing and monitoring the project will be strengthened, communities are exercising ownership of the project and PTAs will be engaged in project implementation through: Conducting capacity building courses for relevant government authorities on planning, management and monitoring of area-based programmes; Conducting social mobilization around selected schools to activate PTAs and involve them in planning, implementation and monitoring of the project to the extent possible; while at the central level advocating for government support to the expanded role of PTAs. |
| Procurement (major items) | Recreational and sanitation kits and essential/basic medical supplies and equipment for PHCCs/ MCH units |

| Funds Committed | $ 1,676,598.65 | % of approved | 95.5% |
| --- | --- | --- | --- |
| Funds Disbursed | $ 1,271,540.95 | % of approved | 72.4% |
| Forecast final date | 30 June 2009 | Delay (months) | 8.5 months |

| Direct Beneficiaries | Number of Beneficiaries | % of planned (current status) |
| --- | --- | --- |
| Men | 200,000 people in the targeted communities | 100% |
| Women |  |  |
| Children | Children in 13 schools | 100% - 17,076 students (37% girls) including those in guest schools |
| IDPs |  |  |
| Others |  |  |
| Indirect beneficiaries |  |  |
| Employment generation (men/women) | 500 people | 100% |

| Quantitative achievements against objectives and results |
| --- |
| Availability and improved quality of water and wastewater disposal will increase | Rehabilitation of Al Faihaa Compact Treatment Unit (200 m3/hr) in Shatt Al Arab district in Basra governorate is ongoing | % of planned | 75% |
| Sanitary facilities for school children, especially for girls will be available | Rehabilitation of sanitation facilities in 13 schools agreed upon with the Directorate of Education (DoE) has been successfully completed, benefiting 17,076 students (37% girls) including those in guest schools Funds saved from rehabilitation works enabled the rehabilitation of an additional four schools - rehabilitation works are ongoing. | % of planned | 100% |
| Selected PHCCs/MCH units will be equipped with essential vaccines, basic medicines, and medical supplies/ equipment | Orders for procurement of supplies and equipment for PHCCs and MCH units developed in consultation with Directorate of Health (DoH) counterparts have been placed. | % of planned | 80% |
| Two PHCCs serving the 13 local communities will be physically rehabilitated | Rehabilitation of Al Qurna PHCC (as per Government request) was satisfactorily completed and handed over to the Government. | % of planned | 100% |
| The quality of health and nutrition services will be enhanced through high quality training courses for 100 health workers serving the local communities | Plans for capacity building by DoE Basra have been developed (jointly with the ICIC team in Basra) for improving the quality of health and nutrition services. Plans include support to community volunteers to improve growth monitoring, health and nutrition promotion and strengthening referral to PHCCs. Implementation of these plans has commenced. | % of planned | 50% |
| Quality psychosocial interventions will be available in child friendly spaces to support the holistic well-being of children in 13 communities | 244 teachers (67 male; 177 female) in the 13 schools have been trained on psychosocial care, and are now providing psychosocial support to 6,384 children in those schools. Plans have been developed to expand psychosocial support for children outside the schools through capacity building of other groups in the community including parents and local leaders. Partnerships and implementation arrangements for execution of these plans are being finalized. 28 children and youth (including nine females) have participated in awareness raising sessions on Principles, Concepts and Practices of child and youth participation. On-the-job training to manage the project and build a model for teacher trainings has been provided to officials from Ministries of Education and Labour and Social Affairs (MoE and MoLSA) jointly with the Ministry of Higher Education in Baghdad. | % of planned | 85% |
| Local authorities’ capacities for planning, managing and monitoring the project will be strengthened, communities are exercising ownership of the project, and PTAs will be engaged in project implementation | 18 Water and Sewerage Authority staff have strengthened skills in different thematic areas All supplies/ equipment for conducting routine wastewater testing and analysis have been delivered to the Sewage Lab in Basra 43 government staff have increased awareness of hygiene practices. Training of Water and Sewerage Engineers on WaterCAD and SewerCAD design software is ongoing. PTAs were established in the 13 schools by People in Need (PIN), a partner INGO, using different funding sources. | % of planned | 100% |

Qualitative achievements against objectives and results

Qualitative achievements will be assessed once the project is completed.

Main implementation constrains & challenges (2-3 sentences)

There was a delay in the commencement of rehabilitation work related to Al Faihaa Compact Treatment Unit due to the refusal by the successful bidder to commence work, citing the receipt of a low offer. The work was then awarded to the 2nd lowest bidder and work is ongoing as planned.

Annex.1:  Status of school rehabilitation in Basra

| No | Governorate | District (HIC) | Sub dis-village | School Name | Progress (%) |
| --- | --- | --- | --- | --- | --- |
| 1 | Basra | Al Basra | Hay Al-Hadi | Al Wahda Al arabiya | 100% |
| 2 | Basra | Al Basra | Hay Al-Hadi | Arafat | 100% |
| 3 | Basra | Al Basra | Al-Tanomah | Al Somod | 100% |
| 4 | Basra | Al Basra | Shat Al-Arab | Shat Al Arab | 100% |
| 5 | Basra | Al Basra | Hay Al-Hussain | Al Maseer Al Wahid | 100% |
| 6 | Basra | Al Basra | Hay Al-Qibla | Balqees | 100% |
| 7 | Basra | Al Basra | Al-Zubair | Al Jazira Al Arabiya | 100% |
| 8 | Basra | Al Basra | Hay Al-Qibla | Al Hussain | 100% |
| 9 | Basra | Al Qurnah | Al-Sharash Dist. | Al Sharash | 100% |
| 10 | Basra | Al Qurnah | Al-Sharash Dist. | Al Muthanna | 100% |
| 11 | Basra | Al Qurnah | Hay Al-Nusayr | Al Thura | 100% |
| 12 | Basra | Al Qurnah | Hay Al-Salam | Al Shema Al Arabiya | 100% |
| 13 | Basra | Al Qurnah | Al-Qurna center | Al Qurna | 100% |
| 14 | Basra | Al Basra | Shat Al-Arab | Sinjar | Ongoing |
| 15 | Basra | Al Basra | Hay Al-Hadi | Poor Saeed | Ongoing |
| 16 | Basra | Al Basra | 5Mile | Diyala | Ongoing |
| 17 | Basra | Al Basra | Kut Al-Hajaj | Al-Risafy | Ongoing |