CENTRAL FUND FOR INFLUENZA ACTION

PROGRAMME QUARTERLY PROGRESS UPDATE

as of 31 March 2009

| Participating UN or Non-UN Organization: | United Nations Office for the Coordination of Humanitarian Affairs – Pandemic Influenza Contingency (PIC) Regional hub for Southern Africa region | UNCAPAHI Objective(s) covered: | Objective 6: Continuity under pandemic conditions |
| --- | --- | --- | --- |
| Implementing Partner(s): | All funds will be managed and spent directly by OCHA; activities will be implemented together with UN and humanitarian country teams and governments in the Southern Africa region. |
| Programme Number: | CFIA-B10 |
| Programme Title: | OCHA Pandemic Influenza Contingency work programme for Southern Africa |
| Total Approved Programme Budget: | US$ 324,456 |
| Location: | Southern Africa region, based from the OCHA Regional Office in Johannesburg |
| MC Approval Date: | 14 November 2008 |
| Programme Duration: | 12 months | Starting Date: | 15 January 2009 | Completion Date: | 31 December 2009 |
| Funds Committed: | US$ 123,599 | Percentage of Approved: | 38% |
| Funds Disbursed: | US$ 123,599 | Percentage of Approved: | 38% |
| Expected Programme Duration: | One year | Forecast Final Date: | 31 December 2009 | Delay (Months): |  |

| Outcomes: | Achievements/Results: | Percentage of planned: |
| --- | --- | --- |
| UN and humanitarian country teams in Southern Africa more ready to maintain essential operations and assist their national host governments | PIC provided assistance to the UN Country Team (UNCT) in Botswana on multi-hazard emergency preparedness and response including pandemic preparedness. Collaboration has been initiated with WHO Office in Botswana to support the Government in revising the pandemic contingency plan. PIC provided guidance to UNCTs in Namibia and Mauritius in the finalization of their Pandemic preparedness plans. Mauritius carried out a table top exercise (TTX) on pandemic preparedness in 2008. PIC conducted a table top exercise in Namibia on 18 February 2009. 20 participants attended the TTX including UN Agencies such as UNDSS, UNICEF, FAO, WHO, UNDP, and the UNRCO, as well as the Red Cross. | 1 simulation was conducted (20% of target of 5) (Namibia) 3 countries used the simplified PIC planning framework for their pandemic contingency plans (Namibia, Botswana, Mauritius) (60% of target of 5) |
| Governments, UN and partners better prepared to support humanitarian response in a pandemic | PIC is working closely with UNISDR, OCHA regional offices and the African Union Commission to integrate Pandemic Preparedness into Disaster Risk Reduction Initiatives at regional, sub regional and national levels. Thanks to negotiation by PIC and IFRC, Pandemic Preparedness is to be part of the Agenda of the Second Africa Regional Platform Consultative Meeting for Disaster Risk Reduction which is to be held from 05 to 08 May 2009 in Nairobi. PIC and IFRC had a meeting to discuss the cooperation between the 2 organizations. It was agreed that PIC and IFRC will organize joint missions to countries in the region and share information on countries’ preparedness. |  |
| Governments in restricted capacity developing countries in Southern Africa improve their beyond-health preparedness for a sudden pandemic | In Botswana, PIC met the Disaster Management Department in the Office of the President and the Ministry of Health to advocate the importance of the “Whole-of-society Approach” on pandemic preparedness. It was agreed that a table top exercise for the Botswana Government, the UNCT and the SADC secretariat will be held on 22 April 2009. PIC has also initiated discussions with the SADC Secretariat to integrate pandemic preparedness into the regional health and population strategy. PIC met the Seychelles Government Disaster Risk Management Department and UNDP country office to explain the whole-of-society approach and discuss the conduct of a table top exercise on pandemic preparedness. It was agreed that the TTX will take place on 22 May 2009 in Seychelles. | 2 national disaster focal points were lobbied about integrating pandemic preparedness into their work (25% of target of 8) and 2 presentations were made to governments/regional organisations on multi sector preparedness (50% of target of 4) (Botswana and Seychelles) |

Qualitative achievements against outcomes and results:

With support from PIC, two countries in the region made successful bids to the CFIA small projects fund for UN Resident Coordinators, (Zambia and Mozambique) which will enable kick starting of multisectoral preparedness activity in those countries.

# Footnotes

The term “programme” is used for projects, programmes and joint programmes.