CENTRAL FUND FOR INFLUENZA ACTION

PROGRAMME QUARTERLY PROGRESS UPDATE

January 2009 – March 2009

| Participating UN or Non-UN Organization: | International Organization for Migration (IOM) | UNCAPAHI Objective(s) covered: | Objective 6: Continuity under pandemic conditions With reference to Objective 3: Human Health: Objective 5: Public information and communication for behavior change |
| --- | --- | --- | --- |
| Implementing Partner(s): | International Organization for Migration |
| Programme Number: | CFIA – B4 |
| Programme Title: | Pandemic Preparedness For Migrants And Host Communities |
| Total Approved Programme Budget: | $ 990,000 |
| Location: | Cambodia, Egypt, Thailand ,Vietnam with global coordination from Geneva, Switzerland |
| MC Approval Date: | 20 February 2008 |
| Programme Duration: | 12months | Starting Date: | February 2008 | Completion Date: | December 2008 |
| Funds Committed: | $ 990,000 | Percentage of Approved: | 100% |
| Funds Disbursed: | $ 840,144 | Percentage of Approved: | 85% |
| Expected Programme Duration: | 12 months | Forecast Final Date: | February 2009 | Delay (Months): | 1 |

| Outcomes: | Achievements/Results: | Percentage of planned: |
| --- | --- | --- |
| Pandemic preparedness for migrants and host communities | SWOT analysis of phase I activities were conducted in all locations. This information was shared during a team meeting in Geneva in February 2009. Each location shared its IEC material. Partners were invited to the IOM team meeting to share what they were doing in pandemic preparedness and state what they thought IOM should contribute towards | Completed |
| Qualitative achievements against outcomes and results: |
| During this reporting period in all project locations, SWOT analysis of phase I was conducted. Lessons learnt will improve activities in Phase II IOM continues to engage with partners at the International, Regional, National and District levels to promote the needs of migrants. |

# Footnotes

The term “programme” is used for projects, programmes and joint programmes.