JOINT PROGRAMME MONITORING REPORT

ENVIRONMENT AND CLIMATE CHANGE WINDOW

This report is due no more than 20 days following the end of the 2nd and 4thquarter. Please submit to the MDF-G Secretariat at: mdgf.secretariat@undp.org

Section 1: Identification and Joint Programme Status

- Joint Programme Identification and basic data

| Date of Submission: March 25, 2010 Submitted by: Name: Sinisa Rodic Title: National Programme Manager and Coordinator Organization: UNDP CO Bosnia and Herzegovina Contact information: srodic@undp.ba |  | Country and Thematic Window Bosnia and Herzegovina Environment and Climate Change |
| --- | --- | --- |
| MDTF Atlas Project No: 00058000 Project Award ID: 00048025 Title: “Mainstreaming environmental governance: Linking local and national action in Bosnia and Herzegovina” |  | Report Number: 1 Reporting Period: December 16, 2009 – December 31, 2009 Programme Duration: 36 months |
| Participating UN Organizations UNDP, UNEP, UNESCO, UNV and FAO |  | Implementing partners Ministry of Foreign Trade and Economic Relations, Council of Ministers BiH RS Ministry for Spatial Planning, Construction and Ecology FBiH Ministry of Ecology and Tourism |

| Estimated Budget Summary |
| --- |
| Total Approved Joint Programme Budget: | UNDP/UNV: 4,119,362.23 UNEP: 905,000.66 FAO: 311,969.02 UN RC: 163,531.07 Total: USD 5,449,862.99 |
| Total Amount of Transferred to date: | UNDP/UNV/UNESCO/RC: 847,729.32 UNEP: 373,474.64 FAO: 116,571 Total: 1,337,774.96 |
| Estimated Total Budget Committed to date: | UNDP/UNV/UNESCO/RC: 0 UNEP: 0 FAO: 0 Total: 0 |
| Estimated Total Budget Disbursed to date: | UNDP/UNV/UNESCO/RC: 0 UNEP: 0 FAO: 0 Total: 0 |

Beneficiaries

Direct Beneficiaries

| Indicate Beneficiary type (i.e. farmers, policy makers, SMEs, etc.) | No. Institutions | No. Women | No. Men | No. Ethnic Groups |
| --- | --- | --- | --- | --- |
| National/Entity Government (Environmental sector) | 1 national-level institution: BiH Ministry of Foreign Trade and Economic Relations (MoFTER) 2 entity-level institutions: FBiH Ministry of Tourism and Environment (MTE) RS Ministry of Spatial Planning, Construction and Ecology (MSPCE) | N/A | N/A | N/A |
| Local Government | Shortlisted 30 municipalities (% female) | N/A | N/A | N/A |
| CSOs | Local CSOs (% female) Environmental Organizations Associations of citizens Local Development Agencies Tourist Organizations | N/A | N/A | N/A |
| Citizens and other Beneficiaries |  | N/A | N/A | N/A |
| Media Journalists and Media workers |  | N/A | N/A | N/A |
| Total |  | N/A | N/A | N/A |

Indirect Beneficiaries

| Indicate Beneficiary type (i.e. farmers, policy makers, SMEs, etc.) | No. Institutions | No. Women | No. Men | No. Ethnic Groups |
| --- | --- | --- | --- | --- |
| National/Entity Government (Environmental sector) | 1 national-level institution: BiH Ministry of Foreign Trade and Economic Relations (MoFTER) 2 entity-level institutions: FBiH Ministry of Tourism and Environment (MTE) RS Ministry of Spatial Planning, Construction and Ecology (MSPCE) | N/A | N/A | N/A |
| Local Government | Shortlisted 30 municipalities (% female) | N/A | N/A | N/A |
| CSOs | Local CSOs (% female) Environmental Organisations Associations of citizens Local Development Agencies Tourist Organisations | N/A | N/A | N/A |
| Citizens and other Beneficiaries |  | N/A | N/A | N/A |
| Media Journalists and Media workers |  | N/A | N/A | N/A |
| Total |  | N/A | N/A | N/A |

Note: Because of the fact that this project officially began implementation on December 16, 2009 and that the reporting period ends on December 31, 2009, there was in reality only a 16-day period at the very beginning to have activities. Therefore, considering that the entire project team was not even at place by that time, few activities occurred, meaning no beneficiaries, and hence, both these tables have been filled in as “N/A” (“not applicable”).

- Joint Programme M&E framework

The template is taken from the JP document. Please, provide an updated Joint Programme M&E framework

The template below is from the JP document, no revision or update has been made during this period. It is expected that the revision of the M&E framework shall be undertaken during the inception phase,  2010.

| Expected Results (Outcomes & outputs) | Indicators (with baselines & indicative timeframe) | Means of verification | Collection methods (with indicative time frame & frequency) | Responsibilities | Risks & assumptions |
| --- | --- | --- | --- | --- | --- |
| JP Outcome 1. Improved local level environmental planning Output 1. Improved local level environmental planning 1.1 Effective local level participatory environmental planning mechanisms strengthened. 1.2 Cross-cutting environmental governance methodology integrated into local participatory planning processes. (UNDP-led multi-agency approach). 1.3 Strengthened capacity of 30 municipalities for environmental programming and planning (UNDP). 1.4 Thirty (30) Local Environmental Action Plans defined and agreed by municipal stakeholders (UNDP). | Indicator 1.1 No. of local coordinators trained in facilitation of local environmental planning and programming process and LEAP formulation Baseline: 0 Target: 30 | Training evaluation and reports | Immediately after each training event participants fill the evaluation sheets Training provider complete training report after training | UNDP | Evaluations sheets are not filled by participants ( the requirement to have evaluation sheets and training report should be part of ToR of training provider |
|  | Indicator 1.2 No. of civil servants trained in environmental planning and programming for including LEAP into budgetary formulation processes Baseline: 0 Target: 90 (3 per municipality) | Training evaluation and reports | Immediately after each training event participants fill the evaluation sheets Training provider complete training report after training | UNDP | Evaluations sheets are not filled by participants ( the requirement to have evaluation sheets and training report should be part of ToR of training provider |
|  | Indicator 1.3 No. of members of Local Action Group trained in LEAP planning and implementation Baseline: 0 Target: 150 (5 per municipality) | Training evaluation and reports | Immediately after each training event participants fill the evaluation sheets Training provider complete training report after training | UNDP | Evaluations sheets are not filled by participants ( the requirement to have evaluation sheets and training report should be part of ToR of training provider |
|  | Indicator 1.4 No. of LEAPs developed Baseline: 30 Target: 60 | Municipal Council decision on LEAP adoption | Local legal acts on Municipal Council decisions, once a year | UNDP | LEAP development process will take longer tima than planned ( to agree the process, steps and deadlines from very beginning of the process |
|  | Indicator 1.5 No. of participants actively participated in LEAPs development process Baseline: 0 Target: 300 (30per municipality) | Number of calls for participation per medium Participant lists of local LEAP development forums | Archive of call for participation, advertisements in newspapers. Participants will register their participation in LEAP forums, after each event immediately | UNDP | Low interest to participate in local environmental planning – to increase the interest via implementing small visible pilot projects |
| JP Outcome 2. Enhanced management of environmental resources and delivery of environmental services Output 2. Enhanced management of environmental resources and delivery of environmental services 2.1 Improved management of environmental resources in 30 municipalities. 2.2 Priority actions identified in LEAPs addressed in 30 municipalities. 2.3 Improved environmental, energy, water and sanitation services in 40 municipalities for the poor. | Indicator 2.1 No. of grants distributed for LEAP’s priority project implementation Baseline: 0 Target: 30 | MoUs/Contracts with municipalities/ grant-holders signed | From archive of grant decision making Board, once a year | UNDP | Risk not to have MoUs/Contracts is very low, as this is the basis for grant transfer |
|  | Indicator 2.2 % of grant matching funds provided by municipalities/other donors Baseline: N/A Target: 25% | Co-financing agreements signed | From archive of grant decision making Board, once a year | UNDP | Risk not to have co-financing agreements is very low, as this is the basis for grant transfer |
|  | Indicator 2.3 No. of projects implemented Baseline: 0 Target: 30 | Project Monitoring Reports, Annual Review Report | Field visits, twice a year | UNDP | Risk is unprofessionally implemented projects ( to provide project management training to Grant-Holders |
|  | Indicator 2.4 No. of developed and implemented preventive poverty risk systems Baseline: 0 Target: 30 | Project Monitoring Reports, field reports | Field visits, twice a year | UNDP | Risk is that less attention has been paid to poverty prevention ( to include poverty prevention requirements to ToR of service provider |
| JP Outcome 3. Increased national environmental awareness and action, localizing and achieving MDGs Output 3. Increased national environmental awareness and action, localizing and achieving MDGs 3.1 Documentation of the legal and institutional background for environmental governance at entity and state level. 3.2 Reliable environmental indicators (linked with poverty reduction) to inform entity and state policy development. 3.3 Increased public access to environmental information. 3.4 Expanded access to environmental finance. 3.5 Capacity development for greater implementation of environmental governance actions demonstrating innovation, poverty reduction and social inclusion approaches and addressing the achievement of MDG 6, 7 and 8 through improved service delivery. 3.6 Lessons and best practices from effective delivery documented and used to inform policy development. | Indicator 3.1: Use of Operational Environmental Information System; Baseline: Rudimentary and disconnected data Target: Environmental Operational Environmental Information system is fully functional, continuously updated and actively used – 50 visits per day | Environmental Information System Track Record, which includes user statistics e.g. number of users, size of databases, number of different projects using the database | From website logs on user statistics, once a month | UNEP | Summary of assumptions and risks for each result The risk is that Information system is programmed without keeping user statistics ( to include user statistics component to software development service provider |
|  | Indicator 3.2: DNA established and No. of CDM projects; Baseline: No DNA, no CDM projects Target: DNA fully functional, 10 CDM projects in operation | Project Monitoring Reports, Annual Review Reports | National legal documents once a year, DNA website once a month | UNDP | The risk is in lack of capacities to establish and operate DNA professionally ( adequate training needs assessment and training of responsible authorities |
|  | Indicator 3.3: State of the Environment Report; Baseline: 0 (No comprehensive state-level SoE) Target: 1 | Report | Report | UNEP | No major risks identified |
|  | Indicator 3.4: No. of innovation grants provided and projects implemented; Baseline: 0 Target: 10 | Project Monitoring Reports, Annual Review Reports | National legal documents once a year | UNDP | Risk is unprofessionally prepared project proposals and inadequate criteria for project selection ( providing training on project proposal and working out criteria of project selection in open participatory and transparent manner in close cooperation with key-stakeholders via consensus building process |

- Joint Programme Results Framework with financial information

The following table refers to the total cumulative joint programme implementation at the end of the semester, it is meant to be an update of your Results Framework included in your original programme document. You should provide a table for each output.

--

| JP output: 1.1 Please highlight the rate of delivery for each joint programme’s output: a. Less than 30% b. between 31%-50% c. between 51-60 d. between 61%-70% e. between 71%-80 d. More than 80% |
| --- |
| Programme Outputs | Activity |  | YEAR | UN AGENCY | RESPONSIBLE PARTY |  |  | Estimated Implementation Progress |
|  |  | Y1 | Y2 | Y3 |  | NATIONAL /LOCAL | Source of Funding | Budget description | Total amount Planned | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
| Output 1. Strengthened capacity of municipalities and CSOs to manage and participate in long-term sustainable environmental planning and management process | 1.1 Effective local level participatory environmental planning mechanisms strengthened. | 388,322 | 133,960 | 121,224 | UNDP UNV | UNDP | MDG-F | 1.1.1 Design, testing and choosing of context specific, poverty focused participatory planning method; Publishing the guidelines on participatory and inclusive planning method; Training needs assessment of local planning coordinators; Training of local planning coordinators; Establishing network of local development coordinators. | - | - | - | Less than 30% |
|  | 1.2 Cross-cutting environmental governance methodology integrated into local participatory planning processes | 285,850 | 134,224 | 112,217 | UNEP UNV FAO UNDP | UNDP | MDG-F | 1.2.1 Assessment of local environmental needs using participatory planning approaches, 1.2.2 Assessment of local integrated good governance training needs; 1.2.3 Data collection and input on land use planning to local integrated development processes. | - | - | - | Less than 30% |
|  | 1.3 Strengthened capacity of 30 municipalities for environmental programming and planning. | 110,911 | 102,866 | X | UNEP UNV UNDP | UNDP | MDG-F | 1.3.1 Develop selection criteria for environmental, social and poverty-reduction cost-benefit analysis; 1.3.2 Analysis of best practices on integrated assessment and planning; | - | - | - | Less than 30% |
|  | 1.4 Thirty (30) Local Environmental Action Plans defined and agreed by municipal stakeholders. | 48,696 | 69,497 | 54,867 | UNV UNDP | UNDP | MDG-F | 1.4.1 Development of LEAPs as part of local integrated planning process | - | - | - | Less than 30% |
| Output 2. Secured understanding of the necessity of sustainable management of natural resources within local communities and impr-o-ved link betwe-en local and state/e-ntity level policies | 2.1 Improved management of environmental resources in 30 municipalities. | 51,437 | 152,655 | 85,353 | UNV UNEP UNDP FAO | UNDP | MDG-F | 2.1.1 Implement key enhancements in the management of natural resources using multi-agency best-practice approaches; 2.1.2 Assisting canton/entity authorities to update the databases of natural resources; 2.1.3 Promoting sustainable use of natural resources | - | - | - | Less than 30% |
|  | 2.2 Priority actions identified in LEAPs addressed in 30 municipalities. | X | 1,136,073 | 18,636 | UNDP | UNDP | MDG-F | 2.2.1 Establish national funding mechanism for co-financing of LEAP priority projects and deliver thirty (30) grants ranging from $ 30,000-70,000 for the project implementation support | - | - | - | Less than 30% |
|  | 2.3 Improved environmental, energy, water and sanitation services in 30 municipalities for the poor. | 51,934 | 51,934 | 158,383 | UNV UNESCO UNDP | UNDP | MDG-F | 2.3.1 Build capacity for implementing poverty focused actions for biodiversity protection, clean energy, water supply and sanitation proposals | - | - | - | Less than 30% |
| Output 3. Strengthened capacity of state to manage local socio-economic development and engage key national partners - capacity of government in designing and implementing public investment budget strengthened | 3.1 Documentation of the legal and institutional background for environmental governance at entity and state level. | 52,644 | 25,928 | 21,639 | UNEP | UNDP | MDG-F | 3.1.1 Conduct desk review of existing legal-institutional framework, produce "road map" recommendations for MoFTER's position and advocacy activities | - | - | - | Less than 30% |
|  | 3.2 Reliable environmental indicators (linked with poverty reduction) to inform entity and state policy development. | 45,570 | 35,149 | - | UNEP FAO | UNDP | MDG-F | 3.2.1 Review existing NEAP indicators and produce new comprehensive framework; Produce comprehensive new indicator framework including data sources. | - | - | - | Less than 30% |
|  | 3.3 Increased public access to environmental information. | 37,744 | 103,141 | 102,463 | UNEP | UNDP | MDG-F | 3.3.1 Identify gaps (particular emphasis on environment-poverty linkages); Link, modify and update existing environmental databases/information sources in accordance with indicator framework; Conduct gap analysis for comprehensive environmental information system; Organizing stakeholder workshop on content and priorities for pilot State of the Environment Report; Select drafting team and advisory committee for SoE | - | - | - | Less than 30% |
|  | 3.4 Expanded access to environmental finance. | 54,962 | 524,785 | 522,946 | UNDP | UNDP | MDG-F | 3.4.1 Establish national funding mechanism for innovative projects linking environment and poverty; Establish governance structure and selection criteria for seed/innovation grants; Award grants (10) grants in average value of $ 90,000 for project implementation support and monitor/evaluate implementation. | - | - | - | Less than 30% |
|  | 3.5 Greater implementation of environmental governance actions demonstrating innovation, poverty reduction and social inclusion approaches and addressing the achievement of MDG 6, 7 and 8 through improved service delivery. | 10,819 | 30,349 | 30,349 | UNEP | UNDP | MDG-F | 3.5.1 Develop capacity needs assessment for MoFTER, the Inter-entity Environmental Committee and entity environmental Ministries; Develop capacity building strategy for MoFTER on priority areas such as environmental monitoring and reporting | - | - | - | Less than 30% |
|  | 3.6 Lessons and best practices from effective delivery documented and used to inform policy development. | 58,100 | 41,098 | 35,550 | UNEP | UNDP | MDG-F | 3.6.1 Establish project website; Develop electronic network linking municipalities and national authorities; Forming the database and network of national and international experts, who are able to answer to all requests from local stakeholders on priority issues | - | - | - | Less than 30% |
|  | Management (UNDP) | 118,290 | 108,017 | 107,732 |  | - | - | - | Less than 30% |
|  | Monitoring and Evaluation (UN RC BIH) | 42,494 | 41,210 | 79,826 |  | - | - | - | Less than 30% |
|  | 1,357,774 | 2,690,895 | 1,451,192 | Total | 0 | 0 | 0 | Less than 30% |

Section II: Joint Programme Progress

- Narrative on progress, obstacles and contingency measures

Please provide a brief overall assessment of the extent to which the programme components are progressing in relation to the outcomes and outputs expected for the reporting period. Please, refer only to progress in relation to the planned in the Joint Programme Document. Try to describe facts avoiding interpretations or personal opinions.

Are there difficulties in the implementation?  Yes No

If so, what are the causes of these difficulties? Please check the most suitable option

UN agency Coordination

Coordination with Government

Coordination within the Government (s)

Administrative (Procurement, etc) /Financial (management of funds, availability, budget revision, etc)

Management: 1. Activity and output management 2. Governance/Decision making (PMC/NSC) 3. Accountability

Joint Programme design

External to the Joint Programme (risks and assumptions, elections, natural disaster, social unrest, etc)

Other. Please specify:

Please, briefly describe (150 words) the current difficulties the Joint Programme is facing. Refer only to progress in relation to the planned in the Joint Programme Document. Try to describe facts avoiding interpretations or personal opinions.

Please, briefly describe the current external difficulties (not caused by the joint programme) that delay implementation. Try to describe facts avoiding interpretations or personal opinions.

Please, briefly explain (150 words) the actions planned to eliminate or mitigate the difficulties (internal and external) described in the previous text boxes. Try to be specific in your answer.

- Inter-Agency Coordination and Delivering as One

- Is the Joint Programme in line with the UNDAF? Please check the relevant answer

Yes No

- If not, does the Joint Programme fit into the national strategies?

Yes No

If not, please explain:

What types of coordination mechanisms and decisions have been taken to ensure joint delivery?

Are different joint programmes in the country coordinating among themselves? Please reflect on these questions above and add any other relevant comments if you consider it necessary:

Please provide the values for each category of the indicator table described below:

| Indicators | Baseline | Actual Value | Means of Verification | Collection methods |
| --- | --- | --- | --- | --- |
| Number of managerial practices (financial, procurement, etc) implemented jointly by the UN implementing agencies for MDG-F JPs. |  |  |  |  |
| Number of joint analytical work (studies, diagnostic) undertaken jointly by UN implementing agencies for MDG-F JPs. |  |  |  |  |
| Number of joint missions undertaken jointly by UN implementing agencies for MDG-F JPs. |  |  |  |  |

Please, provide additional information to substantiate the indicators value (150 words). Try to describe qualitative and quantitative facts avoiding interpretations or personal opinions.

- Development Effectiveness: Paris Declaration and Accra Agenda for Action

Are governments and other national implementation partners involved in the implementation of activities and the delivery of outputs?

Not involved

Slightly involved

Fairly involved

Fully involved

In what kind of decisions and activities is the government involved? Please check the relevant answer

Policy/decision making

Management:  budget procurement service provision

other, specify: Defining criteria, evaluations, workshops etc.

Are civil society and/or the private sector involved in the implementation of activities and the delivery of outputs?

Not involved

Slightly involved

Fairly involved

Fully involved

In what kind of decisions and activities are they involved? Please check the relevant answer

Policy/decision making

Management:  budget procurement service provision

other, specify: Active participation in creation of Local Environmental Action Plan document

Are citizens involved in the implementation of activities and the delivery of outputs?

Not involved

Slightly involved

Fairly involved

Fully involved

In what kind of decisions and activities are citizens involved? Please check the relevant answer

Policy/decision making

Management:  budget procurement service provision

other, specify: Participation in creation of Local Environmental Action Plan document

Where is the joint programme management unit seated?

National Government  Local Government UN Agency By itself other, specify: Entity Government

| Indicators | Baseline | Actual Value | Means of Verification | Collection methods |
| --- | --- | --- | --- | --- |
| % Of UN support to Government sector under the Joint Programme reported on the Government budget | 0 |  |  |  |
| % of funded Technical Assistance /Technical Cooperation that is coordinated with the country’s capacity development objectives and strategies. | 0 |  |  |  |

Briefly describe the current situation of the government, civil society, private sector and citizens on regards of ownership, alignment and mutual accountability of the joint programme. Try to describe facts avoiding interpretations or personal opinions.  Please be specific on the role of different actors (i.e. implementing partners, or third parties being sub-contracted for specific service delivery).

- Communication and Advocacy

Has the JP articulated an advocacy & communication strategy that helps advance its policy objectives and development outcomes?

Yes   No

Please provide a brief explanation of the objectives, key elements and target audience of this strategy (max. 250 words).

What concrete gains are the advocacy and communication efforts outlined in the JP and/or national strategy contributing towards achieving?

Increased awareness on MDG related issues amongst citizens and governments

Increased dialogue among citizens, civil society, local national government in relation to development policy and practice

New/adopted policy and legislation that advance MDGs and related goals

Establishment and/or liaison with social networks to advance MDGs and related goals

Key moments/events of social mobilization that highlight issues

Media outreach and advocacy

Others (use box below)

What is the number and type of partnerships that have been established amongst different sectors of society to promote the achievement of the MDGs and related goals?

Faith-based organizations     	 Number

Social networks/coalitions    	 Number

Local citizen groups                	 Number

Private sector 		      	Number

Academic institutions              	Number

Media groups and journalist   	Number

Others (use box below)          	Number

What outreach activities does the programme implement to ensure that local citizens have adequate access to information on the programme and opportunities to actively participate?

Focus groups discussions

Household surveys

Use of local communication mediums such as radio, theatre groups, newspapers, etc

Open forum meetings

Capacity building/trainings

Others

Section III: Millennium Development Goals

- Millennium Development Goals

The MDG-F main objective is to contribute to progress to the attainment of the Millennium Development Goals worldwide. This subsection aims to capture data and information on the joint programmes contribution to 1 or more Millennium Development Goals and its targets.

For this purpose the Secretariat has developed a matrix where you should link your joint programme outcomes to one or more Millennium Development Goal and Target. You should also select the most suitable indicators from your joint programme M&E framework as a measure of the Millennium targets selected. Please, refer to the example provided below.

| MDG # | Joint Programme Outcome | MDG Target # | MDG Indicators | JP Indicator |
| --- | --- | --- | --- | --- |
| Goal # 1, 6, 7 and 8 | JP Outcome 1. Improved local level environmental planning | Currently, the link between each JP outcome and MDG targets is not elaborated. “The joint programme will support the achievement of MDGs 1, 6, 7 and 8 in BiH.” JP Outcome 3 is to contribute to MDG Goal 6, 7, 8. |  |  |
|  | Joint Programme Outcome 2 |  |  |  |
|  | JP Outcome 2. Enhanced management of environmental resources and delivery of environmental services |  |  |  |
|  | Joint Programme Outcome 3 |  |  |  |
|  | JP Outcome 3. Increased national environmental awareness and action, localizing and achieving MDGs |  |  |  |

Additional Narrative comments

Please provide any other comments information or data you would like to communicate to the MDG-F Secretariat

# Footnotes

Please list all the partners actually working in the joint’s programme implementation, NGOs, Universities, etc.  If you are working with a large number of partners please annex the list.

This indicator has been adapted from the Paris Declaration

This indicator has been adapted from the Paris Declaration

# Text boxes

Progress in outcomes:

- In this reporting period (December 16, 2009 – December 31, 2009) there was no progress in relation to the outcomes.

Progress in outputs:

- In this reporting period (December 16, 2009 – December 31, 2009) there was no progress in relation to the outputs.

In this reporting period, UN Agencies were working on establishment of teams for the implementation of Joint Programme.

N/A

N/A

N/A

The government at State and Entity level is fully involved in the MDG-F programme. Besides their role in the PMC and NSC, the government will be involved in many programme activities such as: creation of criteria for selection of 30 LEAP municipalities, evaluation and selection of municipalities, defining criteria for small grants and innovative grants, DNA establishment and etc.

N/A

The Joint Programme overall aims to contribute to MDG Goals  1, 6, 7 and 8. However, the programme document does not describe clearly the link between each JP outcome with the MDG goals, targets, indicators, except mentioning MDG 6, 7, 8 in the outcome 3, output 3.5. Refinement of the M&E framework during the inception phase would clarify and if any specific linkages would be made.