# United Nations Development Group Iraq Trust Fund

# Project #:C10-09

# Date and Quarter Updated: June 2009 (2nd  Quarter)

| Participating UN Organisation: UNDP (Lead Agency) UNESCO, ILO, UNHABITAT, UNIFEM, WHO | Sector: Education |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Education and Ministry of Labour and Social Affairs |

| Title | Local Area Development Programme (LADP) / Area Based Development |
| --- | --- |
| Geographic Location | Governorate of Sulymaniyah: Sayid Sadiq & New Halabja districts Governorate of Babylon: Hillah district Governorate of Basrah: Mdaina district Governorate of Thi Qar: Chibayesh district Governorate of Missan: Maymouna district |
| Project Cost | US$ 30, 338,384 (of which UNESCO’s budget = US$ 3,235,570) |
| Duration | 31 months (Project was extended until 18th December 2009) |
| Approval Date (SC) | April 10, 2007 | Starting Date | May 1, 2007 | Completion Date | Project was extended until 18th Dec. 2009 |
| Project Description | Project Description The Programme will strengthen the abilities of local authorities in three areas in the north, centre and south to prepare and implement human rights based, gender sensitive local area development plans; stimulate local economic development and generate short term and sustainable long term employment; improve social and physical infrastructure using labour intensive approaches. |

Development Goal and Immediate Objectives

Development Goal: Improve living conditions and contribute to sustainable poverty reduction in the three selected areas in Iraq. Objective 1: Strengthen the capabilities of local authorities in three selected areas in the north, center and south to plan and manage reconstruction and development activities through the formulation and implementation of human rights based, gender sensitive local area development plans. Objective 2: Stimulate local economic development and generate short-term and sustainable long term employment in the three selected areas. Objective 3: Improve social and physical infrastructure using labour intensive approaches and the service delivery capabilities of local governments in the three selected areas.

| Outputs, Key activities and Procurement |
| --- |
| Outputs | (List in reference to the key immediate objectives) Comprehensive human rights based, gender sensitive local area development plans (LADPs) for three areas prepared and adopted by local authorities and stakeholders assisted by a team of UN agencies based on joint-participatory needs assessments. Strengthened coordination and communication mechanisms between central government and local authorities in the three areas. 2.1. Improved local business environment for small businesses in the three areas. 2.2. At least 80 new small enterprises and cooperatives established in three areas. 2.3. Enhanced employment skills for at least 1500 residents in three areas 3.1. 30 water and sanitation facilities and services improved in three areas 3.2. 9 primary educational facilities and programme activities improved in three areas 3.3. 12 health services centers and services improved in three areas. 3.4. 2500 housing units and 12 community facilities improved in three areas 3.5. Improved conditions for agriculture development and the promotion of environmental awareness including through 60 small infrastructures projects in three areas. 3.6. 30 community based electricity facilities and services improved in three areas 3.7. 9 damaged religious sites rehabilitated in three areas. |
| Activities | To rehabilitate physics, chemistry, biology labs & provide lab furniture in 8 schools To rehabilitate 3 Vocational Training Centers by providing workshops for training To build capacity of VTC staff by providing technical and pedagogical training. |
| Procurement (major items) | Lab Furniture and equipment to 8 schools (2) Suleimanya, (3) Hilla (3) Marshlands. Workshop equipment to 3 vocational training centres (1 in each governorate) |

| Funds Committed | US$ 1,537,919 | % of approved | 47.53% |
| --- | --- | --- | --- |
| Funds Disbursed | US$ 841,287 | % of approved | 26 % |
| Forecast final date | 18 December 2009 | Delay (months) | 10 months |

| Direct Beneficiaries | Number of Beneficiaries | % of planned (current status) |
| --- | --- | --- |
| Men | 1000 |  |
| Women | 500 |  |
| Children | ---- |  |
| IDPs | ---- |  |
| Others | ---- |  |
| Indirect beneficiaries | 3000 |  |
| Employment generation (men/women) | 1500 |  |

| Quantitative achievements against objectives and results |
| --- |
| Objective 1: Strengthen the capabilities of local authorities in three selected areas in the north, center and south to plan and manage reconstruction and development activities through the formulation and implementation of human rights based, gender sensitive local area development plans. | Refer to output 2.3: Two training workshops have taken place for staff of Vocational Training Centers The first one was held from 15-26 March 2009 and focused on training four VTC trainers from each area on Pedagogy and Technical training. The second workshop was conducted from 10- 21 May 2009 and focused on training 8 VTC staff members from each area on Life skills. | % of planned 80 % |  |
| Objective 2: Stimulate local economic development and generate short-term and sustainable long term employment in the three selected areas. | Refer to output 2.3: - Contracts have been signed for all equipment except the Automotive workshops which the contract is being prepared. It is expected that all equipment will be received September 2009. | % of planned 80 % |  |
| Objective 3: Improve social and physical infrastructure using labour intensive approaches and the service delivery capabilities of local governments in the three selected areas. | Refer to output 3.2: - Physics labs have been delivered to the three Directorates of Education in Sulaimanya, Hilla and Missan. Contracts for Chemistry and Biology labs and Lab furniture are being prepared. It is expected that all equipment will be received by September 2009. | % of planned 75 % |  |

Qualitative achievements against objectives and results

The VTC workshops will have to be up and running before any tangible conclusion can be made as to the qualitative achievements

Main implementation constrains & challenges (2-3 sentences)

One of the main aims of the project is to give support to the three specific areas of Sayyid Sadiq in Sulaimanya, Hilla in Babel, and Maymoona in the Marshlands. We have been informed by Ministry of Labour and Social Affairs in March 2009 that a decision has been made not to employ new staff and hence Maymoona VTC can not be opened. As a temporary arrangement UNESCO agreed to deliver equipment and train staff of Missan VTC (closest in the Area). Meanwhile meetings are taking place with the Local Steering Committee and MOLSA officials to open the Maymoona VTC as the VTC in Missan has already been rehabilitated by one of the NGOs.