# United Nations Development Group Iraq Trust Fund

# Project #:C10-06

# Date and Quarter Updated: April-June 2nd Quarter 2009

| Participating UN Organisation: UNOPS, ESCWA | Sector: Economic Reform and Diversification (ERDSOT) |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Labour and Social Affairs, Ministry of Municipalities and Public Works |

| Title | Governance in Support of Employment Creation (GEC) |
| --- | --- |
| Geographic Location | Basra Governorate Districts: Al Faw, Shat Al Arab, Al Khaseeb |
| Project Cost | US$ 4,126,284 |
| Duration | 18 months + 15 months extension-I + 6 month extension-II = 39 months in total The budget revision was approved on the 30th May 2007 |
| Approval Date (SC) | 16-Jul-06 | Starting Date | 1 August 2006 | Completion Date | Original date was 31 January 2008. Project Extended till October 31st , 2009 |
| Project Description | Unemployment and underemployment in Iraq remains one of the major concerns and the priorities of the newly established Government of Iraq. In its effort to assist the Government, UNOPS has designed a project addressing socio-economic local development through optimal employment generation and implementation of the pro-poor strategies at the local level. The project will provide an integrated package of the employment creation and income generation activities. The main components of the project are a) building capacity of the 3 selected municipalities in Basra governorate to effectively plan and manage rehabilitation and development activities with a special focus on employment generation and social protection, b) introducing community participation mechanism at the municipal level, c) short term employment creation through quick impact public works schemes and infrastructure rehabilitation, d) support to income generation activities, including vocational training and support to small business, in order to enhance long term employment opportunities. The project will be implemented in the Lower South, in Basrah governorate in coordination with the Ministry of Labor and Social Affairs, Basra Provincial Council and the Municipalities |

Development Goal and Immediate Objectives

The project has been developed within the framework of UN Cluster C (Governance and Human Development) and contributes to the Programme goal 1 to “Support economic and human development and sustainable management of resources” under the outcome “Enabling environment for sustainable employment opportunities and social protection for all” The project is consistent with the Basra Provincial Development Strategy, in particular the Objectives: 1) Seeking to achieve comprehensive economic development and 2) Completing and developing the infrastructure. As the main objective of the project is to reduce the levels of vulnerability through employment creation, it will contribute to the aims of MDG 1, which aims at eradicating extreme poverty and hunger. The overall objective of the project is to contribute to poverty reduction and sustainable livelihoods through optimal employment generation in all sectors at the local level, in particular, its objectives are: Objective 1: Promote broad participation, including for example the optimal participation of women, in decision-making processes for public works, rehabilitation and short term employment at the Municipal level. Objective 2: Optimize employment opportunities within the rehabilitation and reconstruction of social and economic infrastructures, using an employment-intensive approach. Objective 3: Support decentralised policies for a social safety net through a pilot phase in the Governorate of Basra Objective 4: Contribute to long term employment creation through support to income-generation activities

| Outputs, Key activities and Procurement |
| --- |
| Outputs | Outputs for Objective 1 1.1 Six Municipal Steering Committees established in three Districts of Basra Governorate 1.2 One Governorate Steering Committee established in Basra Governorate within the existing Provincial Council Reconstruction and Development Committee 1.3 Seven Technical Units set up in 3 Districts and Basra Governorate to support the Municipal and Governorate Steering Committees 1.4 Municipal and Governorate staff as well as Steering Committee staff trained in territorial and conflict management techniques 1.5 Established and operative Temporary Income Assistance Fund 1.6 Indicator to measure the participation of women in the municipal planning boards and steering committees Outputs for Objective 2 2.1 Establishment of four Multipurpose Technology Community Centres (implemented by ESCWA); 2.2 Drafted and implemented rehabilitation and development plans 2.3 Refurbished municipal public infrastructure 2.4 Establishment of Local Development Fund to support community infrastructure projects 2.5 Temporary Income for Labourers through the provision of up to US$ 250,000 Outputs for Objective 3 3.1 Established safety nets through implementation of the Safety Net Fund 3.2 Income generating activities made available and provided to the most vulnerable groups Outputs for Objective 4 4.1 Establishment of Rural Recovery Fund specifically designed and set-up to provide support for farming activities. 4.2 Small Business Support Fund developed to support income generation activities. 4.3 400 small farmers provided with support and to benefit from the rural recovery fund and tool kits 4.4 100 small businesses who will have been assisted through a grants scheme The below mentioned outputs are relevant to the Current Reporting period -Income generating activities made available and provided to the most vulnerable groups. -Temporary Income for Labourers through the implementation of the Public works activities and Infrastructural works |
| Activities | The below mentioned Activities are relevant to the Current Reporting period -Public works activities in Shatt Al-Arab / Park Water Feature construction -Public works activities in Al-Fao / Cornish Rehabilitation -Construction of Three Local Markets under the infrastructural works in Abu Al-Khaseeb District -Construction of Four Pedestrian Bridges under the infrastructural works in Abu Al-Khaseeb District - Loans disbursed to applicants who intend to start/develop their own business under the Micro-Finance components -GEC-ESCWA three Business Development Centres in Al-Fao, Shatt Al-Arab, and Abu-Al Khasseb has been set up ,equipped and operational providing Trainings to participants from the three Districts graduating an estimate of 80 participants every month |
| Procurement (major items) | NA |

# During the current reporting period:

| Funds Committed | 467,161USD (out of 3,865,665 committed during the whole project) | % of approved | 12 % (94% of the total budget has been committed) |
| --- | --- | --- | --- |
| Funds Disbursed | 169,285 USD (out of 3,567,790 disbursed during the whole project) | % of approved | 4.7 % (86% of the total budget has been disbursed) |
| Forecast final date | 31st October 2009 | Delay (months) | Extended 21 months |

| Direct Beneficiaries | Number of Beneficiaries | % of planned (current status) |
| --- | --- | --- |
| Men | NA |  |
| Women | NA |  |
| Children | NA |  |
| IDPs | NA |  |
| Others | NA |  |
| Indirect beneficiaries | NA |  |
| Employment generation (men/women) | NA |  |

| Quantitative achievements against objectives and results |
| --- |
| Infrastructure work in Al-FAO district | short term employment creation through quick impact public works schemes and infrastructure rehabilitation | % of planned | 60 % |
| Infrastructure works in Abu Al-khaseeb district | short term employment creation through quick impact public works schemes and infrastructure rehabilitation | % of planned | 60 % |
| Income generating activities made available and provided to the most vulnerable groups | Identify and select beneficiaries for micro loans assistance in line with the approved mechanism. (Loans disbursed) | % of planned | 100% |

| Qualitative achievements against objectives and results during the reporting period |
| --- |
| achievements | objectives |
| Infrastructure project in Al-FAO (Construction of Three Local Markets) | Optimize employment opportunities within the rehabilitation and reconstruction of social and economic infrastructures, using an employment-intensive approach. |
| Infrastructure project in Abu Al-khaseeb district (Construction of Four Pedestrian Bridges) | Optimize employment opportunities within the rehabilitation and reconstruction of social and economic infrastructures, using an employment-intensive approach. |
| Small Business Support Fund developed to support income generation activities to the most vulnerable groups. Beneficiaries for micro loans were identified and loans disbursed. | Contribute to long term employment creation through support to income-generation activities |

Main implementation constrains & challenges (2-3 sentences)

During the reporting period problems have been experienced stemming from delays of local Partners/ structures in Basra in providing comprehensive financial and technical reports. Collecting all the required information from the local implementing partners has taken significant effort and time. This further coincided with the resignation of a member of project staff due to family reasons.