# United Nations Development Group Iraq Trust Fund

# Project #:C10-06

# Date and Quarter Updated: January- March, 1st Quarter 2009

| Participating UN Organisation: UNOPS ESCWA | Sector: Economic Reform and Diversification (ERDSOT) |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Labour and Social Affairs, Ministry of Municipalities and Public Works |

| Title | Governance in Support of Employment Creation (GEC) |
| --- | --- |
| Geographic Location | [Basra Governorate} Districts: Al Faw, Shat Al Arab, Al Khaseeb |
| Project Cost | US$ 4,126,284 |
| Duration | 18 months + 15 months extension = 33 months in total The budget revision was approved on the 30th May 2007 |
| Approval Date (SC) | 16-Jul-06 | Starting Date | 1 August 2006 | Completion Date | Original date was 31 January 2008. New Closing date April 30th, 2009. |
| Project Description | Unemployment and underemployment in Iraq remains one of the major concerns and the priorities of the newly established Government of Iraq. In its effort to assist the Government, UNOPS has designed a project addressing socio-economic local development through optimal employment generation and implementation of the pro-poor strategies at the local level. The project will provide an integrated package of the employment creation and income generation activities. The main components of the project are a) building capacity of the 3 selected municipalities in Basra governorate to effectively plan and manage rehabilitation and development activities with a special focus on employment generation and social protection, b) introducing community participation mechanism at the municipal level, c) short term employment creation through quick impact public works schemes and infrastructure rehabilitation, d) support to income generation activities, including vocational training and support to small business, in order to enhance long term employment opportunities. The project will be implemented in the Lower South, in Basrah governorate in coordination with the Ministry of Labor and Social Affairs, Basra Provincial Council and the Municipalities |

Development Goal and Immediate Objectives

The overall objective of the project is to contribute to poverty reduction and sustainable livelihoods through optimal employment generation in all sectors at the local level, in particular: - Promote broad participation, including for example the optimal participation of women, in decision-making processes for public works, rehabilitation and short term employment at the Municipal level - Optimise employment opportunities through the rehabilitation and reconstruction of social and economic infrastructure, using an employment-intensive approach - Support decentralized policies for a social safety net through a pilot phase in the Governorate of Basra - Contribute to long term employment creation through support to income-generation activities

| Outputs, Key activities and Procurement |
| --- |
| Outputs | The below mentioned outputs are relevant to the Current Reporting period - Implemented the infrastructural Works in the SHATT AL-ARAB District For the Extension of Al-Aerfan Intermediate Schools for Boys and Shatt Al- Arab School for Girls. - Income generating activities made available and provided to the most vulnerable groups. - Business Development Trainings Conducted to enable participants to successfully start their business. |
| Activities | The below mentioned Activities are relevant to the Current Reporting period - Drafted the Plans, drawings and BoQs for the infrastructural Works in Al-FAO District for the Construction of Three Local Markets for the implementation phase expected to start April 1st ,2009 - Drafted the Plans, drawings and BoQs for the infrastructural Works in Abu Al-Khaseeb District for the Construction of Four Pedestrian Bridges for the implementation phase expected to start April 1st ,2009 -UNOPS Implementing contractor for the micro-loans component is collecting and analyzing data of applicants whom will be giving Micro-loans to start their own business. -GEC-ESCWA three Business Development Centres in Al-Fao, Shatt Al-Arab, and Abu-Al Khasseb has been set up ,equipped and operational providing Trainings to participants from the three Districts graduating an estimate of 80 participants every month - Loans will be disbursed to applicants who intend to start their own business |
| Procurement (major items) | NA |

# During the current reporting period:

| Funds Committed | 359,256 USD (out of 4,068,654 committed during the whole project) | % of approved | 8.9% |
| --- | --- | --- | --- |
| Funds Disbursed | 386,926 USD (out of 3,575,845 disbursed during the whole project) | % of approved | 11% |
| Forecast final date | 30 April 2009 | Delay (months) | Extended 15 months |

| Direct Beneficiaries | Number of Beneficiaries | % of planned (current status) |
| --- | --- | --- |
| Men | NA |  |
| Women | NA |  |
| Children | NA |  |
| IDPs | NA |  |
| Others | NA |  |
| Indirect beneficiaries | NA |  |
| Employment generation (men/women) | NA |  |

| Quantitative achievements against objectives and results |
| --- |
| Establishment of Three Multipurpose Technology Community Centres (implemented by ESCWA) | a) building capacity of the 3 selected municipalities in Basra governorate to effectively plan and manage rehabilitation and development activities with a special focus on employment generation and social protection, b) Support to income generation activities, including vocational training and support to small business, in order to enhance long term employment opportunities. | % of planned | 100% |
| Infrastructure project in Shat Al Arab district (Extension of Al-Aerfan Intermediate Schools for Boys and Shatt Al- Arab School for Girls) | short term employment creation through quick impact public works schemes and infrastructure rehabilitation | % of planned | 100% |
| Infrastructure project in Al-FAO (Construction of Three Local Markets) | short term employment creation through quick impact public works schemes and infrastructure rehabilitation | % of planned | 35% |
| Infrastructure project in Abu Al-khaseeb district (Construction of Four Pedestrian Bridges) | short term employment creation through quick impact public works schemes and infrastructure rehabilitation | % of planned | 35% |
| Contribute to long term employment creation through support to income-generation activities | support to income generation activities, including vocational training and support to small business, in order to enhance long term employment opportunities | % of planned | 25% |

| Qualitative achievements against objectives and results during the reporting period |
| --- |
| achievements | objectives |
| Drafted and implemented rehabilitation and development plans | short term employment creation through quick impact public works schemes and infrastructure rehabilitation |
| Small Business Support Fund developed to support income generation activities | short term employment creation through quick impact public works schemes and infrastructure rehabilitation |
| Income generating activities made available and provided to the most vulnerable groups. This was done through employment for public works in the districts. | short term employment creation through quick impact public works schemes and infrastructure rehabilitation |

Main implementation constrains & challenges (2-3 sentences)

- Problems with recruitment has been experienced following a number of staff resigning, mainly due to the security situation. -Problems have been experienced arising from delays on the behalf of local Partners/ structures in Basra in providing comprehensive financial and technical reports. Collecting all the required information from the local implementing partners has taken significant effort and time.