# United Nations Development Group Iraq Trust Fund

# Project #: C10-06

# Date and Quarter Updated: 4th quarter, October-December 2008

| Participating UN Organisation: UNOPS ESCWA | Sector: Economic Reform and Diversification (ERDSOT) |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Labour and Social Affairs, Ministry of Municipalities and Public Works |

| Title | Governance in Support of Employment Creation (GEC) |
| --- | --- |
| Geographic Location | Basra Governorate, Districts: Al Faw, Shat Al Arab, Al Khaseeb |
| Project Cost | US$ 4,126,284 |
| Duration | 18 months + 15 months extension = 33 months in total The budget revision was approved on the 30th May 2007 |
| Approval Date (SC) | 16-Jul-06 | Starting Date | 1 August 2006 | Completion Date | Original date was 31 January 2008. The project extension request was submitted in December 2007. Expected closing date – April 2009 |
| Project Description | Unemployment and underemployment in Iraq remains one of the major concerns and the priorities of the newly established Government of Iraq. In its effort to assist the Government, UNOPS has designed a project addressing socio-economic local development through optimal employment generation and implementation of the pro-poor strategies at the local level. The project will provide an integrated package of the employment creation and income generation activities. The main components of the project are a) building capacity of the 3 selected municipalities in Basra governorate to effectively plan and manage rehabilitation and development activities with a special focus on employment generation and social protection, b) introducing community participation mechanism at the municipal level, c) short term employment creation through quick impact public works schemes and infrastructure rehabilitation, d) support to income generation activities, including vocational training and support to small business, in order to enhance long term employment opportunities. The project will be implemented in the Lower South, in Basrah governorate in coordination with the Ministry of Labor and Social Affairs, Basra Provincial Council and the Municipalities. |

# Development Goal and Immediate Objectives

The overall objective of the project is to contribute to poverty reduction and sustainable livelihoods through optimal employment generation in all sectors at the local level, in particular: - Promote broad participation, including for example the optimal participation of women, in decision-making processes for public works, rehabilitation and short term employment at the Municipal level - Optimise employment opportunities through the rehabilitation and reconstruction of social and economic infrastructure, using an employment-intensive approach - Support decentralized policies for a social safety net through a pilot phase in the Governorate of Basra - Contribute to long term employment creation through support to income-generation activities

# Outputs, Key activities and Procurement

| Outputs | 1.1 Three Municipal Steering Committees established in three Districts of Basra Governorate |
| --- | --- |
|  | 1.2 One Governorate Steering Committee established in Basra Governorate within the existing Provincial Council Reconstruction and Development Committee |
|  | 1.3 Three Technical Units set up in 3 Districts and Basra Governorate to support the Municipal and Governorate Steering Committees |
|  | 1.4 Municipal and Governorate staff as well as Steering Committee staff trained in territorial and conflict management techniques |
|  | 1.5 Established and operative Temporary Income Assistance Fund |
|  | 1.6 Indicator to measure the participation of women in the municipal planning boards and steering committees |
|  | 2.1 Establishment of three Multipurpose Technology Community Centres (implemented by ESCWA); |
|  | 2.2 Drafted and implemented rehabilitation and development plans |
|  | 2.3 Refurbished municipal public infrastructure |
|  | 2.4 Establishment of Local Development Fund to support community infrastructure projects |
|  | 2.5 Temporary Income for Labourers through the provision of up to US$ 360,000 |
|  | 3.1 Support to safety nets through implementation of the income generation activities |
|  | 3.2 Income generating activities made available and provided to the most vulnerable groups |
|  | 4.1 Small Business Support Fund developed to support income generation activities. |
|  | 4.4 100 small businesses who will have been assisted through a grants scheme |
| Activities | People from the community and local authorities have been trained by UNOPS/ILO-ITC in Turin-Italy to increase and improve their capacities to ensure the community participation in Territorial Diagnosis & Institutional Mapping. Preparing " Territorial Diagnosis & Institutional Mapping" for the three districts Public works, which include constructing public parks in Fao and Abi Khasib districts, and rehabilitating the riverside in Shat Al Arab. This will be done through employing unemployed people in these districts, 12000 working days in each Infrastructure projects which the local partners in the districts together with community participation have selected. The projects selected are a local market in Fao, 4 pedestrian bridges in Abi Khasib, and building extra classrooms in 2 schools in shat Al Arab Mobile training workshops at which people from the districts are trained vocationally. The trainees will be later provided with tool kits Loans will be disbursed to applicants who intend to start their own business. Multi-purpose training centres have been established in Fao, Abi Khasib and Shat Al Arab districts. These are concerned with small business development. |
| Procurement (major items) | - 3 Mobile Training workshops - 3 Tents & a Truck - Tool Kits for training workshops - 6 Flatbeds - IT Equipments for 3 districts |

| Funds Committed | 3.709.398 USD | % of approved | 90 |
| --- | --- | --- | --- |
| Funds Disbursed | 3.188.919 USD | % of approved | 77 |
| Forecast final date | April 2009 | Delay (months) | Extended 15 months |

# Quantitative achievements against objectives and results

| Three Municipal Steering Committees established in three Districts of Basra Governorate | a) building capacity of the 3 selected municipalities in Basra governorate to effectively plan and manage rehabilitation and development activities with a special focus on employment generation and social protection, b) introducing community participation mechanism at the municipal level, | % of planned | 100 |
| --- | --- | --- | --- |
| One Governorate Steering Committee established in Basra Governorate within the existing Provincial Council Reconstruction and Development Committee | a) building capacity of the 3 selected municipalities in Basra governorate to effectively plan and manage rehabilitation and development activities with a special focus on employment generation and social protection, b) introducing community participation mechanism at the municipal level, | % of planned | 100 |
| Three Technical Units set up in 3 Districts and Basra Governorate to support the Municipal and Governorate Steering Committees | a) building capacity of the 3 selected municipalities in Basra governorate to effectively plan and manage rehabilitation and development activities with a special focus on employment generation and social protection, | % of planned | 100 |
| ((32)) Municipal and Governorate staff as well as Steering Committee staff trained in territorial and conflict management techniques | a) building capacity of the 3 selected municipalities in Basra governorate to effectively plan and manage rehabilitation and development activities with a special focus on employment generation and social protection, | % of planned | 100 |
| 3 TDIM in three distracts was completed | building capacity of the 3 selected municipalities in Basra governorate to effectively plan and manage rehabilitation and development activities with a special focus on employment generation and social protection, | % of planned | 100 |
| Established and operative Temporary Income Assistance Fund | a) support to income generation activities, including vocational training and support to small business, in order to enhance long term employment opportunities. | % of planned | 85 |
| participation of 6 women in the municipal planning boards and steering committees | introducing community participation mechanism at the municipal level | % of planned | 100 |
| Establishment of Three Multipurpose Technology Community Centres (implemented by ESCWA) | a) building capacity of the 3 selected municipalities in Basra governorate to effectively plan and manage rehabilitation and development activities with a special focus on employment generation and social protection, b) support to income generation activities, including vocational training and support to small business, in order to enhance long term employment opportunities. | % of planned | 100 |
| Drafted and implemented rehabilitation and development plans for three parks | short term employment creation through quick impact public works schemes and infrastructure rehabilitation | % of planned | 100 |
| an infrastructure project in Shat Al Arab district has been completed | short term employment creation through quick impact public works schemes and infrastructure rehabilitation | % of planned | 100 |
| Two infrastructure projects in Abi Khasib and Fao districts will be implemented | short term employment creation through quick impact public works schemes and infrastructure rehabilitation | % of planned | 50% |
| Temporary Income for Labourers through the provision of up to US$ 360.000 | short term employment creation through quick impact public works schemes and infrastructure rehabilitation | % of planned | 98 |
| 100 small businesses who will have been assisted through a grants scheme | support to income generation activities, including vocational training and support to small business, in order to enhance long term employment opportunities | % of planned | 90 |

# Qualitative achievements against objectives and results

| Achievements | Objectives |
| --- | --- |
| Municipal and Governorate staff as well as Steering Committee staff trained in territorial and conflict management techniques | a) building capacity of the 3 selected municipalities in Basra governorate to effectively plan and manage rehabilitation and development activities with a special focus on employment generation and social protection, |
| Drafted and implemented rehabilitation and development plans | short term employment creation through quick impact public works schemes and infrastructure rehabilitation |
| Small Business Support Fund developed to support income generation activities. | support to income generation activities, including vocational training and support to small business, in order to enhance long term employment opportunities |
| The community participation and gender balance have been achieved at the municipal level through involving people representing different groups of the community and ensuring that women participate in decision-making concerning issues and proposals related to the development of the districts | Introducing community participation mechanism at the municipal level. |
| Income generating activities made available and provided to the most vulnerable groups. This was done through employment for public works in the districts. | short term employment creation through quick impact public works schemes and infrastructure rehabilitation |