# United Nations Development Group Iraq Trust Fund

# Project No.:  C9-18

# Date and Quarter Updated:  October-December 2008

Participating UN Organisation: UNDP Sector: Governance Government of Iraq – Responsible Line Ministry: Board of Supreme Audit

| Title: | Institutional Strengthening Programme for the Supreme Audit Board |
| --- | --- |
| Geographic Location: | Iraq (country wide) |
| Project Cost: | 4,879,535 USD |
| Duration: | 2006.01 to 2009.03 |
| Approval Date (SC): | 2005.10.29 | Starting Date: | 2006.01.01 | Completion Date: | 2009.03.31 |
| Project Description: | Institutional strengthening programme to promote transparency and more efficient management of public funds. |

# Development Goal and Immediate Objectives:

The project aims to promote good governance, honesty, transparency and accountability in the use and management of public resources by strengthening the capacity of the BSA of Iraq, realizing the outcome “Strengthening Institutional and Administrative Infrastructure” in the UN-Iraq Assistance Strategy Matrix. The project’s main objectives are: Conduct and complete a Training Needs Assessment of the BSA; Develop research, using international experiences on money laundering to establish future audit programmes (assessment of Australian & Canadian); Conduct off-the-shelf short-term courses around the Arab region for 269 auditors in the following priority areas: 1) Performance Audit; Short Train-the-Trainer programme; 2) Debt Accounting & Audit; 3) Fraud Detection Audit; 4) Aid Management and Coordination Audit, Short Train-the-Trainer programme; 5) Procurement & Contract Management Audit; 6) International Standards & Guidelines; 7) Privatization Audit; Short Train-the-Trainer programme; 8) IT Audit; 9) ISO 9001 Certification (Quality Control & ISO certification); and, 10) Financial Audit; Conduct Train-the-Trainer workshops to develop the long-term training programme for 3 groups of 30 audit practitioners each in the following areas: 1) Financial auditing and fraud detection – Revenue and expenditure; 2) Computer auditing; and, 3) Performance audit; Enhance the capabilities of 30 technicians to coordinate and support the introduction of the audit operations’ computerization and BSA’s administrative systems; Develop and disseminate the following: 1) Audit guidance on the training activities referred above; and, 2) Code of conduct to BSA based on INTOSAI code of ethics; Adapt and disseminate BSA guide on fraud awareness and detection; Ensure the sustainability of BSA Iraq’s capacity reinforcement.

# Outputs, Key activities and Procurement

| Outputs: | The project’s outputs are: Comprehensive Training Needs Assessment conducted covering 18 regional offices. Research paper and recommendations to be drafted and presented on ‘money laundering’ audit programmes for BSA. Ten (10) short-term courses to be conducted for 269 auditors over 44 weeks. Three (3) teams of 30 Functional Responsibility Leaders (FRLs) assigned in the fields of financial audit and fraud detection, computer auditing and performance auditing. The FRLs to develop long-term customized training programmes on the above noted subject matters. Three (3) standardized course manuals developed on the subject matters noted in 4.1. A group of thirty (30) technicians assigned, who will be capable of coordinating and supporting the initiation of the BSA operations’ computerization; and a guide produced to facilitate this computerization. Audit guidance and Ethics Code manual developed and disseminated. The guide on fraud awareness and detection adapted and disseminated. Three (3) experimental audits conducted. The Institutional Strengthening Committee (ISC) and workgroup formed. A secretariat established to support BSA’s needs in coordinating future activities with donor agencies. BSA (strategic and operational) institutional strengthening plan developed. |
| --- | --- |
| Activities: | Comprehensive Training Needs Assessment Study Tour on Money Laundering Performance Audit Course Debt Accounting and Audit Course Fraud Detection Audit Course Aid Management and Co-ordination Audit Course Procurement and Contract Management Audit Course International Standards and Guidelines Course Privatisation Audit Course Information Technology Audit Course Incomplete Records Audit Course Financial Audit Course Long Term Training Programme IT Technician Training Workshop Institutional Computerisation Guide Electronic Document Management System Audit Guides Code of Conduct Fraud Awareness and Detection Guide Experimental Audits Institutional Strengthening Committee Training and Donor Aid Co-ordination Secretariat Institutional Strengthening Plan |
| Procurement: (major items) | Electronic Document Management System Video-conference equipment |

| Funds Committed | 100 | % of approved |  |
| --- | --- | --- | --- |
| Funds Disbursed | 82.78 | % of approved |  |
| Forecast final date | 2009.03.31 | Delay (months) | 24 months |

# Quantitative achievements against objectives and results

| Comprehensive Training Needs Assessment Study Tour on Money Laundering Performance Audit Course Debt Accounting and Audit Course Fraud Detection Audit Course Aid Management and Co-ordination Audit Course Procurement and Contract Mgt Audit Course International Standards and Guidelines Course Privatisation Audit Course Information Technology Audit Course Incomplete Records Audit Course Financial Audit Course Long Term Training Programme IT Technician Training Workshop Institutional Computerisation Guide Electronic Document Management System Audit Guides Code of Conduct Fraud Awareness and Detection Guide Experimental Audits Institutional Strengthening Committee Training and Donor Aid Co-ordination Secretariat Institutional Strengthening Plan | 100 0 100 0 100 100 100 100 100 100 100 100 100 100 100 50 100 100 100 100 100 100 100 | % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned % of planned |  |
| --- | --- | --- | --- |

# Qualitative achievements against objectives and results

Output – Incomplete Records Audit training Course A two-week training course was given in incomplete records auditing for twenty-four auditors from the BSA in Amman, Jordan from October 30 to November 9, 2007. Audit and training experts from the National Audit Office of the United Kingdom prepared and delivered the course. The course provided auditors with improved skills in the basics of financial auditing and auditing in an environment of incomplete records. An improved skill set in the area will enable BSA auditors to better cope with instances where circumstances dictate that work be completed in offices where some records may be missing. Output – Development of an Institutional Strengthening Plan An international expert in institutional strengthening of Supreme Audit Institutions was hired and brought to Amman in December 2006 to work with the BSA to develop an institutional strengthening plan (i.e. a strategic development plan) charting the BSA’s capacity building course over the next three years. The plan was finalised at the end of the year. In early 2007, the team re-assembled in Amman and used the plan as the basis for developing a project document and funding request for the second phase of the programme. Output – Training of a Staff Member of the BSA’s Training Secretariat In December 2006, the BSA delegated one of its staff to the UNDP/Iraq office. This staff member worked alongside the UNDP/Iraq’s project manager as part of a planned project activity whereby the BSA’s institutional capacities are strengthened through “on-the-job” training. This activity would ensure a smoother transition of duties and responsibilities from the UNDP-Iraq to the BSA in the future. Output – Development of the Project Document/Funding Proposal for Phase 2 An international expert in institutional strengthening of "Supreme Audit Institutions" was hired and brought to Amman in January 2007 to work with the BSA to develop a project document/funding proposal for the second phase of the project. The project document, developed in Dec.2006, is based on the institutional strengthening plan (i.e. a strategic development plan) for 2008-10. Output – Purchase of IT and A/V Equipment for the BSA Training Secretariat Two laptops and an electronic video projector were purchased for the BSA’s training secretariat. Output – Oracle Developer Training Course A three-week training course on the Oracle Developer enterprise system for eighteen (18) information technology technicians from the BSA was given in Amman, Jordan from February 18 to March 8, 2007. The course was prepared and delivered by a private sector firm specialising in these types of systems and this type of training. Output – Fraud Prevention and Detection Audit Course (Technical Module) A two-week technical training course in fraud prevention and detection audit for twenty-seven (27) auditors from the BSA was given in Amman, Jordan from February 19 to March 1, 2007. The course was prepared and delivered by audit and training experts from the "National Audit Office" of the United Kingdom. Output – Financial Audit Course A two-week technical training course in financial audit for twenty-nine (26) auditors from the BSA was given in Cairo, Egypt from February 25 to March 8, 2007. The course was prepared and delivered by audit and training experts from the Central Auditing Organisation of Egypt. In parallel to the technical training module, the train-the-trainer module of this course for eighteen (18) auditors from the BSA was given in Cairo from February 25 to March 22, 2007, also by the Central Auditing organisation. Output – Procurement Audit Course (Technical Module) A two-week technical training course in procurement audit for twenty-seven (28) auditors from the BSA was given in Amman, Jordan from April 9 to 19, 2007. The course was implemented in cooperation with the World Bank while the course material was prepared and delivered by audit and training experts from the International Labour Organisation-International Training Centre and the Court of Accounts of Morocco. Output – International Accounting and Auditing Standards Course (Technical Module) A two-week technical training course in international accounting and auditing standards for thirty-nine (39) auditors from the BSA was given in Amman, Jordan from April 16 to 26, 2007. The course was prepared and delivered by audit and training experts from the National Audit Office of the United Kingdom. Output – International Accounting and Auditing Standards Course (Train-the-Trainer Module) A one-week train-the-trainer training course in international accounting and auditing standards for eighteen (18) auditors from the BSA was given in Amman, Jordan during June 3 - 7, 2007. The course was prepared and delivered by audit and training experts from the "National Audit Office" of the United Kingdom. Output – Information Technology Audit Course A training course in information technology audit for twenty-four (24) auditors from the BSA was given in Noida, India during June 11 -30, 2007. The course was prepared and delivered by audit and training experts from the Office of the Comptroller and Auditor General of India. Output – Training of a Staff Member of the BSA Training Secretariat The BSA delegated one of its Training Secretariat staff to the UNDP/Iraq office for the period of December 2006 to August 2007. This staff member worked alongside the UNDP/Iraq’s project manager as part of a planned project activity whereby the BSA’s institutional capacities are strengthened through “on-the-job” training. This activity will ensure a smoother transition of duties and responsibilities from the UNDP/Iraq to the BSA in the future. Output – Performance Audit Course (Technical and Train-the-Trainer Modules) A two-week technical training course in performance auditing for twenty-nine (29) auditors from the BSA, followed immediately by a four-week train-the-trainer module for eighteen (18) auditors, was given in Tunis, Tunisia from August 20 to September 28, 2007. The course was prepared and delivered by audit and training experts from the Court of Accounts of Tunisia. Output – Fraud Prevention and Detection Audit Course (Train-the-Trainer Module) A two-week train-the-trainer course in fraud prevention and detection auditing for eighteen (18) auditors from the BSA was given in Amman, Jordan from October 21 to November 1, 2007. The course was prepared and delivered by audit and training experts from the "National Audit Office" (NAO) of the United Kingdom. Output – Pilot Audit Workshop Six (6) auditors from the BSA travelled to NAO offices in the United Kingdom for a one week workshop from November 26 to 30, 2007. This was the first of four workshops that aim to help the BSA to develop institutional audit programmes that comply with international standards, to prepare for a pilot (test) audit, to obtain feedback on the conduct of the pilot audit during the exercise and to get guidance on the completion of the audit. Output – Institutional Strengthening Committee Meeting A meeting was held on December 9-10, 2007 between representatives of the BSA, the UNDP/Iraq, the World Bank, the National Audit Office of the United Kingdom, the Central Audit Organisation of Egypt, the Audit Bureau of Jordan, the Comptroller and Auditor General of India and the United States Department of State. During the first part of the meeting, the delegates analysed the activities that had already been delivered and identified areas of improvement for the future. The second half of the meeting focused on the contributions that the various technical partners could make during the second phase of the BSA programme. Output – Institutional Fraud Awareness Workshop A four-day institutional fraud awareness workshop was delivered to eighteen managers and directors of the BSA in Amman, Jordan during December 11 -16, 2007. The workshop covered the role of the supreme audit institution in a country’s overall accountability and transparency framework, the institutions relationship with other government entities, civil society and the public covered a practical case of fraud detection. Output – Institutional Fraud Awareness Guide A team of five BSA directors spent three days with an international supreme audit institution capacity building expert during December 17 - 19, 2007 in Amman, Jordan. The group drafted a structure for an institutional fraud awareness guide. This was the first of four such meetings, at the end of which the guide and a complementary fraud detection audit plan applicable for all BSA audits would be completed. Output – Fraud Manual Working Meetings (3) The middle two of three fraud manual development working meetings were held in Amman, Jordan August 6 - 7, 2008. The working meetings were held between four dedicated senior audit officers of the BSA and an international expert in institutional fraud awareness. The meetings convened to complete work on an ‘Institutional Fraud Awareness Guide’ being developed for the BSA. Output – Pilot Audit Workshops (3) The middle three of four pilot audit workshops were held in London, England July 21 - 25, 2008. Six senior audit officers, chosen to be pilot audit champions within the BSA, attended the meetings. The knowledge taken from the workshops has lead to significant improvements in national capacity for auditing. Output – Procurement Audit Course (Train-the-Trainer Module) A two-week train-the-trainer course in procurement audit for nineteen (19) auditors from the BSA and OFM was given in Turin, Italy at the ITCILO Center. The course was implemented in cooperation with the World Bank while the course material was prepared and delivered by audit and training experts from the International Labour Organisation-International Training Centre and the Court of Accounts of Morocco. Output – Institutional Meeting of BSA President with National Audit Office of the U.K A one week meeting between the BSA President and the National Audit Office of the United Kingdom was held in London, UK during December 8 - 16, 2008. The meeting discussed current technical cooperation with the Iraqi Board of Supreme Audit (BSA), as well as determining the prospects for future cooperation as we move into Phase Two of the Institutional Strengthening Project of the BSA. Output -Anticorruption and Integrity Awareness Workshop for Inspector-Generals (IG) A one week workshop on Anticorruption and Integrity Awareness was held in Amman, during 2 - 6 November 2008; sixteen 16 Inspector-Generals participated, and discussed legal frameworks and powers of IGs, fraud detection, etc.