Eight Six-month progress report for project

# REPORT COVER PAGE

| Participating UN Organization: |  | Cluster: |
| --- | --- | --- |
| UNDP |  | C – Governance and Human Development |

| Project No. and Project Title: |  | Report Number: |
| --- | --- | --- |
| C9-21a: Strengthening of the Constitutional Process and Good Governance |  | 3 |

| Reporting Period: |  | Project Budget [and revision if applicable]: |
| --- | --- | --- |
| 1 January – 30 June 2008 |  | US$ 4 Million |

| List Implementing Partners: |  | Geographic Coverage/Scope: |
| --- | --- | --- |
| UNDP-Programme On Governance in the Arab Region (UNDP-POGAR) Higher Judicial Council (HJC) Ministry of Justice (MoJ) Iraqi High Tribunal (IHT) Judicial Training Institute (JTI) Ministry of Human Rights (MoHR) Iraqi National Assembly (INA) NGO Coordination Committee in Iraq (NCCI) National Centre for Consultancy and Management Development, Ministry of Planning and Development Cooperation (NCCMD) UN Economic and Social Commission for Western Asia (UNESCWA) Canadian International4 Development Agency (CIDA) Team International Turin Training Centre |  | National Coverage – Ministries & Parliament Baghdad – National Dialogue Community Initiatives |

| Abbreviations and acronyms: |  | Project Status: Duration/Closed Project/Timeline Extension: |
| --- | --- | --- |
| List the main abbreviations and acronyms that are used in the report. |  | 12 months Extension to 15 March 2009 obtained |

# Purpose

1.1.The overall development objective of this project is to:

Support the planning and implementation of the Iraqi Constitution and help the establishment and/or strengthening of key institutions that are necessary to help build a democratic and effective system of governance in Iraq, and

Promote national dialogue among key constituencies to diffuse tension and promote cross-community collaboration aimed at fostering inclusiveness, public participation (of all the regions) and transparency.

The first key objective of this programme is the establishment and strengthening of priority institutions and Ministries such as the National Centre for Consultancy & Management Development, National Human Rights Commission, the Judiciary, Parliament, Ministry of Human Rights, Ministry of Interior and Ministry of Justice to build their capacity to advance the rule of law, to promote human rights, and to ensure transparent public administration and good governance. 

The second objective is to increase national dialogue on reconciliation and regional and cross community collaboration, enhancing development and reconstruction.

1.2 This programme aims at strengthening the rule of law in Iraq, by building the capacity of judicial and legal institutions; supporting locally led management reforms of Iraqi public institutions that contribute to an effective, efficient, responsive, and transparent public sector, within the current context of political instability in Iraq; and strengthening the promotion and protection of human rights.

Under Security Council Resolution 1770, passed on August 10, 2007, the Security Council reinforces the United Nations mandate in Iraq to promote the protection of human rights and judicial and legal reform in order to strengthen the rule of law in Iraq.  The Resolution also assigns the United Nations in Iraq several other roles, including the promotion, support and facilitation, in coordination with the Government of Iraq, of the implementation of the International Compact with Iraq. Finally, it foresees a prominent role for the UN in dialogue and reconciliation.

This programme addresses the GoI’s goals as set forth in the International Compact with Iraq - that the rule of law should be strengthened.  Specifically, in section 3.1, it states that the establishment of the rule of law through institutionalized reforms is fundamental for the successful implementation of the Compact, and identifies the strengthening of the judiciary and the administration of justice as one of its reform priorities.

It also addresses the GoI’s goal to establish a civil service corps on the principles of professionalism, integrity and non-partisanship, as set forth in the International Compact with Iraq.   Specifically, in section 9.43, it states that the Government will formulate a comprehensive civil service reform programme which is fundamental for the successful implementation of the Compact.

In addition, the NDS also states the need for an independent judiciary that provides fair and equitable justice with respect for human rights; and the need for a civil service reform, especially management reform of the public sector institutions as a priority.

1.3 UNDP is working with several international and national partners in implementing this project. 

International Partners
UNDP-POGAR will be the implementing agent for three projects: Updating of the Iraqi Legal Database, Modernizing of Iraq’s Public Prosecutors’ Office and Strengthening the Iraqi Parliament. UNESCWA will be the implementing agent for development of the public sector whilst CIDA and Team International will provide the training programmes for this part of the project. UNAMI/HRO will be implementing agent for some of the human rights activities – specifically training for the Ministries of Interior and Defence. The Canadian NGO, Alternatives, will implement one activity in the national dialogue and reconciliation component of this project.

National partners 
The HJC, JTI and the IHT will be key partners in the judicial reform section of this project. NCCI and other Iraqi NGOs will be implementing agents for activities under the national dialogue and reconciliation programme. 

Key line ministries involved in this project are NCCMD/Ministry of Planning and Development Cooperation, Ministry of Human Rights, Ministry of Defence, Ministry of Interior and Ministry of Justice and the line Ministries.

- Human Resources

One National Project Manager and one National Project Assistant have been recruited for the National Dialogue and Human Rights components of this project. This recruitment was significantly delayed due to restrictions on the recruitment of Iraqi nationals without residency permits.

  - International Staff: One international Programme Officer is responsible for the Human Rights, National Dialogue and Parliament components of this project. An international Programme Specialist and a national Programme Officer funded by UNDP Core resources are managing the Rule of Law and Institutional Strengthening components of this project.

- Methods of Operating

The primary implementation mechanism utilized has been DEX, through NGO and UN implementing partners. In the National Dialogue component of this project, UNDP will be working with 2-3 NGOs as implementing partners. UND-POGAR will implement the Parliamentary Strengthening and Rule of Law activities under the project, whilst UNESCWA will implement the Institutional Strengthening component.  A portion of this project’s budget ($500,000) was allocated to UNAMI/HRO during the design process. Accordingly, HRO will implement these activities with assistance from UNDP.

Provide details on the procurement procedures utilized and explain variances in standard procedures.

The project adhered strictly to the UNDP procurement guidelines and practices. The selection of the Implementing agencies and the hiring of the national/international consultants were undertaken within the legal guidelines of UNDP.

Monitoring of the activities is done through evaluation of quarterly and final reports, participant evaluation forms, quality review of documents submitted by partner Ministries and oversight of budgets.

Report on any assessments, evaluations or studies undertaken.

None to report.

- Results

Provide a summary of programme/project progress in relation to planned outcomes and outputs; explain any variance in achieved versus planned outputs during the six month reporting period.

For Judicial reform, all activities were on target.

Due to its key role in the development and reform of the Iraqi Public Sector, the National Center for Consultancies and Management (NCCMD) is involved in different projects implemented by UN agencies and other international donors.  This situation is overwhelming the NCCMD officials who have difficulties in scheduling activities.  Some of the planned activities had to be postponed due to previous commitments of the NCCMD.  This delay had impact on the overall implementation of the project. A meeting was held with the NCCMD to revise the priorities and set forth a workplan for the 2nd half of 2008.

Serious delays in communication with the Iraqi ministries have stalled the implementation of the Human Rights Component.  A meeting was held between UNDP, UNAMI/HRO, Ministry of Interior and Ministry of Defense as an attempt to restart the project activities.

Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period.

See above.

Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries Updating of the Iraqi Legal Database 80% completed, Support to the NCCMD 50% completed, National Dialogue 30% completed, Parliamentary support 50% completed, Modernizing of Iraq’s Public Prosecutors’ Office 80% completed, support to HRs 20% completed.

Support to the Role Of Law:

During the second phase of the Iraqi Legal Database project, a number of improvements were made to the ILD, including but not limited to the following:

For each law or legal text that has been modified or annulled through a subsequent text, full reference has been provided to the modifying text, and the modified text itself has been updated (which is the first time that this has been done in Iraqi law);

All laws and regulations from the Kurdish Region were incorporated into the database.  These texts were obtained from the Kurdistan Official Gazette (1992-2007);

A criminal code, a criminal procedural code, and a commercial code were created.  Each legal code groups together all the laws, regulations and other legal texts, as well as court decisions that relate to its particular subject and makes them available in a single source; and

Officials from Iraq’s judicial sector have been trained in the use of the ILD to ensure that the Iraqi State benefits from the work that has already been completed.

A training session was organized for 11 Iraqi lawyers, judges and IT specialists for the purpose of familiarizing them with the ILD, and in order to train them to update the database.  This training session took place in Beirut from April 8 to April 12, and was attended by Iraqi officials from both Baghdad and Erbil, including the Minister of Justice from the Kurdish Region, the Chief of Investigatory Judges from Baghdad, amongst others.   The purpose of the training session was partly to hand over responsibility for maintaining and updating Phase II of the ILD to the Iraqi authorities, as well as to train them in its use.  The training session was also designed to ensure that our Iraqi counterparts will have the capacity to participate in the upgrading of the database, which will take place during Phase III of the ILD Project.

A meeting was organized in Amman, Jordan between senior representatives of the Iraqi Higher Judicial Council (the “HJC”), UNDP-Iraq and UNDP-POGAR in order to discuss a number of regional activities, particularly with a view to encouraging the Higher Judicial to identify its priorities. On the basis of these discussions, the HJC was able to identify its priority areas, which served as the foundation for all future work on the Iraq component of the Project.

Four Rrepresentatives from the HJC participated in the First Regional Conference on Supporting Implementation of the United Nations Convention Against Corruption in the Arab Region.  The Conference was attended by representatives of over 15 Arab states, and all major international organization that are involved in the fight against corruption.  One of the conference’s outputs was to agree on the formation of a regional anti-corruption network (the “ACTNET”).  Iraq expressed its commitment to join and support the formation of this network.

Six representatives from the HJC participated in a regional conference on intellectual property crimes that was organized by UNDP-POGAR and that took place in Manama, Bahrain.

One representative from the HJC participated in the conference on the separation of powers, the independence of the judiciary and the role of public prosecutors in the rule of law that was held in Doha, Qatar. This conference was organized jointly by the French Ministry of Justice, the Qatari Public Prosecution Office and UNDP-POGAR.

Training for Trainer’s Session on Investigative Techniques of Modern Crimes which took place in Cairo, Egypt. This session was organized by UNDP in cooperation with the National Center for Social and Criminological Research (NCSCR) in Cairo.

Work commenced to incorporate Iraq in the Arab criminal legal database;

UNDP has  commenced acquiring materials and preparing for the establishment of an Information Department in the HJC for public prosecutors and investigatory judges on international best practice in relation to investigatory techniques;

UNDP-POGAR commissioned the translation of a USIP publication on model criminal codes for post conflict societies.

Support to the National Center for Consultancies and Management Development:

A Situation Analysis Consultative Meeting was held  with the aim of identifying and reaching consensus on the current state of affairs within the Iraqi Public Sector, with a particular emphasis on its needs and limitations.  The outcomes of the meeting served as a basis for the development of a comprehensive strategic plan for the National Center for Consultancy and Management Development (NCCMD) during the strategic planning workshop that followed the meeting, in addition to providing the project with an informational platform that would facilitate the development of the framework for management development.

In addition to NCCMD representatives, decision makers from major Iraqi ministries and public institutions were targeted in order to corroborate the results of the above exercise and provide feedback on the needs and limitations faced by their respective institutions. The Consultative Meeting focused on gathering accurate and objective information on the Iraqi Public Sector through brainstorming sessions and identification of needs and limitations using a SWOT analysis approach, which in turn led to the confirmation of the Situation Analysis  and identification of priority areas for improvement and reform.

A Strategic Planning Workshop was planned to succeed the Situation Analysis Consultative Meeting and targeted the same NCCMD representatives with the aim of preserving the momentum created during the first session and ensuring that the strategic plan of the Center would be developed in accordance with the conclusions and findings of the first meeting.  The Strategic Planning workshop gathered eight (8) NCCMD participants for a period of four consecutive days and established a medium and long term Strategic Plan for the institutional development of the NCCMD, which will in turn contribute to the enhancement of the overall reform and upgrade of the Iraqi Public Sector.

In the prospect of upgrading the Information Communication and Technology (ICT) infrastructure of the NCCMD, an assessment of all IT equipment – hardware and software – was performed during this reporting period.  The assessment was performed by the IT staff of the NCCMD as part of the coaching approach adopted by the project team and reviewed by ESCWA’s ICT experts.  The results of the assessment were revised and finalized after discussions between involved stakeholders.

Training of trainers (TOT) on business planning and performance management.  UNDP-ESCWA, and the World University Service of Canada (WUSC) joined efforts in the implementation of this activity.  Within its joint project, UNDP, ESCWA, and WUSC had developed the training materials and performed a training of practitioners on the subject.  The TOT was the second phase of the UNDP project, and ESCWA along with UNDP seized the opportunity and decided to combine project activities and deliver a joint TOT.  Four out of twenty-two representatives from the NCCMD participated in the training.

Facilitated the activation of the NCCMD membership in the regional and international knowledge networks like the  Governance Institutes Forum for Training (GIFT) in the MENA region.  The network serve as a platform for encouraging exposure and information sharing between the NCCMD and other governance and training institutions on the regional and international levels.

Support to the National Dialogue:

Phase II of the National Dialogue launched early 2008, and  Right to live in Safety campaign started  in Baghdad City and its surroundings. Target group are academics and Civil Society Organizations.  46 academics participated in two workshops, and 49 CSOs  have participated in three workshops. These one week workshops focused on many subjects, including Training  of Facilitators, Peace Building, Conflict Management & Transformation, Conflict Resolution , Gender, Human Rights and Proposal Writing.

Parliamentary Support:

Two workshops were held pursuant to a specific request that was made by the Presidency of the Council of Representatives, which has long argued that its members must improve their drafting skills mainly with a view to ensuring that future legislation is as comprehensive as possible and benefits from international and regional best practice.  The Council has requested that over 100 of its members and advisers be trained in four separate training sessions.  The training session that took place during the reporting period are two in the series of four. The issues that were covered during the workshops included (i) a session designed to assist legislative drafters identify unclear language, and ambiguous terms that are typically used in poorly drafted laws; (ii) a session on how to draft legislation that amends existing laws; (iii) a session on ensuring that provisions in a same text complement each other and on how to avoid unintentional contradictions; (iv) a session on when specific reference should be made to state institutions, in what way, and what type of language should be used when establishing such an institution; (v) several sessions were organized for the purpose of illustrating regional best practice to the participants, including Lebanese and Egyptian best practice; (vi) a session was organized for the purpose of illustrating how the Iraqi Legal Database (the creation of which was designed and financed by UNDP) can be used to improve legislative drafting

Support to HRs:

Representatives of the Ministry of Human Rights continued to participate in the ongoing Business Planning and Performance Management Programme. During the reporting period, A strategic plan foe the Ministry was developed, and the priority activity identified in the strategic plan was implemented.

List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

UNDP’s key partnerships have been outlined above in 1.3

Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

The promotion and protection of human rights is a key component of this project. Whilst UNDP is working to strengthen the institutional capacity of the Ministry of Human Rights, it is also assisting the Ministries of Defence and Interior to mainstream human rights into their by-laws, SOPs and training manuals.

The project continuous to ensure the direct and full participation of both men and women in strategic planning, needs assessments, meetings and workshops.

- Future Work Plan

Phase III of the Iraqi Legal Database – Phase II completed and disseminated to Iraqi counterparts.

Expand the scope of the Rights to Live Campaign to the whole country and four networks are created.

Completion of the project to modernize Iraq’s Public Prosecutors’ Offices.

Finalize the NCCMD framework for management development of the public sector.

Training  of NCCMD staff on implementation of service/demand driven e-government

applications

Connecting the NCCMD staff and other relevant HR managers with model

regional/international relevant training centers

Facilitating NCCMD’s networking with counterparts and experts on public sector

management   development and reform

NCCMD training materials and methods upgraded (based on outcome of assessment -

output 1.2)

Continue the Series of activities under  Phase 2 of the national dialogue in Iraq.

Continued technical advice to the Ministry of Human Rights on the establishment of a National Institute of Human Rights, finalization and implementation of the Ministry’s strategic plan and required preparations for the development of a National Plan of Action.

Launch of UNAMI/HRO training programme for MoD and MoI.

Two TOT courses for the Iraqi National Institute for Human Rights