CFIA Fund (Influenza)

Annual Programme NARRATIVE progress report

REPORTING PERIOD: 01 january – 31 December 2009

| Submitted by: United Nations High Commissioner for Refugees (UNHCR) Organization code: 001997 Contact Information: Hervé Isambert, Senior Operations Officer, Public Health and HIV Section, Division of Programme Support and Management, UNHCR HQ Geneva, Switzerland. E-mail: isambert@unhcr.org | Country and Thematic Area (when applicable) |
| --- | --- |
| Programme No: CFIA- B8 Project ID: 00067362 MDTF Office Atlas No: MDTF Office to supply Organization Reference: | Participating Organization: UNHCR |
| Programme Title: Avian and Human Influenza Preparedness and Response in Refugee Setting Location: Countries hosting refugees assisted in camps and in an urban situations |
| Implementing Partners: Democratic Republic of Congo: IMC Rwanda: ARC and AHA Burundi: AHA Nepal: Association of Medical Doctors of Asia (AMDA) Egypt: Caritas / Refuge Egypt / Egyptian Family Planning Association/ Catholic Relief Services; Algeria: Triangle Generation Humanitarian- Algerie Syria: Syrian Red Crescent Yemen: SHS/ MSF-Spain/ Interaction for Development/ CSSW; and UNHCR direct implementation in 12countries. | Programme Budget: US$ 2,970,00 |
| Programme Duration: 18 months Start date: 1 January 2009. End date: 30 June 2010 Original end date: 31 December 2009. Revised end date, if applicable: 30/06/2010 Budget Revisions/Extensions: ------ extension approved on 15/12/2009 |  |

- Purpose and how the programme relates to the Strategic UN Planning Framework guiding the operations of the Fund

UNHCR is the sole UN Agency with the mandate to protect refugees. The project on Avian and Human Influenza Preparedness and Response in Refugee Setting (AHIPRRS) is a UNHCR contribution to the “UN System Consolidated Action Plan- UNCAPAHI” for influenza. Though the projects targets primarily influenza, it also tackles a number of other epidemics. UNHCR has the responsibility to ensure preparedness and pandemic mitigation and create appropriate conditions for the continuity of basic delivery assistance in case of pandemic

AHIPRRS has been developed in close collaboration with national authorities and UNHCR implementing partners (IPs). AHIPRRS has contributed to UNCAPAHI by participating in the development of national capacity in surveillance, in communication strategies to prevent, detect and respond to outbreaks, and by contributing to a functional national emergency response capacity specifically in countries that hosted large number of refugees, internally displaced populations and other persons of concern (PoC) to UNHCR. UNHCR has collaborated at all levels with other UN agencies, including WFP, and with national and international agencies in countries where AHIPRRS has been implemented

Objectives / Goal:

Under the overall UNHCR protection mandate, the strategic goal of AHIPRRS is to mitigate the direct and indirect consequences of the pandemic on the health and well being of PoC to UNHCR. The project, funded through the Central Fund for Influenza Action (CFIA), contributed to meeting the objectives in the UNCAPAHI, specifically related to human health, communication (public information and supporting behavioral change), and continuity under pandemic conditions.

# II. Resources

Financial Resources:

- Provide information on other funding resources available to the project, if applicable.

  - None

- Provide details on any budget revisions approved by the appropriate decision-making body, if applicable.

  - NA; Only extension of the length of the contract with no additional cost has been approved

- Provide information on good practices and constraints in the mechanics of the financial process, times to get transfers, identification of potential bottlenecks, need for better coordination, etc.

  - No problem was encountered

Human Resources:

- National Staff: Provide details on the number and type (operation/programme)
No national staff have been paid under this funding

- International Staff: 5 International staff have been working for this project

  - 4 Epidemic Preparedness and Response Coordinators deployed in 4 regions : Asia, Middle East and North Africa, East and Horn of Africa, and Central Africa

  - 1 Global Information Officer based in Geneva Head Quarter

# Implementation and monitoring arrangements

Projects were implemented in 22 countries, through IPs and by direct UNHCR implementation in 12 countries.

III.a. Key implementation strategies used:

- Advocating for PoC to UNHCR to be fully integrated as beneficiaries into the national epidemic/ pandemic preparedness and response system;

- Establishing and maintaining an effective health surveillance system enabling early warning detection of the outbreak and constant monitoring to guide and prioritize the intervention;

- Taking epidemic control actions, and behavioral change interventions;

- Prioritizing intervention towards vulnerable population among PoC;

- Mobilizing and training the community network for early detection of cases, home based monitoring and/or prompt referral; and to facilitate dissemination of health education messages and social mobilization activities;

- Training medical staff on the use of national and / or WHO standardized and updated protocols for management of cases highlighting life saving procedures;

- Ensuring staff and patient safety by providing adequate Personal Protective Equipment (PPE) and guidance on its use, and by adopting practices following the WHO recommendations on infection prevention in health care settings;

- Adapting the health working environment to a possible influx of patients and to the recommended specific isolation procedures;

- Ensuring that care for other diseases continues in the context of increased workload and possible staff absenteeism; give priority to acute/ life- threatening diseases;

- Coordinating pandemic preparedness and response plans in a multi-sectoral approach;

- Ensuring continuity of essential social, economic, protection and governance services, and the implementation of humanitarian relief under pandemic conditions;

- Strengthening partnerships with governments, camp coordinators and community leaders to ensure coordination of activities between UNHCR and PoC to UNHCR; and

- Carrying out missions in refugee camps to assess needs, conduct training, monitor, enforce coordination, and carry out risk analysis.

III.b. Procurement procedures:

Procurements were done according to the standard procurement procedures of UNHCR and managed at the field project level. Depending on the specific items needed (drugs, lab test, masks…) purchasing was done either internally (most frequent case) or nationally (if good quality items available locally at competitive cost).

- Results

AHIPRRS was started in 2007 and continued to be implemented in the different countries where UNHCR has operations. UNHCR’s AHI programmes have primarily concentrated on camp-based populations. In 2009, responding the needs created by the pandemic influenza, UNHCR decided to expand its program to urban refugee populations.

UNHCR held a Pandemic coordination meeting in early July 2009 with numerous agencies including donor, UN and NGOs to present and discuss the accomplishments and next steps of UNHCR’s pandemic programmes.

In 2009, emphasis was given to further develop the coordination of UNHCR with other field partner agencies; this was notably the case of WFP with which joint assessment missions have been organised; it was also the case of the Red Cross / Red Crescent societies that have opened in few countries (incl. Bangladesh and Nepal) the participation of refugees / staff taking care of refugees to trainings organised at district level. Materials made available on the H2P website were regularly checked and used where needed. Timely adjustments of the protocols and case management have been done after recommendations were issued by WHO.

Surveillance regarding the detection and reporting of Influenza Like Illnesses have been intensified. Though sporadic cases among refugees have been confirmed in some locations including Dadaab camps /Kenya, Sahrawi camps/Algeria…H1N1 outbreaks have only been reported in Thailand refugee camps (Maela), no severe complication was observed during the outbreak.

In late 2009, UNHCR coordinated at global level the procurement of vaccines to refugee health care settings and Epidemic Preparedness and Response Regional Coordinators (EPRCs) have actively participated in the H1N1 vaccination planning process at field level for health staff serving PoC to UNHCR, including ensuring availability of local resources (e.g. staff, logistic support and cold chain).

IV.1. Practical examples of country progress achieved mainly during the second, third and fourth quarters of 2009 (see CFIA-B5 report for the first quarter)

A. Central Africa:

A.1. Rwanda:

- 150 health personnel, camp leaders, community health promoters (CHP) and refugee representatives trained in control measures.

- Generic camp contingency plans developed and disseminated to all camps; 3 camps developed camp-specific contingency plans.

- 37 medical and paramedical staff implementing partners (IPs) trained on case management and reporting of influenza like illnesses.

- Influenza like illnesses included in the weekly statistical reports submitted by all camps.

- Hygiene promotion supplies stocked in the camps.

- IEC materials disseminated; public awareness promoted through audio-visual aids.

- Constructed an isolation room at each of Nyabihke and Kiziba Camps

- Trained 52 CHPs from ARC and AHA in the Nyabiheke, Gihembe and Kiziba camps Gasorwe in A (H1I1) with an emphasis on disseminating key awareness messages.

- Carried out rehabilitation in the Gihembe, Nyabiheke and Kiziba camps (health facilities provided with piped water, floors of health centres cemented and sewage disposal improved).

A.2. Burundi:

- Trained 30 CHPs in case detection to improve outreach activities

- Included Influenza like illnesses in the weekly statistical reports from all camps

- Trained 52 health personnel, camp leaders, CHPs and refugee representatives in control measures.

- Camp task force committees strengthened and trained.

- Simulation exercise carried out at the national level; UNHCR and IPs participated in this exercise.

- Medical supplies and equipment in addition to PPE delivered to 3 camps.

- Reproduced 20 videotapes on AHI and distributed for refugee camps and transit centers.

- Launched outreach campaigns in the Gasorwe and Musasa camps to enhance public awareness on influenza and hygiene.

- Disseminated IEC materials.

- Constructed patient isolation rooms in 3 camps.

- Procured pumps to provide water and evacuate latrines in one refugee camp.

- Improved electrical supply to the health facilities in 2 camps.

A.3. Chad:

- Trained 8 trainers in H1N1.

- Medical supplies and equipment in addition to PPE delivered to camps

- Funds were made available to the country team to continue a series of cascaded training in Chad, and work with the UNICEF and other stakeholders to produce and adopt IEC materials.

A.4. DRC:

- Trained 250 health professionals’ doctors, nurses, laboratory technicians, managers, communication specialists, journalists, veterinary doctors and agronomies in case management and reporting of pandemic influenza.

- Influenza like illnesses included in weekly reporting format.

- Supported health authorities to improve contingency plans.

- Medical supplies and equipment in addition to PPE delivered to 3 IDP camps.

- Stocks of hygiene promotion supplies including cleaning tools and supplies, water reserving containers and soap distributed among 3 camp health facilities

- IEC materials disseminated among IDPs living in North and south Kivu camps.

- Radio and TV awareness programs regularly aired and reached IDP populations living in North and south Kivu.

- Provided IDP camp health facilities with stock of water reservation equipment and cleaning tools.

- Soap and other hygiene supplies distributed for returnees in North Kivu.

- Revised preparedness, response and continuity of business plans for A (H1N1) and other epidemics with WFP at Uvira.

B. East and Horn of Africa

- Up to date information regularly shared with all camps.

- Awareness training on H1N1conducted in East Sudan and in Ethiopia for community health workers (CHWs).

- 50 participants trained on the use of HIS for epidemic monitoring in East Sudan and in Ethiopia.

- Surveillance has been heightened in refugee camps in Kenya after a confirmed case of H1N1; IFO old Hospital has set up as isolation ward. There are sufficient supplies of Tamiflu and protective materials for staffs in Kenya programme. As part of preparedness plan for UNHCR staff, 90 doses of Tamiflu, 400 face masks and 900 pairs of gloves are made ready. This is part of. Standard Operating Procedure (SOP) developed with the IPs in Dadaab on preparedness and response plan for H1N1 (Dadaab-Kenya).

- WASH projects in Uganda and in East Sudan.

C. MENA

- Water, Sanitation and Hygiene Promotion projects ongoing in Algeria and in Yemen. Water filters purchased, hygiene promotion training conducted for school teachers and students and WASH IEC/BCC materials distributed for Bassateen urban settlement and Kharaz camp in Yemen.

C.1. Syria

- Supported the printing of the H1N1 awareness raising materials for the MoH; delivered 75,000 brochures and posters on H1N1 to the Ministry of Health (MoH).

- Organised awareness session on H1N1 for UNHCR staff.

C.2. Algeria

- First case of H1N1 was detected among Sahrawi refugees during this reporting period. Measures taken to contain the outbreak. Because large number of Sahrawi refugee children often travel to various European countries to spend their summer vacation within the framework of the "Vacations in Peace" program, UNHCR continued to monitor the situation during the reporting period. UNHCR pre-positioned pandemic preparedness items and control measures involving all health actors in the camps with the aim of addressing the first surge of Pandemic Influenza cases in the camps; and closely coordinated with the Algerian MoH and WHO. By the time this report was compiled, no new cases of Influenza A H1N1 detected after the first confirmed case.

D. West Africa:

- UNHCR has launched “AHI preparedness and response in camp settings” in Guinea, Ghana, Ivory Coast, Liberia, Nigeria and Sierra Leone in 2007.

- Confirmed cases of A H1N1 to date are in Cote d’Ivoire, Nigeria, Ghana and Liberia.

- Key interventions included; training of CHWs and community leaders; establishment of task forces (created in 6 camps: Budumburan and Krisan in Ghana, Nicla (Zaaglo) in Ivory Coast and Kouankan 1 – 2 and Laine in Guinea); and procurement and stockpile of personal protective equipments, essential drugs including Tamiflu

- In September 2009 EPR focusing on A H1N1 scaled up; 8 countries were selected for interventions on securing access PoC to clean water and hygienic items and ensuring adequate sanitation; hygiene promotion through awareness campaigns; improving outbreak preparedness by stockpiling medical and PPE and; rehabilitations of water and sanitation facilities

- Developed a joint sub regional project with IOM aimed at improving awareness and response capacities in refugee and migrant hosting areas in Senegal, Guinea, Mali and the Gambia. Project will be implemented in 2010 depending on availability of funds.

D.1. Sierra Leone:

- Developed a joint proposal to support the Government of Sierra Leone to raise the level of awareness and prevention within the communities where refugees are locally integrating in four targeted Districts of Moyamba, Kenema, Pujahun and Bo.

- Trained 80 persons (health workers, students and CHWs).

- Conducted awareness campaigns and distributed locally developed/adapted IEC materials

- Procured hygiene promotion materials, rehabilitated sanitation and water points for health facilities (10) and schools (8).

D.2. Guinea

- Interventions focused on public awareness, hygiene promotion and capacity building.

- Reactivated and trained EPR task force, including CHW, 47 persons from refugee and host communities.

- Trained 38 health staff in the refugee camp and government health facilities on A (H1N1) clinical management and surveillance.

- Procured essential drugs, IEC materials and PPE for CHWs, health facilities, peer educator and the task force.

D.3. Togo

- Rehabilitated a health centre and a maternity ward that provide health services to around 30 villages.

- Rehabilitated the only water pump that provides safe water to the community, school and health facility

- Provided essential drugs, PPE to 2 health facilities ( AGOE health centre and BE hospital) and the National EPR committee as part of UNHCR’s contribution to EPR to the Togolese government.

D.4. Cote d’Ivoire:

- Trained 60 CHW and 50 health club members on hygiene promotion.

- Produced various IEC materials locally in collaboration with the MOH.

- Stockpiled drugs, hygiene and PPE at UNHCR’s IP’s offices in Tabou and Guiglo.

- 11 schools benefited from a ToT training on hygiene promotion and received “hygienic kits”

- Conducted around 360 awareness sessions on A H1N1 reaching about 13,000 people.

D.5. Liberia:

- Trained 155 healthcare providers and CHWs.

- Stockpiled PPE and infection control materials for schools, clinics.

- 260 persons trained in hygiene promotion.

- Developed and distributed IEC/BCC materials adapted from the MOH.

- Rehabilitated 15 water points and constructed latrines.

D.6. Ghana

- Coordination meetings held between the national health partners and the UNHCR IPs.

- Intensification of public education through mass media and surveillance for early detection of other cases conducted.

- Holding rooms and isolation rooms identified in all regions including in health facilities in the camps, collection and transportation of samples from suspected cases for diagnosis organised.

- Distributed drugs and specimen collection materials to all camps.

- Trained 48 clinical staff, 38 taskforce members, and 40 volunteers form refugee camps and surrounding host communities.

- Stockpiled clinical and protective materials and equipment.

E. Southern Africa

E.1. South Africa

- Distributed IEC materials on H1N1 prevention to IPs in Pretoria, Durban and Cape Town as a key component of the prevention and sensitization campaign.

- Improved sanitation systems through the provision of portable latrines at Musina area (border with Zimbabwe).

- Conducted hygiene campaigns in all major refugee sites (Cape Town, Durban, Johannesburg, Musina and Pretoria) and distributed soap and H1N1 education materials in different refugee languages.

E.2. Zimbabwe

- Improved water and sanitation systems in Tongogara camp through the fencing of water sources, construction of new boreholes and family latrines.

- Conducted hygiene campaign in the camp.

- Conducted refresher training on outbreak preparedness for CHWs.

- Developed communication plan for the refugees in order to reduce risks and mitigate the impact of cholera outbreak

F. Asia

F.1. Myanmar

- Facilitated pandemic simulation exercise with NGOs and Health Authorities

- Case definition for suspect and probable cases distributed to some health facilities of the Northen Rakhine State

- Renovated and improved water points, including a water storage facility; hence increased availability of water.

- Isolation Ward built in Maungdaw hospital (equipments were provided by WHO)

- Overall the project contributed through improved WASH facilities, hygiene education and the provision of an isolation ward, which should also lead to improved health status of the target population.

F.2. Nepal

- Enhanced surveillance mechanism set up; training provided on H1N1 for 28 UNHCR Community Development Facilitators.

- Health posts staff from the MoH trained on pandemic influenza.

F.3. Thailand

- UNHCR is involved in the surveillance system. The H1N1 outbreak that happened in Maela camp was documented retropectively.

F.4. Pakistan

- UNHCR has requested that the Influenza Pandemic 2009 Urgent Needs Identification and Prioritization Tool (UNIP) that has been developed by WHO, OCHA and UNSIC to also cover humanitarian issues.

F.5. Bangladesh

- UNHCR has coordinated with the Bangladesh Red Crescent Society (BDRCS) pandemic preparedness activities.

- WASH was improved in both camps incl. water supply that now reaches 16 and 24 liters per capita per day in each camp, respectively.

F.6. India:

- 40 UNHCR staff (40) and community animators from IPs (45) in New Delhi were trained on pandemic influenza.

IV.2. Achievements per generic activities: Refugees inclusion in National Plans.

- As at the end of 2009, about 40% of the countries have included refugees in their National Contingency Plans (NCPs). Despite the challenging nature of this activity, this was a big improvement as compared to the first quarter of 2009 where only 5% of countries where UNHCR has AHIPRRS have included refugees into their NCPs.

- Syria, Tajikistan and Papua New Guinea included refugees in NCP in the last quarter of 2009. Advocacy efforts continued to have refugees included into plans on A (H1N1). In Malaysia and Thailand, UNHCR continues to advocate for the inclusion of refugees and other persons of concern not only in the existing, updated and / or new contingency plans/NCPs, but also in the surveillance and control of communicable diseases.

- Some countries agreed to highlight to cover vulnerable populations without necessarily mentioning refugees. UNHCR is working with the UN country teams to support UNHCR in its advocacy effort.

IV.3. Achievements per generic activities: Contingency Plans at camp level: 80%

- Contingency Plans are developed in approximately 80% of camps.

- Contingency Planning for AHI outbreaks have been initiated with key IP in all camps that host > 5000 refugees. Since their initiation, they have been undergoing continuous process of evaluation and improvement. Contingency Planning has been initiated in several camps in Kenya, Rwanda, Burundi, Ethiopia, DRC, Uganda, Tanzania, Nepal, Bangladesh, Yemen, Algeria, Syria and Egypt (adapted to urban setting).

- Assessment of UNHCR operations and partners on capacity to respond and support in business continuity planning and stockpiling done in East and Horn of Africa.

- Camp simulation exercise conducted in Thailand.

- Joint inter-agency plan drafted in Myanmar.

IV.4. Achievements per generic activities: Systems for surveillance: 95%

- Health Information System (HIS) has been established in all old camps and is progressively extended to new camps. Reporting systems, coordination and surveillance mechanisms and systems are put in place in most camps hosting more than 5000 refugees. The reporting system is linked to the national HIS of the Ministries of Health. Case definitions are available for both H5N1 and H1N1.

- Trends in respiratory illnesses are monitored in most camps using Health Information System (HIS). Sentinel surveillance ongoing in Dadaab and Kakuma camps in Kenya. UNHCR and WHO are implementing a joint project to improve epidemic surveillance and response capacity in South Yemen.

- HIS system reviewed in Malaysia and India. In East and Horn of Africa, surveillance has been heightened in almost all camps at the onset of H1N1 outbreak. Epidemiological information is regularly shared to all country operations including disease spread in neighboring countries.

- Both community level and health facility surveillance is enhanced using WHO case definitions.

- Outbreak reports are made weekly in each camp (including zero reporting).

- Surveillance and reporting systems were reviewed based on camp preparedness plans in Bangladesh, Nepal and Thailand. HIS has been reviewed in Asia region.

- HIS Officer is now based in North Kivu, DRC

IV.5. Achievements per generic activities: Stock of drugs and medical equipment in place: (95%

- Drugs and medical equipment in place in the majority of refugee camps. The distribution and the storage of medical supplies and protection equipment have been finalized at the different health posts in the camps.

- Storage conditions have been reviewed and refreshing drug management training has been completed in all the camps provided with equipment and supply.

- UNHCR has reviewed the stocks in Yemen to gauge the consumption, and hence work to replenish the stocks. Drug management training provided to clinicians, pharmacists and store managers in Uganda and East Sudan by MOH and IPs.

- Stockpiled drugs and supplies are being utilized and a system will be put in place to ensure mainstreaming of procurement and availability of buffer stocks through establishing an agreed minimum level of supplies.

- Medical supplies and equipment in addition to personal protective equipment (PPE) delivered to camps in Rwanda, Burundi and Chad, and to IDP camps in DRC. Supplies procured and sent to Algeria, Yemen and Egypt. All received and positioned closest the refugees as applicable. In Algeria, the supplies purchased internationally by UNHCR have been positioned in the Central Pharmacy at the camps in Tindouf. They include PPE, supportive drugs such as fever treatment, anti-malarials, antibiotics, I/V fluids, carry media and a limited quantity of  Tamiflu (200 courses). The supplies are supposed by used to meet the need, and UNHCR is now working with its Operational Partner, MDM-Greece and the management of the Central Pharmacy to ensure proper storage and distribution of the drugs and medical supplies.

- Since many IDPs in DRC live in some provinces along with resident populations and get access to MOH services, UNHCR provided the health provinces in S. Kivu and N. Kivu to fill gaps of supplies. The MoH, DRC State appreciated the support and paid a visit to the UNHCR-DRC Office. Supplies were also moved to the camp sites in Abeche, Chad.

- In Asia, stockpiles where existing (Nepal and Bangladesh) are regularly checked and those with soon-to-expire drugs are moved to the OPD to be consumed and replaced with newer stocks. Additional PPE were procured for agencies implementing health programs in the camps in Thailand. Local procurement done in Bangladesh and Nepal; Pandemic stockpile arrived in Myanmar. Pakistan and Iran both with huge refugee population requested for PPE for the camps, but UNHCR has not been able to provide this due to the huge amount of cost it would entail.

IV.6. Achievements per generic activities: Water, Sanitation and Hygiene: 80% achievement

- UNHCR undertook a review of the existing water and sanitation facilities in different camps with the perspective of the business continuity.

IV.6.a. East and Horn of Africa:

- Provision Projects and activities continued to improve WatSan services in many camps. Construction of an isolation facility and a septic tank for new Ifo hospital, Kenya is almost complete. Projects are ongoing to improve WatSan services in Ethiopia, East Sudan and Uganda camps

IV.6.b Southern Africa:

Hygiene campaigns conducted in Southern Africa through the distribution of soap and H1N1 educational materials.

IV.6.c.  MENA:

- Water, Sanitation and Hygiene Promotion projects ongoing in Algeria and in Yemen. WASH project completed in Yemen. Project activities were aimed at improving the water, sanitation and hygiene situation in Kharaz Camp and Bassateen urban settlement. The outcome is being monitored and the level of awareness among the refugees and host community is seen to have improved. UNHCR is implementing the project through its IPs and in close coordination with UNICEF.

- Translation of public awareness documents for H5N1 into appropriate languages for refugees was completed in majority of camps. In Middle East and North Africa awareness materials was reproduced in 7 languages (Arabic, English, Somali, Tigrigna, Amharic and Spanish) and provided to all countries.

IV.6.d Central Africa

- Provision of piped water for the health posts completed in 2 camps of Rwanda and 3 camps of Burundi. Improved waste disposal at the maternity and other sections of the health facilities in the 3 refugee camps in Burundi. In Burundi, water provision and sewage disposal improved in health posts in two refugee camps.

- One patent isolation room was constructed in the Kiziba Refugee camp in Rwanda. Plans developed to construct latrines annexed to the health post in 2 refugee camps of Rwanda.

- In Rwanda, physical rehabilitation of camp health posts in Gihembe and Nyabiheke completed with activities including provision of piped water to all inpatient and outpatient sections.

- Provided IDP camp health facilities in DRC with stock of water reservation equipment and cleaning tools.

- Needs of isolation rooms and improvement of infection control practices in the camps were assessed in Chad.

IV.6.e Asia

- Watsan improvements are ongoing in Myanmar, and in Bangladesh.

- Review of the hygienic environment including medical waste management of the health facilities has been conducted.

V. Achievements per generic activities: Training

- Training have been organized and conducted for camp staff and refugees in Mozambique, Namibia, Zambia, Nigeria, Sierra Leone, Dadaab, Tanzania, Uganda, Egypt, Rwanda, Burundi, Nepal, Myanmar, Pakistan and Myanmar. Technical support and coordination missions executed in all countries. Training on AHI and on HIS and epidemiological surveillance done MENA (5 countries) and in Central Africa. HIS refresher trainings conducted in Nepal, Bangladesh, and Thailand.

- All UNHCR country operations staff received orientation sessions on H1N1.IEC / awareness materials developed and distributed for UNHCR and implementers partners staff in MENA, Central Africa, and in East and Horn of Africa.

- Training of Trainers (ToT), training of community promoters, Peer Education and mobilized community associations have been organized in many settings

- During this reporting period, training on H1N1 was conducted in Bukavu and Uvira (DRC) and in two refuge camps in Burundi. The training targeted professional health educators and community health promoters, including refugee representatives, and focused on developing, disseminating and evaluating key messages on pandemic influenza, outbreak control and hygiene.  Radio spots continued through 5 channels that cover all sites where IDPs are located in North and south Kivu. A series of health festivals and sports competitions were carried out in two IDP camps of North Kivu. One press conference was held on preparedness for pandemic influenza in North Kivu and broadcast through the five channels of the “North Kivu Radio Association”.

- A ToT was conducted in Abeche, Chad targeting 8 doctors and health coordinators who work for MoH, UNHCR, UNICEF, WHO, IMC, CAM and IRC in a wide geographical area of Eastern Chad. Topics covered included definition of avian, A (H1N1), pandemic and seasonal influenza; etiology, methods of spread, methods of prevention and control of influenza; surveillance; BCC on pandemic influenza; case management and camp contingency plans.

- UNHCR, other UN and IP staff based in Abeche, Chad received ToT in pandemic influenza and drug management.

- ToT was conducted in Yemen for CHWs, HIV Peer Educators, and religious leaders on Hygiene Promotion and awareness raising to fight epidemics. In Algeria, women community leaders were trained on community level prevention of epidemics, including AHI. In Cairo, UNHCR collaborated with IOM which conducted training for migrants in the community.

VI. Achievements per generic activities: Coordination

- UNHCR regular participated in coordination meetings and conference calls t al levels; global, regional and country level. Bilateral and multi- lateral coordination were conducted with OCHA, UNICEF, FAO, WFP, IOM, IFRC, CARE, SCF and national authorities.

- In Nepal, during the outbreak of highly pathogenic avian influenza A (HPAI) in Jhapa region in January 2009, UNHCR participated in the Avian Influenza Task Force coordinated by WHO/UNICEF/FAO. Awareness campaigns were carried out in all seven camps by AMDA, the IP.

VII. Achievements per generic activities: Infrastructure

- Isolation wards, incinerators and tents are available in most refugee camps.

East and Horn of Africa

- Isolation ward construction at Ifo hospital in Kenya under implementation-completion expected in early 2010.

MENA:

- Isolation Center built for Tindouf camps in Algeria.

Asia:

- Isolation ward was built in one township district hospital in the Northern Rakhine State of Myanmar; WHO provided medical equipments.

V.III. Achievements per generic activities: Public Information and awareness campaigns: 95% achievement

- 95% of refugees and other PoC are properly informed and encouraged to adopt healthy behavior. Regular communication and information on H1N1 provided to PoC to UNHCR in camps and in IDP settings where UNHCR is operational. Public awareness documents and information-education-communication (IEC) materials continue to be used and when needed translated into local languages. Training of community promoters, peer education and community associations continued.

- Up to date information regularly shared with relevant staff of refugee camps including treatment guidelines, and vaccine use and access.

- Several meetings were held with camp health authorities to scale up awareness activities in the camps, and awareness sessions conducted for the refugees conducted on H1N1.

MENA:

- Pandemic preparedness activities to refugees in urban situations are undertaken, mainly in MENA and in Asia. IEC / behavioral change communication posters were produced and disseminated in seven languages in Cairo, Egypt, for use in the various countries in MENA. Posters were also shared with AED to be added to the H2P web site.  H1N1 awareness posters were collected from WHO EMRO in English, French and Arabic, and distributed to all countries in MENA for use with UNHCR PoCs, staff and IPs.

- All camps are now using and adapting materials from the host country which is seen as a very good approach to ensure harmonization within the territories of a country and is very much encouraged and supported by UNHCR

Central Africa:

Radio spots continued through 14 channels that cover all sites where IDPs and returnees are located in North and South Kivu. A series of health festivals were carried out in two IDP camps of North Kivu. TV and radio spots with key messages on influenza, cholera and hygiene were regularly aired through 14 local channels in N. Kivu and S. Kivu in DRC.

Asia

- Public Information by camp refugee health workers continue to be implemented in Nepal and Bangladesh. This was intensified during the seasonal influenza outbreak in Nepal with noticeable decrease in the number of cases presenting after two weeks of IEC campaign.

- In Malaysia, UNHCR reproduced counseling cards from H2P. UNICEF animation CDs on H5N1 were distributed to the partners implementing outreach work among urban refugees in India. Contact was made with UNICEF India in order to procure materials that can be used for the awareness campaigns for urban refugees.

- Coordination with H2P programs in Nepal ongoing with regards to training of government health staff in peripheral health posts.

- Bangladesh Red Crescent Society provided training to IPs and UNHCR staff on H1N1 last August.

- Awareness campaigns were conducted by camp refugee health workers and continue to in Nepal and Bangladesh. In Malaysia, UNHCR communicated with refugee community leaders with regards to precautionary measures and to inform their community schools. One refugee community organization in Malaysia has organized its own H1N1 Prevention Program for their constituents. Translations of IEC materials were done in Thailand and Malaysia. There is a need to coordinate more with UNICEF Malaysia to include refugees in its activities as it considers refugees a sensitive issue.

- In Nepal, Bangladesh, Thailand awareness activities about influenza are now part of the routine health education activities in the camps.

- In India and Malaysia, health education is provided by refugee health workers to urban refugees; it has reached approx. 12,000 refugees in Kuala Lumpur.

VIII. Achievements per generic activities: Outbreak control: 95% achievement

- Outbreak control teams have been established and activated in most old camps; this process is building up in new ones.

- Contingency Plans developed in Kenya, Tanzania, Djibouti, East Sudan, and in Ethiopia camps. Outbreak control teams are established and activated in most old camps and in several new ones. Training on HIS, epidemiological surveillance and general epidemics ongoing in the regions, including in East Sudan, Ethiopia, Rwanda, Burundi, and Chad.

- In East and Horn of Africa, some camp contingency plans have been updated to account for ongoing H1N1 pandemic in Ethiopia, Kenya and East Sudan. At least 1 to 3 months supply of food and fuel is available in all refugee operations in the region. Between 8 and 20 weeks supply of antibiotics, antimalarials and intravenous fluids are available. Some Tami flu (1% of refugee population) and Personal Protective Equipment (PPE) are available.

MENA:

- Outbreak surveillance and reporting systems have been systematically strengthened in all MENA countries. In addition, systems for medical referral have been remarkably improved in Syria and Jordan which facilitates the overall pandemic response capacity to address any cases emerging among the urban refugee population.

- Surveillance systems are strengthened in all countries in MENA; referral system improved in Syria and Jordan. UNHCR tested its surveillance system in Tindouf camps, and there are still gaps to be filled. UNHCR recently discussed with WHO and will work to have the gaps filled. 15 packages of UNHCR Heath Information System (HIS) resources in French were sent to Algeria, and a plan to roll out UNHCR HIS in the camps is in the pipeline.

- Outbreak Control Teams were established in countries with refugee camps, and Outbreak Coordination Committees in urban settings, as well as in Tindouf camps.

Central Africa:

- In Rwanda: the reporting system is currently strong and the camp sites report directly to, and are supported, by the relevant Health District Office. The MOH has the capacity to confirm laboratory diagnosis of A (H1N1) and is routinely collecting and testing samples for seasonal influenza.

- In Burundi, the IP, AHA is implementing a reporting system using their team in the camp and keeping in contact with the WHO country office and MOH District Offices.

- In DRC, in IDP camps, IMC is implementing reporting systems whilst in other areas where IDPs live in towns and villages the routine reporting system of the MOH is applied. In Chad, camp cases are being reported to the relevant district hospitals supported by the UNHCR, IFRC and other partners.

- Key staff of UNHCR, IP, and MoH in DRC, Rwanda, Burundi, and Chad was trained on reporting and surveillance.

- In Central Africa, apart from Chad that could not be accessed due to security reasons, key staff of UNHCR, IP and the MOH were trained on reporting and surveillance.

Asia:

- In Thailand, MoH responded to the H1N1 outbreak in Mae La refugee camp by sending in a team to conduct an investigation. They have also agreed to provide Tamiflu for those needing treatment.

- In Malaysia and India, access of urban refugees to government health services during the outbreak (particularly in Kuala Lumpur) was monitored.

- UNHCR participated in the camp simulation exercise conducted by IRC in Thailand. Gaps were identified during this exercise which both UNHCR and IRC are trying to address, in collaboration with the MoH and WHO.

- Due to the deteriorating security situation in Pakistan, no reports were received regarding the H1N1 situation

IX. Coordination

- Regularly participated in the Interagency Emergency Network and Pandemic Influenza Coordination Team meetings at country level; and in coordination meeting at global level, and at camp level when held. Bilateral and multi- lateral coordination continued with OCHA, UNICEF, FAO, WFP, IOM, IFRC, CARE, SCF IFRC and national authorities.

- Regional Epidemic Preparedness and Response Coordinators (EPRCs) continue to provide technical support, ensure coordination with all stakeholders, and provided advice and information to the UNHCR country offices and IPs on preparedness, prevention and response aspects of H1N1.

- UNHCR Branch Offices, supported by the Regional EPRCS, continue to actively participate in the national coordination mechanisms. UNHCR participated in the training on "Home Care Influenza" organized by WHO and UNICEF in Myanmar. UNHCR participated in the review of Standard Operating Procedures (for outbreaks) in Thailand.

- Coordination at camp level is limited to few UN agencies mainly WFP.

X. Achievements per generic activities: Logistics and food pipe line contingency planning with WFP (85%)

- Monitored food stocks with WFP in case of disruptions by the H1N1 pandemic. Coordination ongoing with WFP for implementing a common food strategy in case of pandemic or major disaster continued; assessments and planning are undertaken in many target countries.

- In collaboration with WFP, conducted hazard-risk analysis for continuity of food provision in Chad; results will be utilized to update and modify WFP’s contingency plans.

- UNHCR and WFP collaboration continued to ensure continuity of food delivery during a pandemic. Joint WFP-HCR missions undertaken in several countries including in Kenya, Dadaab and Kakuma refugee camps where subsequently a joint food plan was developed after detailed assessment of food pipeline, transport corridors, storage capacity and distribution modalities. This plan is being implemented.

- UNHCR participated in a WFP’s logistic workshop for developing coordination in case of a crisis in Southern Africa region.

MENA: Ongoing joint planning with WFP specific to camp based operations.

Central Africa:

- In Rwanda and DRC, EPR coordinator is liaising with WFP counterparts for food pipe line contingency planning.

- Conducted a joint mission with the WFP, and visited health facilities and WFP food warehouse in the Brijuin refugee Camp using a hazard-risk analysis module that has been developed by WFP; thoroughly assessed services provided by IRC at the Bridjuin Camp paying special attention to the nutrition centre. WFP has a already a plan of action to continue provision of service in case of general disasters. The plan needs to be adopted for Abeche and pandemic influenza.

- Challenges

  - One of the challenging aspects for UNHCR was to ensure that refugees are included in the National Contingency Plan. Despite intensive advocacy efforts, the percentage of countries that included refugees in their AHI preparedness and response plans was 40%. This is not unique to influenza and requires continuous advocacy effort.

  - Despite progress made at country level, UNHCR is yet to get a global and clear picture of the actual level of operational preparedness in each country program. Frequent turn over of staff (both in UNHCR and in Implementing Partners) make difficult to sustain the staff awareness and their capacity to respond quickly in case of an outbreak. Maintaining the stockpile of the different items is also a big challenge.

  - The Epidemic Preparedness and Response program for refugees and other PoC could not be expanded to more operations as wished because of funding challenges and poor perspective in this matter.

  - In Pakistan, very limited activities could be implemented with regards to H1N1 due to security considerations and the emergency situation of displaced Pakistani population along the border

- Future Work Plan

Mainstreaming and maintaining at least a minimum level of outbreak preparedness acquired over the last few years is the main focus for 2010. UNHCR has to:

- Review country by country preparedness activities that can reasonably be sustained in the absence of specific program

- Develop simple assessment check lists to be used in routine monitoring exercises.

- Assess all existing programs, identify and address remaining gaps notably in term availability of IEC materials and business continuity under pandemic condition

- Develop an Epidemic Preparedness and Response strategic guidance document covering the main epidemic threats, including the risk of pandemic influenza of all kind, specifically designed for its use in camps hosting more than 5000 refugees

Being fully aware of the fragility of the epidemic preparedness in a quick changing environment, essentially part of the refugee nature, and moreover being aware of the frequent turnover of humanitarian staff, continue fundraising advocacy and sustain  adequate response  to mitigate the consequences of outbreaks on refugee populations.

# Footnotes

The term “programme” is used for programmes, joint programmes and projects.

E.g. Priority Area for the Peace building Fund; Thematic Window for the Millennium Development Goals Fund (MDG-F); etc.

The start date is the date of the first transfer of funds from the MDTF Office as Administrative Agent.

Refugees, internally displaced persons, returnees, asylum seekers, stateless persons, surrounding host populations, and other persons of concern

Cote d’ Ivoire, Guinea, Togo, Benin, Liberia, Sierra Leone, and Nigeria and Ghana