# United Nations Development Group Iraq Trust Fund

# Project #: D2-15

# Date and Quarter Updated:  September 2008, 3rd quarter

| Participating UN Organisation: WHO | Sector: Health and Nutrition |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Health |

| Title | Strengthening Medical Equipment Management and Maintenance System across Iraq |
| --- | --- |
| Geographic Location | [Baghdad, Basra, Erbil and Ninevah] |
| Project Cost | US$1,718,281 |
| Duration | 27 months, (including 3 extensions) |
| Approval Date (SC) | 18 Dec 2006 | Starting Date | 22 Dec 2006 | Completion Date | 28 March 2009 |
| Project Description | This program aims at restoring health care services and enhancing the quality and sustainability of health interventions by strengthening the medical equipment management and maintenance system as an integral part of public health system. |

# Development Goal and Immediate Objectives

The development goal and objectives of the project are: Quality of health care services improved and strengthened, through optimization of the Medical Equipment Management and Maintenance (MEMM) system across Iraq. Facilities and staff at Medical Equipment Sections at Departments of Engineering & Maintenance in Kimadia/Baghdad and five DoHs in Rasafa, Karkh, Basra, Ninewah, and Erbil strengthened Capacity of health care technology personnel across Iraq built Medical Equipment Management System strengthened.

# Outputs, Key activities and Procurement

| Outputs | By the end of the project the following outputs are expected Completed needs assessment of targeted medical equipment repair shops. Restored services of the biomedical equipment repair shops by providing test equipment, communication equipment and rehabilitating the infrastructure of the units. Improved skills of 235 health care technology personnel through attending in-country training, international training, conferences and Training of trainers training. 3.1 Supported operational guidelines and revision of medical equipment management policy in addition to establishment of monitoring and information system. |
| --- | --- |
| Activities | Designed a database for managing current inventory and aiding managers in their maintenance, repair and/or procurement decisions. Assessed the status of the maintenance units including staffing, test equipment, tools, physical structure, and availability of spare parts needed for maintenance and repair. Completed physical rehabilitation of biomedical equipment repair shops and furnished with test equipment, informatics, etc needed for the proper operation. Supported the biomedical equipment sections in: Operating according to procedures and rules. Procured teaching and tools (publications, books, soft-wares and devices). Providing mobile maintenance vehicles and service vehicles. Provided training for 235 health care technology personnel through in-country and international training programmes on proper maintenance and management. Established Medical Equipment Management Policy committee comprising DoH representatives and supported by WHO international consultants. Initiated plans and policies needed for project implementation; such as: identification of counterparts & management arrangements, including the supervision & monitoring. Established Medical equipment Management Information System. |
| Procurement (major items) | Procurement of 6 mobile maintenance vehicles, 2 service vehicles (Forklifts), test equipment and tools, informatics at cost of US$552,441 |

# Situation as of 30/09/2008

| Funds Committed | 1,568,430 | % of approved | 91% |
| --- | --- | --- | --- |
| Funds Disbursed | 895,942 | % of approved | 52% |
| Forecast final date | 28 Mar 2009 | Delay (months) | 18 months |

# Quantitative achievements against objectives and results

| Completed needs assessment of targeted medical equipment repair shops. | Assessment was done to quantify and access the present situation and address the needs as a first step in planning. An Assessment tool developed by WHO was used. The outcome of the assessment has helped the project committee to identify gaps and address them through the planned project activities (capacity building, procurement, etc). | % of planned | 100% |
| --- | --- | --- | --- |
| Restored services of medical equipment repair shops by providing test equipment, tools, mobile vehicle, furniture, rehabilitating the physical infrastructure & etc. | Procurement of test equipment, mobile vehicle, informatics, etc is finalized. Delivery to different sites in Iraq is under going. Rehabilitation activities of 4 medical equipment repair shops in Basra, Mosul, Erbil and Baghdad / Medical City are completed. One rehabilitation sites in Baghdad is under process. | % of planned | 83% |
| Improved skills of 235 health care technology maintenance personnel through attending in-country training, international training, conferences & Training of trainers training. | During reporting period, 6 training activities were successfully conducted for 80 medical equipment technology personnel in Baghdad, Erbil and Mosul. One international fellow ship for 3 persons for duration of 3 weeks was completed in the area of anaesthesia and surgical equipment. | % of planned | 95% |
| Supported operational guidelines & revision of medical equipment management policy in addition to establishment of monitoring and information system. | - WHO team conducted a 4-days technical meeting in Erbil on Medical Devices. The meeting was attended by biomedical engineers from different parts of Iraq and aimed at: * revising the procedures and systems followed to manage medical devices, * comparing national medical devices programma and procedures to regional and international ones, * develop a detailed plan of action towards achieving proper management of devices. - The data of the survey of biomedical equipment in 6 hospitals in Iraq is under verification process. The collected data will then be edited into access database. | % of planned | 85% |

# Qualitative achievements against objectives and results

| Although medical devices provide an opportunity for better health care services, the lack of a national system for selection, procurement, use and management may lead to a disproportionate escalation in health care delivery costs. Without proper management of demand, through actual needs assessment, adequate procurement, proper installation, preventive maintenance, rational usage and quality assurance, it will be difficult for health care providers to contain their costs. Thus, implementing a comprehensive Health care Technology Management System offers a range of solutions to address these requirements and to improve quality. The project has addressed following points, which have an impact on achieving the objectives: Developing a detailed plan of action towards achieving proper management of devices. This will support successful implementation and integration of a medical devices programme into national health system. Working on a computerized maintenance management system, which comprises equipment inventory, repair and maintenance history. Building the skills of healthcare technology personnel. Supported cooperation among DOHs in terms of technical consultations and expertise exchange. |  |
| --- | --- |