# United Nations Development Group Iraq Trust Fund

# Project #: D2-17

# Date and Quarter Updated: 15 July 2009 (1 April -30 June  2009)

| Participating UN Organisation: WHO, FAO and UNIDO | Sector: Health and Nutrition |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Health, Ministry of Agriculture and Ministry of Industries |

| Title | Rebuilding Food Safety and Food Processing Industry Capacity in Iraq |
| --- | --- |
| Geographic Location | All over Iraq (particularly in the governorates where the project sites for the rehabilitation of food control infrastructures are located: Baghdad, Basrah, Mosul, Erbil, Babil, entry points of Safwan in Basrah and Zorbatia in Wassit). |
| Project Cost | US$ 6,506,112 |
| Duration | 35 months. Initial period was for 18 months. |
| Approval Date (SC) | 16July 2006 | Starting Date | 04 August 2006 | Completion Date | 30 September 2009 |
| Project Description | This project is a WHO/FAO/UNIDO joint project to support three Ministries (MOH, MOA and MOI) as well as other relevant institutions to re-build food Safety programmes in Iraq and to improve standards in Food Processing Industries in Iraq. |

Development Goal and Immediate Objectives

The overall project developmental goal is to protect consumers’ health and increase potential of the food trade sector in Iraq through addressing current weaknesses of the food safety system and the gaps in the food production sector. The immediate objectives are to (a)create a coordination mechanism for a national food safety system, (b)strengthen the capacity of national institutions and their staff in food control (c)improve the environment for the development of entrepreneurship in food processing sector and (d)ensure food safety improvement throughout food continuum.

| Outputs, Key activities and Procurement (during the reporting period) |
| --- |
| Outputs | Capacity of Food Control services and infrastructures improved Supra-structures related to Food safety, including improved |
| Activities | Activities carried out during the reporting period include the following: Rehabilitation of selected Food control facilities (3 food control labs, model food industries and border food control facilities) Support the participation of Iraq to the work of Codex Alimentation and contribute to the consumer education. Capacity building and training activities in Food Inspection, food borne disease surveillance and good agriculture practices (GAP). Independent evaluation of the project |
| Procurement (major items) | Lab equipment, lab supplies/reagents, reference books, computers and connecting equipment needed by food control facilities have been ordered and delivery is ongoing but near completion. |

| Funds Committed | US$ 6,441,051 | % of approved | 99.0 |
| --- | --- | --- | --- |
| Funds Disbursed | US$ 5,604,380 | % of approved | 86.1 |
| Forecast final date | 30 September 2009 | Delay (months) | 20 |

| Direct Beneficiaries | Number of Beneficiaries | % of planned (current status) |
| --- | --- | --- |
| Men | Not applicable |  |
| Women | Not applicable |  |
| Children | Not applicable |  |
| IDPs | Not applicable |  |
| Others | Not applicable |  |
| Indirect beneficiaries | Whole population of Iraq |  |
| Employment generation (men/women) | About 225 labours (70 % male) | About 150 |
| Quantitative achievements against objectives and results (limited to the reporting period) |
| National Codex Committee for Iraq (NCCI) setup | MOH is sponsoring participants to Codex meetings from its own budget. UN agencies are providing administrative and logistic support for registration and visa issuance | % of planned | 100 |
| Food monitoring and food-borne disease surveillance enhanced and coordinated. Training in Good Agriculture Practices (GAP) | As it was recommended by the Project Steering Committee in its last meeting 3-4 December 2008, training courses on food borne disease surveillance and have been conducted inside the country. For the training on good agriculture practices (GAP), all the preparations (agenda and topics, lecturers, presentations, logistics) have been completed. However, due to the summer holiday, the course was postponed from mid July to mid August. | % of planned | 80 |
| Food Control facilities and applying HACCP principles in selected food industry facilities rehabilitated and strengthened | Lab Food control facilities rehabilitated and the rehabilitation of the Babil milk collection centre and Mosul dairy plant have now been completed. Installation of production equipment is completed and equipment already in use by the Mosul Dairy | % of planned | 100 |
| Food Inspection and food control of imported food improved through rehabilitation of food control facilities, including three regional food laboratories and two veterinary check points (Zurbatia and Safouan | Equipment and supplies for use in food inspection and Food quality control laboratories have been procured and the delivery of procured goods has been completed. The construction of Zurbatia check point was completed, inspected and delivered officially to MOA. Safouan check point: the construction of the building is completed. The work is progressing now with cement plastering of all external and internal walls and installation of electricity, telecommunication and water | % of planned | 95 |

Qualitative achievements against objectives and results (limited to the reporting period)

As it was reported in the quarterly report for Jan-March 2009, the rehabilitation of Food control infrastructures such as construction of food control facilities at the border check points by FAO/MOA, the rehabilitation of Food quality control laboratories of Basra, Mosul and Erbil by WHO/MOH and the rehabilitation by UNIDO/MOI of selected food processing industries to serve as HACCP model compliant industries was one of the major project components yet to be completed. Since then, a lot of progress has been made. The rehabilitation of all the three food control labs has been completed. The focus is now on installation of lab equipment and application training for the use of sophisticated lab devices such as HPLC. For the veterinary check points, the construction of Zurbatia check point was completed, inspected and delivered officially to MOA during the reporting period. For Safouan check point, the construction of the building is completed. The work is progressing now with cement plastering of all external and internal walls and installation of electricity, telecommunication and water. Regarding HACCP compliant facilities, the rehabilitation of both the Babil milk collection centre and Mosul dairy plant have now been completed. Installation of production equipment at Mosul Dairy Plant is also completed and equipment already in use. All in country training activities have also been completed except the training course on Good Agriculture Practices (GAP) which is scheduled to be conducted during July and August 2009 The process of starting the independent evaluation of the project has proven to be taking more time than initially anticipated but progress is being made and it is expected that the actual evaluation will start before September 2009 but its completion could go beyond 30 September 2009.

Main implementation constrains & challenges (2-3 sentences)

With the exception of the preparation of the independent evaluation which is taking longer than initially thought, there was no major implementation constrains experienced during the period under review.