# United Nations Development Group Iraq Trust Fund

# Project #: D2-18

# Date and Quarter Updated: 10 January 2009, 4th Quarter, October-December 2008

| Participating UN Organisation: WHO- UNICEF | Sector:: Health and Nutrition |
| --- | --- |
| Govt of Iraq Line Ministry Responsible: Ministry of Health |

| Title | Avian and Pandemic Influenza preparedness and control |
| --- | --- |
| Geographic Location | Iraq (National) |
| Project Cost | US$ 5,849,615 ( WHO:$ 4,365,921), (UNICEF:$1,483,694) |
| Duration | 18 months + 9 months extension |
| Approval Date (SC) | November 2006 | Starting Date | January 2007 | Completion Date | 31st March 2009 |
| Project Description | Through this project, national capacities for Avian Influenza control and prevention and preparedness for Pandemic Influenza are being strengthened by improving lab-based surveillance, providing needed equipments and materials, revising strategies and plans, supporting training activities, supporting Avian Influenza communications activities, rehabilitation of Avian Influenza isolation units, etc. |

# Development Goal and Immediate Objectives

The development goal and objectives of the project : The prime objective is to ensure health for all through saving lives, reducing the health impact of avian and pandemic influenza and minimizing disruption to health and other essential services in Iraq. This is in line with the MDGs and the UN assistance strategy for Iraq. Immediate Objective: To enhance national capacities to respond to Avian Influenza and to prepare for the Pandemic Influenza.

# Outputs, Key activities and Procurement

| Outputs | By the end of the project the following outputs are expected: Human Health Avian and pandemic influenza strategy is finalized and endorsed. Plans of actions at governorates levels will be finalized Training inside and outside Iraq is provided Communications between the governorates and the centre are improved. Focal points at governorate and central levels are identified and trained. Outbreak investigation teams at governorate and central levels are supported. Technical documents and infection control guidelines are printed and distributed Rehabilitation of two Avian Influenza isolation units to meet WHO infection control standards. Lab reagents, kits, and medical supplies are provided at central and governorate levels. Risk Communication Communication component of national action plan agreed upon, endorsed and implemented. Capacity of MOH/health education staff /health workers in implementing health education Programmes on AI is developed. Capacity of MOA/Vets in communication skills is developed. Quality resource materials developed including Q&As, advocacy materials, Leaflets & posters. Effective multi-strategy approach to the communication campaign is conducted Community participation initiatives for social mobilization are supported and capacity of Community volunteers in affected and high risk areas in community education is developed. Monitoring & evaluation activities conducted. |
| --- | --- |
| Activities | Human Health Finalize the national Avian and pandemic influenza strategy Conducting 100 training workshops for epidemiologists, physicians and health workers Providing training opportunities outside Iraq. Improving communications between the centre and the governorates. Identifying and supporting outbreak investigation teams at governorate and central levels Rehabilitation of two Avian Influenza isolation Providing Lab reagents, kits and other needed medical supplies Risk communication Support coordination meeting with national AI committee. Conduct orientation sessions for decision makers and Training of health workers Equip health education teams with loudspeakers and audio visual equipments. Conduct study tours for best practice areas in social mobilization. Development of quality resource materials for community educators, health professionals and target population. Conduct mobile health education campaigns at affected and high risk areas. |
| Procurement (major items) | -The procurement of lab reagents, kits and other medical supplies needed to improve lab based surveillance system has been completed and shipped to Baghdad. The procurement of medical suppliers needed for the isolation unit and to prepare for the Pandemic Influenza have been completed and most of the items have been shipped to Baghdad, Erbil and Basra. -In order to strengthen surveillance and to ensure timely reporting, different communication supplies have been procured by WHO and delivered to Baghdad. -Equip health education teams with loudspeakers and audio visual equipments have been procured. |

# Situation as of 31/12/2008

| Funds Committed | US$ 5,798,053 | % of approved | 99% |
| --- | --- | --- | --- |
| Funds Disbursed | US$ 4,965,561 | % of approved | 85% |
| Forecast final date | 31st March 2009 | Delay (months) | NA |

# Quantitative achievements against objectives and results

| Procurement of Medical Supplies and Equipment | -The procurement of lab reagents and medical supplies needed to improve lab based surveillance system has been completed and shipped to Baghdad. The procurement of medical suppliers needed for the isolation units and to prepare for the Pandemic Influenza have been completed. Different communication supplies have been procured by WHO and delivered to Baghdad. -Procurement and successful distribution of all communication equipments was completed -MOH, health education department has compiled a CD composing of different preventive messages to be distributed to schools, Youth centres, PHCs and to the mobile educational teams at governorate levels. | % of planned | 98% |
| --- | --- | --- | --- |
| Training Activities | -More than 85 training workshops have been conducted in Iraq. The aim of the workshops was to develop qualified teams of professionals who will be responsible for investigation of outbreaks of human Avian Influenza cases and provide immediate response to the outbreak. -Three Lab technicians have been trained in NAMRU3 between 15- 26 April 2007 and Two engineers have been trained in Beirut on the maintenance of Real Time PCR. PCR is essential for the rapid lab diagnosis of H5N1. -Technical Meeting on Rehabilitation of Avian Influenza Isolation Units in Baghdad – Erbil – Basra was held in Amman between 30 April – 2 May 2007. -WHO has fully supported the investigation for suspected Avian Influenza reported in Al Faw district in the Basra governorate in February 2008. -Many missions have been conducted by WHO International staff to Baghdad to support the national technical committee in updating the Avian and Pandemic Influenza Strategic Plan. -On 22 October 2008, WHO Iraq focal point for Avian and Pandemic Influenza has organized a meeting in Baghdad with Iraq AI technical committee to review and update the Avian- Pandemic Influenza strategic plan of action -All preparations have been done to provide 10 fellowships in the area of Avian-pandemic Influenza and these will be conducted in Cairo, Egypt. - Different training activities have been conducted in the area of communication, -To ensure quality monitoring of communication activities, 26 health education managers were specifically trained on Monitoring and evaluation. -UNICEF maintained its support to MoH to implement the national communication strategy at central and peripheral levels: -Symposiums with health professionals &doctors has been conducted; -Mobile educational campaigns for High Risk areas mainly marshland areas and remote private farms have been supported. -MoH health education department finalized the media assessment and identified 5 main local media channels that are mostly consumed by Iraqi’s. -UNICEF also Equipped Health education teams at governorate levels with laptop, projector and generator to facilitate mobile education sessions in remote areas. -New Animation TV spots were developed focusing on hygiene promotion and reporting specifically for school children are currently under development. -In collaboration with UNICEF office in Egypt and with MOHP Egypt , 5 health education managers from Baghdad , Missan , Babil , Erbil and Diyala have participated in a 5 day study tour in Egypt. - UNICEF facilitated establishment of coordination committee between MOH and MOE and incorporated AI orientations in the teacher training package. more than 1000 teachers were trained in 341 schools that were rehabilitated through UNICEF funds around 15 governorates -Second round on broadcasting key messages through the local media channel was also ensured with a total of 80,000 to intensify efforts during the migratory season of November and December. This was bolstered with the development of 3 new TV spots. -In line with the religious gathering during Muharram months, UNICEF supported the development of 200 flexes to be displayed in key areas in Baghdad and Governorates. | % of planned | 90% |
| Contracts | -Rehabilitation of AI isolation unit of Erbil has been completed while for Basra, the work has been started since five months; about 40% of the work has been done | % of planned | 90% |
| Printing of educational materials | -Printed materials in Arabic and Kurdish were distributed in batches for all governorates -UNICEF is in the process of printing 15,000 copies of the facts for better life in Arabic and 5,000 copies in Kurdish,. The new version included a new chapter on prevention from AI.UNICEF is also printing new materials on hand washing and hygiene promotions in Arabic | % of planned | 100% |

# Qualitative achievements against objectives and results

Since over three years, WHO and UNICEF are providing full technical and logistic support to reduce opportunities for human H5N1 infections and to strengthen early warning system in Iraq. Committees have been established to implement the national preparedness plan. To date, only three cases of human H5N1 have been confirmed in Iraq. Since March 2006 no new cases have been reported. During the H9 N outbreak in Basrah, The response including the communication social mobilization activities at different levels was quite satisfactory with the timely interventions at field level including conduction of mobile education campaign.