# United Nations Development Group Iraq Trust Fund

# Project Summary Sheet

# Updated: 31 March 2008

# Programme/Project Number: D2-20

| Participating UN Organisation: WHO | Cluster: D – Health and Nutrition |
| --- | --- |
| Govt of Iraq Line Ministry Responsible: Ministry of Health |

| Title | Communicable Diseases Prevention and Control Programme |
| --- | --- |
| Location | Iraq (Nationwide) |
| Project Cost | US$ 5,233,263 |
| Duration | 18 months |
| Approval Date (SC) | 27 February 2007 | Starting Date | May 2007 | Completion Date | October 2008 |
| Project Description | Supporting the implementation of communicable diseases prevention and control activities including surveillance of and outbreak response to; water born diseases, vector born diseases, tuberculosis, HIV and other communicable diseases. |

# Development Goal and Immediate Objectives

The development goal and objectives of the project : To control and prevent communicable diseases in all Iraq Immediate Objectives: To strengthen disease surveillance and outbreak response at central and governorate levels To prevent and control vector born and Zoonotic diseases To maintain low prevalence of HIV/AIDS through strengthening of HIV/AIDS surveillance system To maintain high TB treatment success rate and to improve TB case detection rate

# Outputs, Key activities and Procurement

| Outputs | By the end of the project the following outputs are expected: Disease surveillance and outbreak response strengthened at central and governorate levels. Vector control prevention and control activities are conducted including indoor spraying, fogging, entomological surveillance and rodent control activities. Zoonotic diseases prevention and control activities are supported HIV/AIDS prevention and control activities are supported including community awareness, capacity building, 2nd generation surveillance and voluntary counselling and testing. TB prevention and control activities are supported including training, community awareness activities, monitoring and evaluation. |
| --- | --- |
| Activities | Conducting 20 training workshops on diseases surveillance system at governorate and district levels. Providing urgently needed lab reagents, kits and equipments necessary for lab based disease surveillance. Supporting outbreak investigation and response teams at central and governorate levels by providing them with necessary training and support. Conducting 20 training workshops for health workers on the control and prevention of water born diseases, including Viral Hepatitis, Cholera and Typhoid fever amongst others. Supporting community awareness activities on the prevention of water born diseases by conducting 30 advocacy meetings. Providing 30 fellowships on communicable diseases surveillance and outbreak response including fellowships on Viral Hepatitis. Conducting Communicable diseases (disease surveillance, water born diseases, vector control, viral hepatitis, etc) supervision and monitoring activities. Conducting 10 advocacy meetings to raise community awareness on Leishmania and Malaria prevention Conducting 10 workshops for health workers to improve their awareness concerning Leishmaniasis and Malaria prevention and control. Conducting 2 Malaria and Leishmania spraying and fogging campaigns. Printing and distributing advocacy materials taking into consideration Malaria elimination Conducting 19 entomological surveys in all governorates. Conducting 19 rodent control campaigns in all governorates. Conducting 10 training vector control workshops. Conducting10 vector control advocacy meetings. Conducting 5 vector control fellowships. Conducting spraying activities in waste dumping, garbage and water collection sites. Monitoring of insecticide resistance through providing the necessary kits. Providing 5 fellowships on Schistosomiasis control and prevention Conducting 10 advocacy meetings to raise community awareness concerning Schistosomiasis prevention Conducting 10 workshops for health workers to improve their awareness concerning Schistosomiasis prevention and control Conducting Snail (Vector control) spraying campaigns Conducting a Schistosomiasis research study. Conducting a joint epidemiological survey on Brucellosis in Iraq with the Ministries of Health and Agriculture. Providing 4 fellowships on epidemiology, prevention and control of Rabies and Brucellosis for medical and paramedical staff. Conducting 20 HIV/AIDS workshops on HIV/AID surveillance including 2nd generation surveillance. Evaluating and monitoring of HIV/AIDS surveillance activities Improving community participation and awareness through provision and distribution of materials, Initiating HIV/AIDS voluntary and counselling units Providing 10 HIV/AIDS fellowships on HIV/AIDS surveillance including 2nd generation surveillance Providing diagnostic kits and Anti Retroviral (ARV) drugs. Conducting 20 TB workshops all over Iraq to maintain and improve DOTS (Directly observed treatment, short-course) Conducting 20 TB advocacy meetings to increase community awareness. Conducting evaluation and monitoring activities at central and peripheral levels Conducting quarterly TB meetings |
| Procurement (major items) | 5 millions water purification tablets for the Cholera outbreak (60,000 US$) 10 Cholera kits ( 112,000 US$) Anti Malaria Drugs Anti Retroviral Drugs to treat HIV/AIDS |

# Situation as of 31/03/2008

| Funds Committed | US$ 2.635,722 | % of approved | 50% |
| --- | --- | --- | --- |
| Funds Disbursed | US$ 1,635,446 | % of approved | 31% |
| Forecast final date | October 2008 | Delay (months) |  |

# Quantitative achievements against objectives and results

| Procurement of medical Supplies and equipment | List of communicable disease laboratory needs to improve lab based surveillance has been revised and sent to the regional office for procurement. 5 millions water purification tablets have been procured for the Cholera outbreak (60,000 US$) 10 Cholera kits have been procure during the outbreak (112,000 US$) WHO has procured Ant Malaria drugs and Ant RetroViral Drugs to treat HIV/AIDS | % of planned | 60% |
| --- | --- | --- | --- |
| Training activities | 22 epidemiology fellowships have been provided 14 fellowships on Viral Hepatitis prevention and control have been provided in Egypt. Three Iraqis are being supported to get masters degree in Epidemiology WHO has supported (in a technical and logistical facility): 7 vector control workshops. Two Hemorrhagic Fever training workshops. 5 Malaria advocacy meetings. 17 advocacy meetings on water born diseases prevention and control. 6 workshops on water born diseases prevention and control 8 workshops on improving communicable diseases surveillance. 5 Schistosomiasis advocacy meetings. 9 Schistosomiasis training workshops. WHO has participated in the United and Healthy Medical Conference (22 March 2008) and Sixth Scientific Conference of Salah al-Din (23-24 March 2008) Numerous missions have been conducted by WHO International staff during the Cholera outbreak and during the first three months of 2008 to prepare for a second wave of Cholera | % of planned | 70% |
| Contracts | Full technical and logistic support was provided for two Malaria and Leishmania spraying campaigns conducted in May and September 2007 All preparations have been completed to conduct the first Malaria and Leishmania spraying campaign for 2008 WHO has supported multiple communicable diseases investigation activities: spraying campaigns to prevent Schistosomiasis Spraying campaigns in water collection and damping sites 19 rodent control campaigns 19 entomological surveillance campaigns Malaria active detection survey Communicable diseases monitoring and Evaluation activities Preparations are going on to conduct the nationwide Schistosomiasis survey | % of planned | 70% |

# Qualitative achievements against objectives and results

2007 data indicated that there was a decrease in the incidence of many communicable diseases. Only three Malaria cases were reported during 2007; two of them were from Sidican village/ Serwan district/Erbil and one imported case from Ethiopia. This indicates that Iraq is close to Malaria elimination. Only 806 cases of Kalazar were reported during 2007(Excluding Anbar), while 1572 cases were reported during 2006, 2059 cases during 2005 and 3218 cases during 2004, this demonstrates a steady decrease in cases. The majority of Schistosomiasis cases reported during 2007 were from two districts; Baladroz in Diala and Al- Qaem in Anbar, WHO is supporting several prevention and control activities in these two districts. Iraq maintains low prevalence of HIV/AIDS This achievements in Malaria and Leishmania are due to the comprehensive package of prevention and control activities conducted during the previous years by Ministry of Health with full technical and logistic support from WHO on number of other activities, including early diagnosis and response, indoor spraying, fogging, entomological surveillance activities and rodent control activities.