# United Nations Development Group Iraq Trust Fund

# Project #: D2-11 ATLAS# award 54892, project 66892

# Date and Quarter Updated: 1st Quarter 2009 (01 January 31 March 2009)

| Participating UN Organisation: WHO | Sector: Health and Nutrition |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Health |

| Title | Emergency Medical Oxygen Supply and Production (Project recently reprogrammed for Emergency Humanitarian Response) |
| --- | --- |
| Geographic Location | No specific location (Implementation coordination is done at central level but beneficiaries are located all over the country) |
| Project Cost | US$ 2,824,760 |
| Duration | 9 September 2005-30 November 2006, suspension of activities and then resumption from 10 April 2008- 31 December 2008 , The first extension from 31 December 2008 to 31 March 2009 and second from 1 April to 31 October 2009. |
| Approval Date (SC) | 1 September 2005 | Starting Date | 9 Sept 2005 | Completion Date | 31 October 2009 (see extensions under “Duration” above) |
| Project Description | The original project (a quick impact project) aimed at providing medical oxygen to all hospitals in Baghdad, Mosul and Kirkuk governorates as a temporally measure for these hospitals to meet their six month oxygen needs, the time for the MOH to find a suitable solution for a long term oxygen supply solution. The project sought also to provide a reliable, sustained and long term arrangements for an uninterrupted oxygen supply in Iraq through installation of 3 medium size oxygen production plants/units (1 in Baghdad, 1 in Basrah and 1 in Diwaniyah) as a pilot project to be expanded to the entire country with government own resources. However, following several obstacles which were reported in the previous reports, the implementation of the project component for the procurement and installation of the three oxygen plants was interrupted in November 2006 and a decision was taken by WHO in March 2007 to return the remaining funds. However, because of urgent needs faced by the country, particularly in March- April 2008, the Ministry strongly recommended the use of available funds for emergency humanitarian response. Based on the Ministry’s request, the DSRSG, Chairperson of the UNDG ITF Steering Committee approved on 10 April 2008 the project scope change but put the strict condition that the project will have to be completed by 31 December 2008. Details regarding the four main activities under the revised project are given under section: “Key activities and procurement” below. |

Development Goal and Immediate Objectives

The main development goal and immediate objectives of the project remain almost the same as in the initial project. These include two aspects: Increase access to quality health intensive care services especially for vulnerable groups and increase emergency preparedness and response capacity to deal with emergencies; Reduce disability and mortality, including maternal and less than 5 mortality rate due to the lack basic emergency medicines, including oxygen and other anesthetics among patients requiring emergency health care.

| Outputs, Key activities and Procurement |
| --- |
| Outputs | Timely response to emergencies in intensive care units through better access to needed emergency medicines and supplies Improved outcomes of visits to hospital emergency units with reduced morbidity and mortality |
| Activities | Under the reprogrammed project there are four main activities planned which are: Provision of a list of emergency medicines and supplies requested by the MOH. Replacement of some of the basic life support equipment and supplies in a number of ambulances Capacity building (training of trainers) on professionals involved in emergencies with focus on workers involved in first aid and ambulance management and blood transfusions Update the report of on first aid and medical gases services which was conducted early 2006. |
| Procurement (major items) | Procurement of emergency medicines and medical supplies, life support equipment and supplies for ambulances. |
| Funds Committed (as of 31 March 09) | US$ 2,22,570 | % of approved | 79 |
| Funds Disbursed | US$ 1,582,131 | % of approved | 56 |
| Forecast final date | 31 October 2009 | Delay (months) | 44 |

| Direct Beneficiaries | Number of Beneficiaries | % of planned (current status) |
| --- | --- | --- |
| Men | Not applicable (beneficiaries are patients) |  |
| Women | Idem as above |  |
| Children | Idem as above |  |
| IDPs | Idem as above |  |
| Others | Idem as above |  |
| Indirect beneficiaries | Any patient in Iraq is an indirect beneficiary |  |
| Employment generation (men/women) | About 5 of which 3 are male |  |

| Quantitative achievements against objectives and results |
| --- |
| Review and update the report on national survey on first aid and medical gases | Raw data are being reviewed | % of planned | 50 |
| Provision of a list of emergency medicines and supplies | Most of items which were requested by the MOH have been procured and the first shipments were delivered during the period under review. | % of planned | 80 |
| Replacement of basic life support equipment and supplies in a number of ambulances | The list of supplies needed for use in ambulances have been procured | % of planned | 90 |
| Capacity building (training of trainers) on professionals involved in emergencies with focus on workers involved in first aid and ambulance management and blood transfusions | In addition to the 29 health professionals (nurses and paramedics) trained in November 2008 at the Jordan Civil Defence Directorate, a total of 15 professionals working for the National Blood Transfusion Center have completed in February 2009 their training at the Jordan Directorate for Blood Banks | % of planned | 100 |

Qualitative achievements against objectives and results (limited to the period under review)

The process of updating the assessment report on first aid and medical gases in Iraq is currently challenged by lack of institutional memory as most the staff who participated to the survey are no longer working in the Ministry of Health. However, the work is progressing in the right direction. Regarding the procurement process of items requested by the Ministry of Health, there were 3 separate lists of 9 anaesthetics, 42 sutures of different types and 10 types of external fixation devices. Purchase orders have been issued for all these items except for the fixators for reasons which have been explained in the previous updates. Following is the delivery status of each one of these item categories: Sutures: All the 42 different types of sutures ordered have been delivered to Iraq with a total value of $213,780 Purchase orders for all the 10 anesthetics have been issued with a total value of about $500,000. The delivery to Iraq is complete for 8 of them. The two remaining items Suxamethonium Chloride 50mg/ml and Fentanyl 50mcg/ml), these are being shipped to Iraq at the time of preparing this report March 2009. Quadruple blood bags with a total value of $97,200 have been ordered and have been delivered in April 2009. Part of the consignment will be used to reimburse the loan previously given by the Jordan Ministry of Health to Iraq. For the external fixation devices as previously indicated, the determination of specifications took longer than anticipated. Correct specifications have now been received from the MOH and a purchase order is being prepared at the time of preparing this report. Also, the supplier has indicated that the delivery will be done in staged installment.

Main implementation constraints & challenges (2-3 sentences)

High turn-over of technical staff of the Ministry of Health has made difficult the review and update of the survey on First aid and medical gases but solutions are being found. The procurement of specialized items such as external fixation devices took longer than expected due to limited stock available on the international market as well as limited capacity inside the country to provide the required specifications.