# United Nations Development Group Iraq Trust Fund

# Project Number: E3-04

# Updated: 1st Quarter 2008/31 March 2008

| Participating UN Organisation: UNDP | Cluster: E – Infrastructure Rehabilitation |
| --- | --- |
| Govt of Iraq Line Ministry Responsible: Ministry of Electricity |

| Title | Emergency Rehabilitation of Karama Water Treatment Plant – Line I |
| --- | --- |
| Location | Karama, Baghdad, Ittefiya, Karkh |
| Project Cost | US$ 2,955,875 |
| Duration | 15 month |
| Approval Date (SC) | 29.08.2005 | Starting Date | November 2005 | Planned Completion Date | Jan 2007 (pending time extension) |
| Project Description | The rehabilitation of Karama Water Treatment Plant Line I will increase the plant’s production by 40% and bring the total plant’s output back to the pre 1990 capacity of 35 MGD. The sustainability of the project will be ensured by improving the managerial and technical capabilities of the staff at the plant, in addition to selected staff from the Baghdad Water Authority and the Mayoralty of Baghdad. |

# Development Goal and Immediate Objectives

1 Increase production of Karama Water Treatment Plant in Baghdad by 10 MDG 2 Increase reliability and long term operation of Karama water treatment plant 3 Water Quality monitoring and testing laboratory of the plant capable of conducting daily, weekly and monthly tests according to international testing standard procedures.

# Outputs, Key activities and Procurement

| Outputs | Outputs 1.1. Production increased by additional 10 MGD of potable water. 2.1 The reliability and long-term operation of the whole of Karama water treatment plant is improved by 40%. 2.2 The staff of MoB, BWA and Karama WTP has the capacity to manage the potable water system. 3.1 A functioning Water laboratory. 3.2 Staff trained in water testing techniques |
| --- | --- |
| Activities | Key Activities 1.1.1 Procurement of materials and labour for rehabilitation and renovation of Karama W.T.P. Line I to its design capacity of 10 MGD. 2.1.1 Procurement of sand filter media for one-year operation. 2.2.1 Management development of the staff of the laboratory, the staff at the plant, the staff of the Baghdad Water Authority and Baghdad Mayoralty. 2.2.2 The management and staff of MoB, BWA and management of Karama W.T.P. will be trained on, technical, and operating skills. 3.1.1 Supply of materials and equipment for the laboratory’s water quality testing equipment and sand filters for one year’s operation 3.1.2 Provision of training in Water Analysis |
| Procurement (major items) | See above. |

# Situation as of 31/03/2008

| Funds Committed | US$ 2,808,077 | % of approved | 95% |
| --- | --- | --- | --- |
| Funds Disbursed | US$ 2,549,308 | % of approved | 90% |
| Forecast final date | September 2008 | Delay (months) | 20 |

# Quantitative achievements against objectives and results

| Rehabilitation by local contractor | Physical work implementation commenced | % of planned | 12 |
| --- | --- | --- | --- |
| Drawings, manuals and test certificates | Receipt of final deliverables for Phase II of the consultancy assignment: Bills of quantities verification for subsequent dispatch as part of the bidding documents. | % of planned | 90 |
| Training of Trainers | Capacity assessments completed and bidding process ongoing. | % of planned | 50 |

# Qualitative achievements against objectives and results

Evaluation and development of a variation order report for the envisaged additionally required scope of work. Development and study of proposals for additional works uncovered in the course of implementation. Final implementation work plan received from contractor. Review and verification of all project technical requirements, required modifications, etc in light of changes that took place from technical documentation development to date nearing completion. Site handover to contractor carried out on November 10, 2007, and project implementation commenced. Project implementation kick-off meeting was held 21-28 October including UNDP, Baghdad Water Authority, Mayoralty of Baghdad, Consultant and Contractor. Agreement on all implementation related technical, operational, logistical, issues was reached. Project jobsite handover and effective contract dates determined as 3 and 10 November 2007 respectively. Negotiations with the selected contractor, Power Engineering World, completed and final agreement regarding pending items concluded. Implementation contract entered.