# United Nations Development Group Iraq Trust Fund

# Project #:E3-04-00046959

# Date and Quarter Updated: 1 October-31 December 4th Quarter 2008

| Participating UN Organisation: UNDP | Sector: WatSan |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Mayoralty of Baghdad/Baghdad Water Authority |

| Title | Emergency Rehabilitation of Karama Water Treatment Plant – Line I |
| --- | --- |
| Location | Baghdad Governorate, Baghdad City, Karama Area |
| Project Cost | US$ 2,955,875 |
| Duration | 15 months |
| Approval Date (SC) | 29.08.2005 | Starting Date | November 2005 | Completion Date | January 2007 (Original date) |
| Project Description | The rehabilitation of Karama Water Treatment Plant (WTP) Line I will increase the plant’s production by 40% and bring the total plant’s output back to the pre 1990 capacity of 35 MGD. The sustainability of the project will be ensured by improving the managerial and technical capabilities of the staff at the plant, in addition to selected staff from the Baghdad Water Authority (BWA) and the Mayoralty of Baghdad (MoB). |

# Development Goal and Immediate Objectives

Increase production of Karama Water Treatment Plant in Baghdad by 10 MDG Increase reliability and long term operation of Karama water treatment plant Water Quality monitoring and testing laboratory of the plant capable of conducting daily, weekly and monthly tests according to international testing standard procedures.

# Outputs, Key activities and Procurement

| Outputs | 1.1. Production increased by additional 10 MGD of potable water. 2.1 The reliability and long-term operation of the whole of Karama water treatment plant is improved by 40%. 2.2 The staff of MoB, BWA and Karama WTP has the capacity to manage the potable water system. 3.1 A functioning water laboratory. 3.2 Staff trained in water testing techniques. |
| --- | --- |
| Activities | 1.1.1 Procurement of materials and labour for rehabilitation and renovation of Karama W.T.P. Line I to its design capacity of 10 MGD. 2.1.1 Procurement of sand filter media for one-year operation. 2.2.1 Management development of the staff of the laboratory, the staff at the plant, the staff of the Baghdad Water Authority and Baghdad Mayoralty. 2.2.2 The management and staff of MoB, BWA and management of Karama W.T.P. will be trained on technical and operating skills. 3.1.1 Supply of materials and equipment for the laboratory’s water quality testing equipment and sand filters for one year’s operation 3.1.2 Provision of training in Water Analysis |
| Procurement (major items) | Procurement of materials and labour for rehabilitation and renovation of Karama W.T.P. Line I to its design capacity of 10 MGD. Procurement of sand filter media for one-year operation Consultancy Services Works Contract |

| Funds Committed | US$ 2,745,063 | % of approved | 93 |
| --- | --- | --- | --- |
| Funds Disbursed | US$ 2,662,155 | % of approved | 90 |
| Forecast final date | December 2008 | Delay (months) | 22 |

# Quantitative achievements against objectives and results

| Rehabilitation by local contractor | Physical work implementation completed. Final testing and commissioning completed. | % of planned | 100 |
| --- | --- | --- | --- |
| Drawings, manuals and test certificates | Receipt of final deliverables for Phase II of the consultancy assignments: Bills of quantities verification for subsequent dispatch as part of the bidding documents. Completion of the Construction supervision Phase | % of planned | 100 |
| Training of Trainers | Capacity assessment has been completed. Al Karama WTP Technicians-Baghdad Water Authority-Water Department have participated in the following training courses: Instrumentation (4 participants), Recording and Documentation (2 participants), Safe Handling of Chemicals(2 participants), Laboratory Equipment Usage and Statistical Analysis 916 participants) | % of planned | 100 |

# Qualitative achievements against objectives and results

Third Party Inspection (TPI) was completed for all the project supplies Receipt of all project supply lots at the job site Final testing and inspection on 20 November 2008 Minor issues identified in final testing and inspection completed. Issuance of the Certificate of Substantial Completion issued December 2008 Project operationally closed