# United Nations Development Group Iraq Trust Fund

# Project Number: E3-08

# Updated: 1st Quarter 2008/31 March 2008

| Participating UN Organisation: UNDP | Cluster: E – Infrastructure Rehabilitation |
| --- | --- |
| Govt of Iraq Line Ministry Responsible: Ministry of Municipalities and Public Works Directorate of Municipalities-Basra Governorate; Municipality of Umm Qasr |

| Title | Addressing Short and Long Term Water and Sanitation Needs for the Umm Qasr Region |
| --- | --- |
| Location | Umm Qasr, Basrah Governorate |
| Project Cost | US$ 1,020,000 |
| Duration | 15 month |
| Approval Date (SC) | 16 Jul 2006 | Starting Date | Sep 2006 | Panned Completion Date | Dec 2007 (extension pending) |
| Project Description | Provision of water and sanitation supplies, works and services for the port city of Umm Qasr Assessment of water and sanitation situation and needs including the sewerage and solid waste conditions |

# Development Goal and Immediate Objectives

To achieve significant progress in six key areas – increasing access to potable water in urban areas, increasing sewage treatment and access to urban sewerage systems, increasing solid waste collection and disposal, raising access to potable water in rural areas, increasing sanitation services in rural areas, and contributing towards efficiency improvement of the public management systems in Iraq. Key Immediate Objectives: Increase access to potable water to the local impoverished population by decreasing the port commercial water demand, thus availing such at reasonable prices to the community Public Health risks from solid wastes and organic waste build up will be reduced 3. Contribute to the socio-economic development of Umm Qasr town through (i) employment creation and (ii) alleviating the financial burdens on inhabitants by providing water to the port and thence decreasing the demand on the expensive vendor supplied water. Assess the short- and medium-term needs and requirements of the water and sanitation sector in Umm Qasr.

# Outputs, Key activities and Procurement

| Outputs | 1.1 An autonomous source of potable water will be availed for and operated by Umm Qasr port. 1.2 RO units Operation and Maintenance training for local staff will insure sustainability of provided assets. 2.1 420 tons of solid waste (i.e. 10 trips per day x 8 cubic meters x 0.75 ton per cubic meter x 7 days) will be collected per collection cycle (week) from the streets of Umm Qasr village, thanks to the collection equipment provided 3.1 Short and long term employment opportunities focussing on unskilled labourers’ jobs will be created, price of clean water will be decreased. 4.1 Water supply, wastewater systems and solid waste management needs, which will facilitate impact assessment studies, shall be assessed through a consultancy services assignment by a local consultant firm working in close collaboration with all relevant local authorities keyed to assessing the short, medium and long term requirements. |
| --- | --- |
| Activities | Procurement and implementation of equipment, supplies, works and services to rehabilitate the RO units (including consumables), drill groundwater wells and install storage tank in Umm Qasr Port. Delivery of Training services shall be acquired for provision of Operation and Maintenance training for local staff for RO units. 2.1.1 Procurement of solid waste bins for Umm Qasr village. 2.1.2 Procurement of garbage removal truck (i.e. skip loader) for Umm Qasr village. 3.1.1 Cleaning of storm water drainage network, repair and replacement of 15km urgently required water distribution network works and construction of 4 septic tanks, RO operation, through LoU with Umm Qasr Town Council, creating temporary and longer-term employment. 4.1.1 Procurement of consultancy services for the detailed situation analysis of the water and sanitation systems in Umm Qasr and formulation of the emergency requirements for alleviating the associated burdens. Safwan, Shuaiba, and Khor Zubair will be covered if time and funds allow |
| Procurement (major items) | One (1) Solid Waste Skip Loader 100 Solid Waste Containers |

# Situation as of 31/3/2008

| Funds Committed | US$ 1,020,000 | % of approved | 100 |
| --- | --- | --- | --- |
| Funds Disbursed | US$ 918,781.3 | % of approved | 90 |
| Forecast final date | June 2008 | Delay (months) | 7 |

# Quantitative achievements against objectives and results

| Spare parts and equipment | The RO unit together with solid waste collection equipment have been delivered on site. | % of planned | 100 |
| --- | --- | --- | --- |
| Drawings, manuals and test certificates | The assessment is being finalized | % of planned | 100 |
| Training of Trainers | RO unit operation and maintenance training for local staff will be delivered upon installation. | % of planned | 25 |
| Pre-shipment inspection. | Third party inspection of RO unit completed successfully. | % of planned | 100 |

# Qualitative achievements against objectives and results

This project targets the provision of water and sanitation supplies, works and services for the port city of Umm Qasr together with an assessment of water and sanitation situation and needs including the sewerage and solid waste conditions. The assessment has been finalized. UNDP monitored the bidding process and advised on ways to obtain more responsive Bids, and supported Basrah Governorate in developing a new contractors list and finalizing revised bid documents. Basrah Governor’s approval obtained for issuing a public invitation to bid for the works.