# United Nations Development Group Iraq Trust Fund

# Project: E3-12a

# Date and Quarter Updated:  2nd Quarter, April- June 2009

# OPERATIONALLY CLOSED

| Participating UN Organisation: UN Office for Project Services (UNOPS) | Sector: Cluster E – Infrastructure Rehabilitation (WATSAN) |
| --- | --- |
| Govt of Iraq - Responsible Line Ministry: Ministry of Municipalities and Public Works (MMPW) |

| Title | Rehabilitation of Water Distribution Systems in Sidakan and Rawanduz |
| --- | --- |
| Geographical Location | Towns of Sidakan and Rawanduz, Soran District, Erbil Governorate |
| Project Cost | US$2,496,475 |
| Duration | 10 months originally, extended up to 27 months |
| Approval Date (SC) | 27 February 2007 | Starting Date | April 2007 | Completion Date | January 2008 –Original Extended up to 30th June 2009 OPERATIONALLY CLOSED |
| Project Description | Extension and rehabilitation of the existing water distribution network and the construction of reinforced concrete water storage tanks. |

# Development Goal and Immediate Objectives

The Development Goal of the project is to contribute towards improvement in the public health of the inhabitants by increasing the availability of safe drinking water. The project contributes to achieving WATSAN Sector Outcome 1: Sustainable access to safe water for urban and rural populations increased. It further contributes to the achievement of the following Millennium Development Goals (MDGs): Reducing by half the proportion of people without access to safe drinking water and sanitation (MDG 7) Halting and reversing the incidence of malaria and other diseases (MDG 6) Reducing child mortality (MDG 4) Improving maternal health (MDG 5) Immediate objectives: To significantly augment the quality and quantity of water supplied to 10,000 consumers in Sidakan town and 20,000 consumers in Rawanduz town by constructing replacement reservoirs and rehabilitating and extending the existing transmission and distribution mains utilising improved pipe materials and jointing techniques to reduce maintenance costs for the life of the new pipe system. To provide a comprehensive purpose-developed training course in water supply network design and management to at least 30 technical staff of the Directorate of Water and Sanitation so as to improve quality and efficiency throughout the whole management cycle (planning, execution, monitoring) for service provision.

# Outputs, Key activities and Procurement

| Outputs | 30,000 consumers will have improved quantity and quality of water available brought about through reduced contamination and a reduction in losses in the pipe distribution system. Short-term employment creation for over 150 personnel for construction activity during project implementation. Thirty (30) government employees are able to pass on their knowledge to others and to plan, implement, monitor and manage water supply projects in the urban areas. |
| --- | --- |
| Activities | Install about 9 km and 3 km of water supply mains in Sidikan and Rawanduz towns respectively; Construction of one (1) collection tank of capacity 8m3 in Rawanduz and two (2) collection tanks of 12 m3 each in Sidakan towns in addition to one service reservoirs of 750 m3 in Sidakan town to improve the supply and to reduce contamination in stored water. Install about 11 km and 5 km of water supply mains in Sidikan and Rawanduz towns respectively; Construction of fence (compound wall) around the Sidakan water source to protect from pollution. Hire and deploy an estimated 150 skilled and unskilled labourers from vulnerable groups, for the 9 month project duration; Deliver a purpose-designed training course of six-day duration to 30 technical personnel from the MMPW on current design concepts for new or expanded networks; use of new materials and techniques to develop, rehabilitate, operate and maintain water distribution networks; |
| Procurement (major items) and on site activities | The project was awarded to M/s Galaiwa Contracting Company for implementation of the project. The procurement and implementation of all the assigned High Density Polyethylene pipes (HDPE) in addition to the entire related PE fittings was conducted and the network was implemented and tested. Completed the implementation of the works as planned originally (the details of the works are given in item 1. of Activities, mentioned above) and handed over to the water authority. The contract to implement the additional works (approval was received in May 2008) was awarded to M/s Galaiwa Contracting Company. Procurement of material for additional (the details of the works are given in item 2. of Activities, mentioned above) works were completed. Completed the additional works as per specifications and drawings. The Rawanduz Town was handed over to the concerned authority The Siddakan town will be handed over to the concerned authority. |

# Situation as of 30/06/2009

| Funds Committed | 2, 496,475 | % of approved | 100 |
| --- | --- | --- | --- |
| Funds Disbursed | 2,045,486 | % of approved | 82 |
| Forecast final date | June 2009 | Delay (months) | 18 months |

| Direct Beneficiaries | Number of Beneficiaries | % of planned (current status) |
| --- | --- | --- |
| Men | 30,000 | 150% achieved |
| Women |  |  |
| Children |  |  |
| IDPs |  |  |
| Others |  |  |
| Indirect beneficiaries |  |  |
| Employment generation (men/women) | 150 | 150% |

# Quantitative achievements against objectives and results

| Site preparations and contract awarding for civil work | Survey and design document of the civil works with full specifications was finalized. A contractor to install and rehabilitate the water mains and construct the water tanks for both sites was chosen and awarded. Mobilization of material, manpower and equipment was fully completed. | % of planned | 100 |
| --- | --- | --- | --- |
| Procurement of pipes and fitting | For originally planned works Procured 100% of High Density Polyethylene pipes (HDPE) and related PE fittings. All pipes and fitting were strictly crosschecked against the ISO 9001 certification from the International Organization for Standardization and were approved. | % of planned | 100 |
|  | For Additional works Procured all the required Polyethylene pipes (HDPE) and related PE fittings. All pipes and fitting will be as per ISO 9001 certification from the International Organization for Standardization. |  | 100 |
| Civil work and rehabilitation | For originally planned works Completed and handed over to the water authorities. | % of planned | 100 |
|  | For Additional works Mobilized machinery and man power required for the project Rawanduz Town Fully completed and handed over to the concerned authority for operation of the system. Sidakan Town Fully completed and handing over is under progress. |  | 100 |
| Training | The training programme was conducted between 14 to 19th December 2008. | % of planned | 100 |

# Qualitative achievements against objectives and results

The implementation of the originally planned as well as additional works on the network was completed. A fence (wall) was constructed around the water source to protect the water from pollution. The implemented pipeline network was tested under pressure as part of commissioning. The procedure was closely supervised by MMPW as well as by UNOPS site engineer, both confirming the successful operation of the system which was subsequently handed over to the concerned water authority for operation. The Phase -2 works of Rawanduz and Sidakan towns were handed over to concerned water authorities on 13th May 2009 and 7th July 2009 respectively.

Main implementation constrains & challenges (2-3 sentences)

To ensure a smooth implementation of the additional works, technical meetings were continuously conducted with Erbil water directorate. However, due to the delay of the water the authority with providing necessary drawings, the award of contract for additional works had to wait, in turn resulting in the postponement of implementation.