# United Nations Development Group Iraq Trust Fund

# Project Number: E3 – 12-a

# Updated: 1st Quarter 2008/31 March 2008

| Participating UN Organisation: UN Office for Project Services (UNOPS) | Cluster: Cluster E – Infrastructure Rehabilitation |
| --- | --- |
| Govt of Iraq Line Ministry Responsible: Ministry of Municipalities and Public Works (MMPW) |

| Title | Rehabilitation of Water Distribution Systems in Sidakan and Rawanduz |
| --- | --- |
| Location | Towns of Sidakan and Rawanduz, Soran District, Erbil Governorate |
| Project Cost | US$2,496,475 |
| Duration | 10 months |
| Approval Date (SC) | 27 February 2007 | Starting Date | April 2007 | Completion Date | January 2008 (time amended to 30th June 08) |
| Project Description | Extension and rehabilitation of the existing water distribution network and the construction of reinforced concrete water storage tanks. |

# Development Goal and Immediate Objectives

The Development Goal of the project is to contribute towards improvement in the public health of the inhabitants by increasing the availability of safe drinking water. Immediate objectives: To significantly augment the quality and quantity of water supplied to 10,000 consumers in Sidakan town and 20,000 consumers in Rawanduz town by constructing replacement reservoirs and rehabilitating and extending the existing transmission and distribution mains utilising improved pipe materials and jointing techniques to reduce maintenance costs for the life of the new pipe system. To provide a comprehensive purpose-developed training course in water supply network design and management to at least 30 technical staff of the Directorate of Water and Sanitation so as to improve quality and efficiency throughout the whole management cycle (planning, execution, monitoring) for service provision.

# Outputs, Key activities and Procurement

| Outputs | 30,000 consumers will have improved quantity and quality of water available brought about through reduced contamination and a reduction in losses in the pipe distribution system. Short-term employment creation for over 150 personnel’s for construction activity during project implementation. Thirty (30) government employees are able to pass on their knowledge to others and to plan, implement, monitor and manage water supply projects in the urban areas. |
| --- | --- |
| Activities | Install about 9 km and 3 km of water supply mains in Sidikan and Rawanduz towns respectively; Construction of one (1) collection tank of capacity 8m3 in Rawanduz and two (2) collection tanks of 12 m3 each in Sidakan towns in addition to one service reservoirs of 750 m3 in Sidakan town to improve the supply and to reduce contamination in stored water. Hire and deploy an estimated 150 skilled and unskilled labourers from vulnerable groups, for the 9 month project duration; Deliver a purpose-designed training course of six-day duration to 30 technical personnel from the MMPW on current design concepts for new or expanded networks; use of new materials and techniques to develop, rehabilitate, operate and maintain water distribution networks; |
| Procurement (major items) and on site activities | The project has been awarded to M/s Galaiwa Contracting Company for implementation of the project. Mobilization of material, man power and equipments has started. The procurement of the High Density Polyethylene pipes (HDPE) is in progress at the Turkish-Iraqi borders in addition to the entire related PE fittings. Excavation works for the water pipelines path in both sites (Rawanduz and Sidikan) were concluded waiting for the arrival of pipes. Site preparation for the Sidikan 750 m3 water tank is in process. Site preparation for the Sidikan 48 m3 and 8 m3 storage tank was completed. |

# Situation as of 31/03/2008

| Funds Committed | 1,355,871 | % of approved | 54.3 |
| --- | --- | --- | --- |
| Funds Disbursed | 431,940.70 | % of approved | 31.85 |
| Forecast final date | June 2008 | Delay (months) | 6 months |

# Quantitative achievements against objectives and results

| Site preparations and contact awarding for civil work | Survey, design and document the civil works with full specifications was finalized. A contractor to install and rehabilitate the water mains and construct the water tanks for both sites was chosen and awarded to. Mobilization of Material, man power and equipment was fully completed. | % of planned | 100 |  |
| --- | --- | --- | --- | --- |
| Procurement of Pipes and fitting | Procured 70% of High Density Polyethylene pipes (HDPE) and related PE fittings. All pipes and fitting where strictly cross checked against the ISO 9001 certification from the International Organization for Standardization and were approved | % of planned | 70 |  |
| Civil work and rehabilitation | Rawanduz Town Excavation work for the trenches of 160 mm pipes – 4000 m completed Laying of pipeline completed – 800 m R.C. water tank (8M3) at source – Plastering of inside and outside walls completed. Shuttering to cast the top slab has started. Construction of concrete block channel of 200 X 200 X 400 mm size – Entire stretch of 800 m completed. Sidakan Town Excavation work for the trenches of 160 mm pipes – 9000 m completed. Laying of pipeline completed – 1500m Concrete ground water tank (750 M3) – Foundation completed and shuttering for walls started. Concrete ground water tank (48M3) - Foundation completed and shuttering for walls started. | % of planned | 30 |  |
| Training | The training will be conducted in May 08 and the 30 technical personnel from the Ministry of Municipalities and Public Works, Directorate of Water and Sanitation will be invited. Bidding process for selecting appropriate training centres started and will be finalized in January 08 . | % of planned | 10 |  |

# Qualitative achievements against objectives and results

Several technical meetings were conducted in Erbil water directorate to set the plans for a smooth implementation process. The Procurement component of the project is progressing as scheduled while the implementation part is behind schedule due to heavy snow fall in the site. UNOPS staff are meeting regularly with all stakeholders to ensure smooth coordination, monitoring and evaluation of the implementation of the project activities. The implementation of the project got delayed due to delay in handing over the project site.