# United Nations Development Group Iraq Trust Fund

# Project: 55586 (E3 – 12-a)

# Date and Quarter Updated: 15 October 2008, 3rd Quarter – July to Sept 2008

| Participating UN Organisation: UN Office for Project Services (UNOPS) | Sector: Cluster E – Infrastructure Rehabilitation (WATSAN) |
| --- | --- |
| Govt of Iraq - Responsible Line Ministry: Ministry of Municipalities and Public Works (MMPW) |

# Programme/Project Number: E3 – 12-a

| Title | Rehabilitation of Water Distribution Systems in Sidakan and Rawanduz |
| --- | --- |
| Geographical Location | Towns of Sidakan and Rawanduz, Soran District, Erbil Governorate |
| Project Cost | US$2,496,475 |
| Duration | 10 months originally, extended up to 21 months |
| Approval Date (SC) | 27 February 2007 | Starting Date | April 2007 | Completion Date | January 2008 –Original Extended up to 31st December 08 |
| Project Description | Extension and rehabilitation of the existing water distribution network and the construction of reinforced concrete water storage tanks. |

# Development Goal and Immediate Objectives

The Development Goal of the project is to contribute towards improvement in the public health of the inhabitants by increasing the availability of safe drinking water. Immediate objectives: To significantly augment the quality and quantity of water supplied to 10,000 consumers in Sidakan town and 20,000 consumers in Rawanduz town by constructing replacement reservoirs and rehabilitating and extending the existing transmission and distribution mains utilising improved pipe materials and jointing techniques to reduce maintenance costs for the life of the new pipe system. To provide a comprehensive purpose-developed training course in water supply network design and management to at least 30 technical staff of the Directorate of Water and Sanitation so as to improve quality and efficiency throughout the whole management cycle (planning, execution, monitoring) for service provision.

# Outputs, Key activities and Procurement

| Outputs | 30,000 consumers will have improved quantity and quality of water available brought about through reduced contamination and a reduction in losses in the pipe distribution system. Short-term employment creation for over 150 personnel for construction activity during project implementation. Thirty (30) government employees are able to pass on their knowledge to others and to plan, implement, monitor and manage water supply projects in the urban areas. |
| --- | --- |
| Activities | Install about 9 km and 3 km of water supply mains in Sidikan and Rawanduz towns respectively; Construction of one (1) collection tank of capacity 8m3 in Rawanduz and two (2) collection tanks of 12 m3 each in Sidakan towns in addition to one service reservoirs of 750 m3 in Sidakan town to improve the supply and to reduce contamination in stored water. Install about 11 km and 5 km of water supply mains in Sidikan and Rawanduz towns respectively; Construction of fence (compound wall) around the Sidakan water source to protect from pollution. Hire and deploy an estimated 150 skilled and unskilled labourers from vulnerable groups, for the 9 month project duration; Deliver a purpose-designed training course of six-day duration to 30 technical personnel from the MMPW on current design concepts for new or expanded networks; use of new materials and techniques to develop, rehabilitate, operate and maintain water distribution networks; |
| Procurement (major items) and on site activities | The project has been awarded to M/s Galaiwa Contracting Company for implementation of the project. Mobilization of material, man power and equipment has started. The procurement and implementation of all the assigned High Density Polyethylene pipes (HDPE) in addition to the entire related PE fittings was conducted and the network was implemented and tested. Completed the implementation of the works as planned originally (the details of the works are given in item 1. of Activities, mentioned above) and handed over to the water authority. The contract to implement the additional works (approval was received in May 2008) was awarded to M/s Galaiwa Contracting Company. Procurement of material for additional (the details of the works are given in item 2. of Activities, mentioned above) works is under progress. |

# Situation as of 30/09/2008

| Funds Committed | 2,060,360 | % of approved | 82.53 |
| --- | --- | --- | --- |
| Funds Disbursed | 995,379 | % of approved | 39.87 |
| Forecast final date | December 2008 | Delay (months) | 12 months |

# Quantitative achievements against objectives and results

| Site preparations and contract awarding for civil work | Survey and design document of the civil works with full specifications was finalized. A contractor to install and rehabilitate the water mains and construct the water tanks for both sites was chosen and awarded. Mobilization of material, manpower and equipment was fully completed. | % of planned | 100 |
| --- | --- | --- | --- |
| Procurement of pipes and fitting | For originally planned works Procured 100% of High Density Polyethylene pipes (HDPE) and related PE fittings. All pipes and fitting were strictly crosschecked against the ISO 9001 certification from the International Organization for Standardization and were approved. | % of planned | 100 |
|  | For Additional works Procurement of High Density Polyethylene pipes (HDPE) and related PE fittings are under progress. All pipes and fitting will be as per ISO 9001 certification from the International Organization for Standardization. |  | 10 |
| Civil work and rehabilitation | For originally planned works Completed and handed over to the water authorities. | % of planned | 100 |
|  | For Additional works Mobilization is under progress |  | 10 |
| Training | The training will be conducted in December 08 for the 30 technical personnel from the Ministry of Municipalities and Public Works, Directorate of Water and Sanitation will be invited. Bidding process for selecting appropriate training centres was completed and he contract awarded to M/s Engicon. | % of planned | 40 |

# Qualitative achievements against objectives and results

The implementations of the originally planned activities were completed and handed over to the concerned water authority for operation of the system. Technical meetings are conducted in Erbil water directorate to set the plans for a smooth implementation process of the additional works to be implemented. The award of contract for additional works was delayed due to the delay of the water authority with providing drawings. This in turn resulted in the delay of the project implementation. The contract was awarded to M/s Galaiwa Contracting Company in September 2008 to implement the additional works. UNOPS staff is meeting regularly with all stakeholders to ensure smooth coordination, monitoring and evaluation of the implementation of the project activities.