# United Nations Development Group Iraq Trust Fund

# Project Number: E3-15

# Updated: 1st Quarter 2008/31 March 2008

| Participating UN Organisation: UNDP | Cluster: E – Infrastructure Rehabilitation |
| --- | --- |
| Govt of Iraq Line Ministry Responsible: Ministry of Municipalities and Public Works Directorate of Municipalities-Basra Governorate; Municipality of Abu Al Khaseeb |
| Title | Emergency Water Supply and Sanitation for Abu Al-Khaseeb |
| Location | Abu Al-Khaseeb, Basrah Governorate |
| Project Cost | US$ 1,983,268 |
| Duration | 9 months |
| Approval Date (SC) | 4 Oct 2007 | Starting Date | Nov 2007 | Planned Completion Date | Aug 2008 |
| Project Description | Provision of water and sanitation supplies, works and services for the city of Abu Al-Khaseeb |

# Development Goal and Immediate Objectives

The development goal for this project is aligned with the targets of Iraq’s National Development Strategy (2005): “To increase access to: potable water by 10% and access to improved sanitation by 5% by the end of 2007”. Immediate Objective 1: To contribute towards the restoration of the potable water production and consumption, and wastewater services levels to pre-1991 levels. Immediate Objective 2: To develop Counterpart’s WATSAN sector manpower capacity related to operation and maintenance of assets and project implementation related fields. Immediate Objective 3: To contribute towards creation of employment opportunities for the poor and vulnerable segments of the population and maximizing utilization of locally available resources.

# Outputs, Key activities and Procurement

| Outputs | 1.1 Constructed water supply infrastructure (Reverse Osmosis Plant) will supply safe potable water to the project area inhabitants, thereby improving the socio-economic and health conditions for some 30,000 capita. 1.2 Water delivery facilities (water transportation) will ensure access to the improved safe potable water supply services to a fraction of the population (i.e. fraction of 150,000 capita). 1.3 Sewage de-sludging facilities and solid wastes removal activities will ensure access to improved sewage and solid wastes removal services and, as such, enhanced environmental, living, health…etc conditions to a fraction of the population (i.e. fraction of 150,000 capita). 2.1 (Reverse Osmosis) RO plant operators and managers, water delivery facilities and de-sludging trucks operators are capable of carrying out all plant required O&M procedures in a timely and technically appropriate manner. 2.2 For plant, facilities and other equipment, operation, preventive and corrective maintenance are carried out appropriately and in a timely manner. 2.3 Counterparts capacitated to carry out all/most project implementation related activities and are thus capable of implementing projects. 3.1 Temporary employment opportunities totaling some 21,250 man-days to unskilled and semi skilled vulnerable and unemployed people, including women, will be created. In addition, longer-term employment opportunities will also be created during the project operation and maintenance phase. 3.2 Community provides security mechanisms for securing and protecting the provided assets against looting and/or damage and ensuring proper, adequate and timely O&M practices are exercised to sustain such. 3.3 Economic improvements by decreasing dependence on imports. |
| --- | --- |
| Activities | 1.1.1 Supply of one (1) RO unit of 50 cubic meters per hour capacity complete including water filling equipment, consumables, spare parts and chemicals. 1.1.2 Supply of one (1) water storage tank including jerry cans water filling facility, fixtures…etc. 1.1.3 Supply of stand-by power diesel generation set for RO plant. 1.1.4 Supply of electrical power transformer set for RO plant. 1.1.5 Construction of all civil works and installation, erection, assembly, etc. of all RO plant associated equipment and works including excavation and equipping of groundwater wells, RO unit, disinfections unit, jerry cans filling facility, gen-set, and ancillary equipment, piping, instruments, power and control cables, warehouse…etc. 1.2.1 Supply of two (2) water delivery trucks and all required spare parts. 1.3.1 Supply of one (1) sewage tanker and all required spare parts. 1.3.2 Within the framework of the employment creation activity, solid wastes will be cleared from city streets, blocked storm water sewers will be cleared, etc. 2.1.1 Delivery of a comprehensive training programme for Operation and Maintenance (O&M) of RO plant and associated equipment including plant optimization. 2.1.2 Delivery of a comprehensive training programme for O&M of the supplied mobile equipment. 2.2.1 Supply of spare parts, chemicals and consumables for the RO plant for one (1) years of operation. 2.2.2 Supply of spare parts for the supplied water and sewage tankers for one (1) year of operation. 2.3.1 Through the potential engagement with counterparts in a Letter of Agreement (LoA) form for implementing part of the project scope as related to installation works and delivery of an on-the-job capacity. 3.1.1 Implementing of labour intensive, IREP activities in relation to solid wastes collection, storm water networks clearing and similar activities. 3.1.2 Employing a local contractor who employs local labour for project components implementation. 3.1.3 Town council employs local manpower for facilities’ O&M. 3.2.1 Employment of local workers in all construction and O&M activities. 3.3.1 Maximizing locally available resources such as employment of local manpower, use of locally available construction materials (cement, bricks, etc.), procurement of locally manufactured goods (distribution point tanks, etc.). |
| Procurement (major items) | Reverse Osmosis Units Consultancy Services for installation |

# Situation as of 31/3/2008

| Funds Committed | US$ 1,983,268 | % of approved | 36 |
| --- | --- | --- | --- |
| Funds Disbursed | US$ 16,024 | % of approved | 5 |
| Forecast final date | September 2008 | Delay (months) | 1 |

# Quantitative achievements against objectives and results

| Spare parts and equipment | The RO unit being sourced. | % of planned | 50 |
| --- | --- | --- | --- |
| Drawings, manuals and test certificates | Consultancy services being sourced | % of planned | 80 |
| Training | and labor-intensive project | % of planned | 0 |

# Qualitative achievements against objectives and results

Project Kick-off meeting with Qaem Makam of Abu Al-Khaseeb Qadaa and the Town council chairman held 18-20 November 2007. During the meeting, all project related matters were discussed and agreed Project consultancy services contract awarded. Project coordination meeting held on 28 January 2008. Award of the supply contract for the RO plant equipment Receipt and evaluation of proposals for labor intensive water projects to be carried out in the project area. Completion of the Final Evaluation of the supply of water and sewage tankers (Technical and Financial).