Sixth Six-month progress report for project

# REPORT COVER PAGE

| Participating UN Organisation: |  | Cluster: |
| --- | --- | --- |
| United Nations Development Programme |  | E – Infrastructure Rehabilitation (E4-07) |

| Project No. and Project Title: |  | Project Location/Region/Province: |
| --- | --- | --- |
| Project No. 00038901 E4-07 Rehabilitation of Unit Nos. 2 & 4 at Al Mosul Gas Power station |  | Mosul, Ninewa Governorate |

| Reporting Period: |  | Report no: |
| --- | --- | --- |
| 1 January 2007 to 30 June 2007. |  | 6 for IRRFI projects 5 for this project |

| Counterpart organisations / implementing partners: |  | Project cost: |
| --- | --- | --- |
| UNDP/Ministry of Electricity |  | US$ 17,585,450 |

| Abbreviations and acronyms: |  | Project Duration: |
| --- | --- | --- |
| MoE - (Ministry of Electricity) HTC – (Hitachi Limited, Japan) AVT – (Audio Video Teleconferencing system) |  | Up to 21 Months from late May 2005. |

# NARRATIVE REPORT FORMAT

# Purpose

  - Provide the main objectives, outcomes, outputs of the programme/project

Objectives:

1. The generating capacity, availability and reliability of Taji Gas Power Station (Units Nos. 1, 4 & 6) is increased.

2. The plant management and staff are able to operate and maintain the units in accordance with international standards.

Outputs:

1. Gas units 1, 4 & 6 at Taji GPS rehabilitated with increased operational reliability.

2. Set of selected essential spare parts supplied to Taji GPS, which will be available in stock for emergency repairs and routine maintenance, in order to improve the reliability of generation.

3. A substantial number of Plant engineers trained, who will be able to operate and maintain the power plant at higher levels of performance and who also in turn would be able to train other junior technical personnel (engineers and technicians).

  - Explain how the programme/project is relevant to the following benchmarks:

- UN Assistance Strategy for Iraq,

- UN Millennium Development Goals,

- Joint Needs Assessment ,

- Iraqi National Development Strategy

The project is in line with UNDG’s Development Strategy, providing a reliable and efficiently run power system. The project complies with two of the strategy objectives, namely to improve generating capacity and to maximise training of MoE staff in the sector.

The relevant excerpt from the 2006-2007 UN Assistance strategy for Iraq is as follows:

UNCT Goal 2: Assist in the provision of basic services and promotion of community development and participation:

Cluster Outcome 2.6: Rehabilitation and governance of infrastructure at local level.

E3: Increased availability of electricity, particularly to rural and low income areas.

Programme outputs:

-Generation capacity enhanced.

-Technical and management capacity enhanced

  - Indicate the main implementing partners, their roles and responsibilities, and their interaction with the Agency

The project will be implemented through the engagement of Hitachi Ltd as international partner and the Ministry of Electricity (MoE) as national partner. The project was signed on a turn-key basis with Hitachi Ltd (HTC). Project supervision and technical management will be performed by HTC. Implementation of site works will be carried out by a local (Iraqi) subcontractor hired by Hitachi. Overall project liaison with Ministry of Electricity, and monitoring the pace of project implementation, will remain in the hands of UNDP. Monitoring of the site works will be carried out by UNDP’s local consultant, supported by MoE site personnel.

- Resources

Financial Resources:

  - Provide total funds provided, disbursed and committed

See separate detailed financial report.

  - Highlight any variation(s) in projected versus actual spending for the reporting period indicating the reason for such variation(s).

N/A

  - Explain programme/project expenditures within the 10 budget categories, including security expenditures.

See separate detailed financial report.

  - Indicate other funding sources, if applicable.

N/A

  - Provide details on any budget revisions approved by the UNDG ITF Steering Committee, if applicable

The scope of rehabilitation has been broken-down into phases to be addressed separately as submitted to the steering committee.

  - Project expenditures for the 1 July to 31 December 2007 period.

N/A

Human Resources:

  - National Staff: Provide details on the number and type (operation/programme)

None at this stage.

  - International Staff: Provide details on the number and type (operation/programme)

One (1) shared with Taji GPS rehabilitation projects.

- Methods of Operating

  - Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

Due to the prevailing security situation and restrictions placed on the movement of UN staff over the majority of Iraq, in addition to the unique security conditions in Mossul, local contractors and team of engineers and architects were chosen to implement the project.

  - Provide details on the procurement procedures utilized and explain variances in standard procedures.

Procurement is made through competitive process by the experienced UNDP -Iraq procurement office which demonstrated that performance over the last few years is a major asset on which this project has already built and from which it benefited. In case too few competitors respond or are eligible for the task at hand, waiver is sought to contract directly.

  - Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

Implementation is ongoing and works are monitored regularly. This ensures that the sub-contractors for various technical works (electrical, plumbing, carpentry, masonry, etc.) comply with the Bill of Quantities of the projects.

In addition, UNDP’s technical team are fully engaged in advising and guiding the contractors throughout the implementation phase. The implementing agents are paid by UNDP in arrears based on predetermined milestones, which are independently verified by UNDP’s Consultant upon receipt of payment request invoices from the contractor. Payments are subject to the progress of works and the submission of all supporting documentation by the contractor including monthly progress reports, before, during and after photographs of the works, etc.

  - Report on any assessments, evaluations or studies undertaken.

N/A

- Results

  - Provide a summary of programme/project progress in relation to planned outcomes and outputs; explain any variance in achieved versus planned outputs during the six month reporting period.

So far the project remains on schedule.

As far as rehabilitation of Unit No. 4 is concerned, it remained on schedule throughout.

Works on unit number 2 have started on time, but the security situation is deteriorating and an overall delay in completion of the project of approximately 2 months is therefore expected. Unit No. 2 has also been energized during the period under review.

  - Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period.

As detailed in the following section, several financial obligations have been released, paving the way towards financial closure.

  - Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries.

Activities between 01.01.2007 to 30.06.2007

Unit No. 4

- Punch list items have been cleared.

- The unit had developed some problems while in operation, which have been addressed. The unit is ready for energization, but due to low gas pressure this energization was not possible.

- During a video conference, Mosul alerted of the need of a new generator rotor, as the one in use has developed some serious defect. A list of consumables has also been  provided.

Unit No. 2

- Re-assembly of the unit was completed.

- Pre-commissioning tests were completed.

- Unit was run for 72 hours for reliability test.

- Finally the unit was energized and is running.

- Management of Mosul had indicated some defects which have been addressed. Since the unit is still under warranty period, the defect liability rests with Hitachi for the contractual portion of the work.

- A substantial completion certificate was issued after energizing the unit. Payment has been released for issuance of certificate of substantial completion.

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints, lessons learned in the process and actions taken to mitigate future delays.

Geographical isolation, coupled with difficult security conditions, make communication and planning on this complex project extremely difficult. HTC have employed both a local consultant and contractor in Iraq and have opened a representative office in Amman. UNDP-Iraq is in the advance stage of employing a local consultant for liaison, monitoring and verification purposes on site.

UNDP-Iraq has been successful in facilitating communication between HTC and the Iraqi MoE. UNDP-Iraq frequently convenes meetings and bi/tripartite discussions (sometimes by means of satellite audio visual equipment). Communication via reliable VSAT equipment is imperative and should have been installed earlier on in this project.

The deteriorating security situation has become a serious hurdle for the implementation of the project.  The original implementation modalities, which were planned during the preparation stage of the project in the latter part of 2003, are no longer valid under the current situation. New implementation modalities are being reviewed in on-going discussions where MoE engineers will play a larger role in the installation works.

  - List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

As a consequence of the restrictions placed on the movement of UN staff in Iraq, UNDP Iraq sought other ways to overcome the situation on the ground in order to reach the target populations of its interventions. Hence, a strong partnership was developed with line ministries and station management. This arrangement allowed UNDP to assess the local institutions’ capacities for project implementation as well as to support its counterparts in identifying their major priorities.

These de-facto partnerships with beneficiaries and contractors are flexible and efficient operational modalities in Iraq’s difficult conflict environment.

Close collaboration with beneficiaries and contractor allowed for a revised implementation strategy to take account of the concerns of all, adapting optimally to the security situation, the bottlenecks of world markets and the beneficiaries limited room for shutting down the power station.

Key Partnerships:   MoE, GDEP and HTC

Inter-Agency Collaboration: Limited inter-agency collaboration due to the very specialized nature of the works

  - Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

So far the cooperation extended by MoE / Station staff is exemplary. The workers of the contractor are also displaying a sense of great responsibility under the critical security situation. Thereby a good deal of learning by doing is achieved.

- Future Work Plan

  - Summarize the projected activities up to the end of June 2007.

Final report and financial closure.