# United Nations Development Group Iraq Trust Fund

# Project #: E4-07

# Date and Quarter Updated: 1 October-31 December- 4th Quarter 2008

| Participating UN Organisation: UNDP | Cluster: E – Infrastructure Rehabilitation |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Electricity |

| Title | Rehabilitation of Mosul Gas Power Station |
| --- | --- |
| Location | Ninewa Governorate, Mosul |
| Project Cost | US$ 17,585,450 |
| Duration | 24 months (extension till 31 Dec 2008) |
| Approval Date (SC) | 22.07.2004 | Starting Date | 16 August 2004 | Completion Date | 16 April 2006 (original date) |
| Project Description | Mosul GPS consists of 12 x 20 MW gas turbine units, out of which four are of Hitachi manufacture. The technical rehabilitation of existing 2 x 20 MW units No. 2 and 4 will complete the refurbishment of the entire Hitachi Plant as the replacement of the other 2 existing units No. 1 and 3 will be carried out under a separate bilaterally funded project. Implementation of this rehabilitation project will result in reinstatement of the design capacity of the two units, significant extension of their operational life span and will restore the overall output of the plant by 30 MW. After completion of the rehabilitation works, the power station will be able to generate more reliable electric power. This project will contribute to the decrease of load shedding and blackouts and permit more reliable supply of electricity to Iraqi people especially for the residents of the city of Mosul and surrounding areas. |

# Development Goal and Immediate Objectives

1. To respond to the immediate humanitarian needs of the war-affected Iraqi people by ensuring the supply of reliable and safe electricity to permit operation of essential humanitarian services including water supply, hospitals, schools, sewage treatment plants and other community services. 2. The generating capacity, availability and reliability of Mosul Gas Power Station (Turbine Units No.2 and 4) restored. 3. Plant personnel trained in accordance with international standards.

# Outputs, Key activities and Procurement

| Outputs | 1.1 Units 2 and 4 at Mosul Gas Power Station rehabilitated with increased operational reliability. 2.1 Set of selected, essential spare parts supplied to Mosul Gas Power Station for emergency repairs and routine maintenance, in order to sustain the increased generation. 3.1 A substantial number of trained plant engineers, who will be able to operate and maintain the power plant for higher levels of performance and also in turn would be able to train other junior technical personnel (engineers and technicians). |
| --- | --- |
| Activities | 1.1.1 Implementation of scheduled rehabilitation works of Turbine Units No. 2 and 4. 2.1.1 Provision of specified spare parts and relevant rectification of selected components coming from disassembled units. 3.1.1 Implementation of the relevant training process carried out both at site and at the manufacturer’s workshop. |
| Procurement (major items) | Major essential spare parts required for rehabilitation of gas turbine generator, control and rotor. |

| Funds Committed | USD 17,391,861 | % of approved | 98.90% |
| --- | --- | --- | --- |
| Funds Disbursed | USD 17,390,521 | % of approved | 98.89% |
| Forecast final date | November 2008 Operationally Closed | Delay (months) | 31 |

# Quantitative achievements against objectives and results

| Spare parts and equipment | All the initial planned equipment arrived at site as per schedule | % of planned | 100% |
| --- | --- | --- | --- |
| Drawings, manuals and test certificates | All drawings, adjustments and test certificates issued | % of planned | 100% |
| Training of Trainers | Nine Mosul site engineers have undergone extensive training at the manufacturer’s facility in Japan | % of planned | 100% |
| Pre-shipment inspection | Coordination and supervision of factory-witness tests in Japan of selected equipment successfully completed during March – April 06 | % of planned | 100% |

# Qualitative achievements against objectives and results

Rehabilitations of Turbines Unit No. 2 and 4 were completed and Units commissioned according to new schedules; Delayed procurement of additional spare parts initiated in August 2007 with expected delivery in October / November has contributed towards overall delays; The contract work was completed with minimum delay even with deterioration in the security situation; The rotor for Turbine Unit 4 was shipped to Hitachi Japan in order to reap optimal benefits of the rehabilitation in October and returned in December 2008; Post commissioning monitoring is ongoing on Units 2 and 4 until March 2009; Final report in draft; All spare parts and 104 tons of equipment have arrived at the site for emergency repairs and routine maintenance, in order to sustain the increased power generation; 9 Mosul site engineers have undergone extensive training at the manufacturer’s facility in Japan; 1 technical adviser (Iraqi) was trained in Japan by Hitachi for rehabilitation/commissioning works; 50 unskilled/semi skilled workers were provided on the job training; 3 engineers were trained in Amman on commissioning of Units; 40-50 persons were provided employment during rehabilitation commissioning works; Regular post commissioning monitoring indicates Units 2 and 4 operating satisfactorily. Both are capable of generating 19 MW each, but at present the output is limited to 15 MW each due to low gas pressure and aging of the parts, not included in rehabilitation works; Project operationally closed in December 2008.