# United Nations Development Group Iraq Trust Fund

# Project #: E4-07

# Date and Quarter Updated: 1 July 2008 - Q2 2008

| Participating UN Organisation: UNDP | Cluster: E – Infrastructure Rehabilitation |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Electricity |

| Title | Rehabilitation of Mosul Gas Power Station |
| --- | --- |
| Location | Mossul, Ninewa Governorate |
| Project Cost | US$ 17,585,450 |
| Duration | 20 months |
| Approval Date (SC) | 22.07.2004 | Starting Date | August 2004 | Completion Date | March 2006 (ext 31 Dec 2008) |
| Project Description | Mosul GPS consists of 12 x 20 MW gas turbine units, out of which 4 are of Hitachi manufacture. The technical rehabilitation of existing 2 x 20 MW units No. 2 and 4 will complete the comprehensive refurbishment of the entire Hitachi Plant as the replacement of the other 2 existing units No. 1 and 3 will be carried out under a separate bilaterally funded project. Implementation of this rehabilitation project will result in reinstatement of the design capacity of the 2 units, significant extension of their operational life span and will increase the overall output of the plant by 30 MW. After completion of the rehabilitation works, the power station will be able to generate more reliable electric power. This project will contribute to the decrease of load shedding and blackouts and permit more reliable supply of electricity to Iraqi people especially for the residents of the city of Mosul and surrounding areas. |

# Development Goal and Immediate Objectives

1 To respond to the immediate humanitarian needs of the war-affected Iraqi people by ensuring the supply of reliable and safe electricity to permit operation of essential humanitarian services such as water supply, hospitals, schools, sewage treatment plants and other community services. 2 The generating capacity, availability and reliability of Mosul Gas Power Station (Units No.2 and 4) increased. 3 Plant personnel trained in accordance with international standards.

# Outputs, Key activities and Procurement

| Outputs | 1.1 Units 2 and 4 at Mosul Gas Power Station rehabilitated with increased operational reliability. 2.1 Set of selected, essential spare parts supplied to Mosul Gas Power Station for emergency repairs and routine maintenance, in order to sustain the increased generation. 3.1 A substantial number of trained plant engineers, who will be able to operate and maintain the power plant for higher levels of performance and also in turn would be able to train other junior technical personnel (engineers and technicians). |
| --- | --- |
| Activities | 1.1.1 Implementation of scheduled rehabilitation works to both units No. 2 and 4. 2.1.1 Provision of the set of specified spare parts and relevant rectification of selected components coming from the all disassembled units. 3.1.1 Implementation of the relevant training process carried out both at site and at the manufacturer’s workshop. |
| Procurement (major items) | Generator Rotor |

| Funds Committed | USD 17,421,791 | % of approved | 99.07% |
| --- | --- | --- | --- |
| Funds Disbursed | USD 16,641,710 | % of approved | 94.63% |
| Forecast final date | June 2008 | Delay (months) | 25 |

# Quantitative achievements against objectives and results

| Spare parts and equipment | All the equipment arrived at site as per schedule | % of planned | 100% |
| --- | --- | --- | --- |
| Drawings, manuals and test certificates |  | % of planned | 100% |
| Training of Trainers | 9 Mosul site engineers have undergone extensive training at the manufacturer’s facility in Japan | % of planned | 100% |
| Pre-shipment inspection | Coordination and supervision of factory-witness tests in Japan of selected equipment successfully completed during March – April 06 | % of planned | 100% |

# Qualitative achievements against objectives and results

Rehabilitations of Unit No. 2 and 4 were completed as scheduled and units were commissioned. Additional works have been arranged for the rotor of Unit 4 in order to reap optimal benefits of the rehabilitation. Post commissioning monitoring of the units’ continues: unit 2 and 4 are currently operating stably at 15MW below the potential 18MW due to weak gas pressure. All the spare parts and equipment arrived at the site for emergency repairs and routine maintenance, in order to sustain the increased generation. 9 Mosul site engineers have undergone extensive training at the manufacturer’s facility in Japan.