# United Nations Development Group Iraq Trust Fund

# Project #: E4-08

# December 2007/4th Quarter 2007

# Project Summary Sheet

| Participating UN Organisation: UNDP | Cluster: E – Infrastructure Rehabilitation |
| --- | --- |
| Govt of Iraq Line Ministry Responsible: Ministry of Electricity |

| Title | Rehabilitation of Taji Gas Power Station |
| --- | --- |
| Location | Taji, Baghdad Governorate |
| Project Cost | US$ 25,891,860 |
| Duration | 22 months (as in project document) (project extended until 30 June 2008) |
| Approval Date (SC) | 22 July 2004 | Starting Date | November 2004 | Completion Date | 30 June 2008 |
| Project Description | The technical rehabilitation of existing 3 x 20 MW units No. 4, 6 and 7 will complete the comprehensive refurbishment of the entire Plant as the replacement of the other 4 existing units No.1, 2, 3 and 5 will be carried out under a separate bilaterally funded Project. Implementation of the Project will result in reinstatement of their design capacity, significant extension of the operational life span of existing units and will increase the overall output of the Plant by 50 MW. |

# Development Goal and Immediate Objectives

To respond to the immediate humanitarian needs of the war-affected Iraqi people by ensuring the supply of reliable and safe electricity to permit operation of essential humanitarian services such as water supply, hospitals, schools, sewage treatment plants and other community services. Immediate Objectives 1. The generating capacity, availability and reliability of Taji Gas Power Station (Units No.4, 6 and 7) increased. 2. The plant management and staff able to operate and maintain the units in accordance with international standards

# Outputs, Key activities and Procurement

| Outputs | 1. Gas units 4; 6 and 7 at Taji GPS rehabilitated with increased operational reliability. 2. Set of selected, essential spare parts supplied to Taji GPS, which will be available in stock for emergency repairs and routine maintenance - in order to improve the reliability of generation. 3. Trained a substantial number of Plant engineers, who will be able to operate and maintain the power plant for higher levels of performance and also in turn would be able to train other junior technical personnel (engineers and technicians). |
| --- | --- |
| Activities | 1. Implementation of scheduled rehabilitation works to all 3 units (No. 4, 6 and 7). 2.Provision of the set of specified spare parts and relevant rectification of selected components coming from the all disassembled units. 3. Implementation of the relevant training process carried out both at site and at the Manufacturer’s workshop. |
| Procurement (major items) | Generator rotor Generator rotor bearings |

# Situation as of 31/12/2007

| Funds Committed | USD 25,433,474 | % of approved | 98.23% |
| --- | --- | --- | --- |
| Funds Disbursed | USD 24,176,207 | % of approved | 93% |
| Forecast final date | June 2008 | Delay (months) | 21 months |

# Quantitative achievements against objectives and results

| Spare parts and equipment | All the shipments of material have been delivered at site within schedule and are stored | % of planned | 100% |
| --- | --- | --- | --- |
| Drawings, manuals and test certificates | Drawings and manuals delivered, Certificate of Substantial Completion signed. | % of planned | 100% |
| Training of Trainers | 12 Taji site engineers have received extensive training at the manufacturer’s facility in Japan. | % of planned | 100% |
| Pre-shipment inspection. | Coordination and supervision of factory-witness tests in Japan of selected equipment successfully completed during March – April 06. | % of planned | 100% |

# Qualitative achievements against objectives and results

Rehabilitation of all Units 1, 4 & 6 has been completed, including performance tests. Unit 1 energized on liquid fuel. Energizing explored for Units 4 & 6.