8th  Six-month progress report for project

# REPORT COVER PAGE

| Participating UN Organization: |  | Cluster: |
| --- | --- | --- |
| United Nations Development Programme |  | E – Infrastructure Rehabilitation (E4-08) |

| Project No. and Project Title: |  | Report Number: |
| --- | --- | --- |
| E4-08 - 00038906 Rehabilitation of Unit Nos. 1, 4 and 6 at Taji Gas Power Station |  | 8 for UNDG-ITF 7 for this project |

| Reporting Period: |  | Project Budget: |
| --- | --- | --- |
| 1 January to 30 June 2008 |  | US$ 25,891,860 |

| List Implementing Partners: |  | Project Coverage/Scope: |
| --- | --- | --- |
| UNDP/Ministry of Electricity |  | Taji / Baghdad Governorate |

| Abbreviations and acronyms: |  | Project Duration/Closed Project: |
| --- | --- | --- |
| ME (Ministry of Electricity) HTC - (Hitachi Limited, Japan) AVT – (Audio Video Teleconferencing system) |  | 22 Months from end of August 2004 Extension request until November 2008 granted in April 2008 |

# NARRATIVE REPORT FORMAT

# Purpose

  - Provide the main objectives, outcomes, outputs of the programme/project

Objectives:

1. The generating capacity, availability and reliability of Taji Gas Power Station (Units Nos. 1, 4 & 6) increased.

2. The plant management and staff able to operate and maintain the units in accordance with international standards.

Outputs:

1. Gas units 1, 4 & 6 at Taji GPS rehabilitated with increased operational reliability.

2. Set of selected essential spare parts supplied to Taji GPS, which will be available in stock for emergency repairs and routine maintenance, in order to improve the reliability of generation.

3. Train a substantial number of Plant engineers, who will be able to operate and maintain the power plant for higher levels of performance and also in turn would be able to train other junior technical personnel (engineers and technicians.)

.

  - Explain how the programme/project is relevant to the following benchmarks:

- UN Assistance Strategy for Iraq,

- UN Millennium Development Goals,

- Joint Needs Assessment ,

- Iraqi National Development Strategy

The project is in line with UNDG’s Development Strategy, providing a reliable and efficiently run power system. The project complies with two of the strategy objectives, namely to improve generating capacity and to maximise training of MoE staff in the sector.

The relevant excerpt from the 2006-2007 UN Assistance strategy for Iraq is as follows:

UNCT Goal 2: Assist in the provision of basic services and promotion of community development and participation:

Cluster Outcome 2.6: Rehabilitation and governance of infrastructure at local level.

E3: Increased availability of electricity, particularly to rural and low income areas.

Programme outputs:

-Generation capacity enhanced.

-Technical and management capacity enhanced

-Power plant equipped with sufficient spare parts and Operation / Maintenance Manuals and drawings for ready reference in efficient operation and maintenance.

  - Indicate the main implementing partners, their roles and responsibilities, and their interaction with the Agency

The project has been implemented through the engagement of Hitachi Ltd as international partner and the Ministry of Electricity (MoE) as national partner. The project was signed on a turn-key basis with Hitachi Ltd (HTC). Project supervision and technical management will be performed by HTC. Implementation of site works will be carried out by a local (Iraqi) subcontractor hired by Hitachi. Overall project liaison, monitoring of the pace of its implementation, with the Ministry of Electricity, will remain in the hands of UNDP. Monitoring of the site works was carried out by way of daily web camera conferences which facility was developed in Hitachi office in Amman, and three party meetings at different intervals in Amman. arranged by UNDP.

- Human Resources

  - National Staff: Provide details on the number and type (operation/programme)

None at this stage.

  - International Staff: Provide details on the number and type (operation/programme)

One (1) shared with Mosul GPS rehabilitation project who is  supervised from Amman Office.

- Methods of Operating

  - Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

Due to the prevailing security situation and restrictions placed on the movement of UN staff over the majority of Iraq, in addition to the unique security conditions in Taji, local contractors and team of engineers were hired by Hitachi to carry out rehabilitation works at site.

8 Engineers were trained in Japan who in turn carried out the plant assessment assignment which helped in quantifying material and services. One Technical adviser (Iraqi) was also trained with the specific duties for supervision at site which lead to successful rehabilitation works. The local workers hired by the sub-contractor were also provided on the job training while at work. Additionally on the request of Manager of Mosul, training on Excitation System was provided in Amman to two engineers.

These trainings have ensured quality rehabilitation works, but they also fostering the readiness of the power station staff for similar rehabilitation and maintenance operations in future.

  - Provide details on the procurement procedures utilized and explain variances in standard procedures.

Procurement is made through competitive process by the experienced UNDP -Iraq procurement office which demonstrated that performance over the last few years is a major asset on which this project has already built and from which it has benefited.

In this case since Hitachi is the Original Equipment supplier, a waiver was sought / approved by CAP and ACP from competitive bidding.

  - Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

When the implementation was on going, works were monitored regularly. A web camera system was installed both in the office of Hitachi in Amman and on the site of work. This facilitated day to day discussion and also the web camera could be directed to the precise point of work for close monitoring. This system was on throughout the working time of the day.  This ensured that the sub-contractors for rehabilitation works (electrical, mechanical, control) comply with the instruction and acceptable procedures of works.

.

In addition, UNDP’s technical team are fully engaged in close monitoring throughout the implementation phase.

The implementing agents are paid by UNDP based on predetermined milestones, which are independently verified by UNDP’s Project Manager upon receipt of payment request invoices from the contractor. Payments are subject to the progress of works and the submission of all supporting documentation by the contractor including monthly progress reports, before, during and after photographs of the works, etc.

On a needs basis, progress of works is also assessed through three partite meetings held in Amman, attended by Hitachi, MoE/Mosul and UNDP.

  - Report on any assessments, evaluations or studies undertaken.

Prior to commencement of works on each indivual unit, as per technical procedure, assessment of performance of the unit was carried out.

- Results

  - Provide a summary of programme/project progress in relation to planned outcomes and outputs; explain any variance in achieved versus planned outputs during the six month reporting period.

The works on Unit No. 4 were completed but the unit could not be energized due to non availability of gas at the station as the gas lines have been severely damaged by sabotage.

Works on unit number 6 were completed under the same day to day threats as indicated above. After completion the unit could not be energized due to non availability of gas at the station.

Works on Unit number 1 were also completed in a similar way to unit number 4 and 6. The MoE had arranged for liquid fuel and requested assistance for converting unit number 1 on liquid fuel. These were additional works, which were completed with the assistance of staff of sub-contractor of Hitachi and the unit was energized on liquid fuel.

  - Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period.

Activities between 01.07.2007 to 31.12.2007

On Units 1, 4 & 6:

- After rehabilitation, all re-assembly works were completed.

- Subsequently all the pre-commissioning tests which were possible without availability of gas were completed but energizing the unit was not possible due to non availability of gas (fuel). After discussions with MoE and Hitachi, a provisional substantial completion certificate was issued and signed by both parties (UNDP and Hitachi) deducting the work portion which related to energizing the unit and which could not be done due to non availability of  gas at the station. The following tests could not be carried out:

  - AVR Dynamic Characteristic and SynchronizationTtest.

  - Load Operation Test (as per contracted scope of work.)

  - Reliability Test (as per contracted scope of work.)

At a later stage, when the works on Unit No.1 were reaching completion, MoE was able to arrange liquid fuel instead of gas. Hitachi / UNDP assisted in the conversion of the unit to burn liquid fuel instead of gas. After carrying out the conversion and performing all required pre-commissioning tests, the unit was energised.

  - Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries.

Works on conversion of Unit No. 1 from gas to liquid fuel were completed and the unit was energized to produce 19 MW.

Since the defect liability period of unit number 4 was over, the matter was discussed with Hitachi and a conditional certificate of final completion has been issued.

Negotiations are on going for conversion of Unit Number 6 on liquid fuel, subject to availability of financial resources.

A camp was established in the Taji GPS compound to overcome the daily problem and risk involved in transporting workers to and from Taji which proved to be an effective solution to complete the work.

Training of Iraqi Engineers in Japan and provision of drawings, operation and maintenance manuals helped in increasing the capability of Iraqi engineers and staff to handle complex maintenance job comparatively smoothly in future with lesser time consumption.

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints, lessons learned in the process and actions taken to mitigate future delays.

Geographical isolation coupled with difficult security conditions make communication and planning on this technically complex project extremely difficult. HTC have employed technically capable local subcontractor in Iraq, provided training to an Iraqi technical advisor for the project, and opened a representative office in Amman. UNDP-Iraq had carried out the supervision and monitoring / project management on regular basis by an International Project Manager / Technical Advisor, located in Amman.

UNDP has facilitated MoE/HTC/UNDP cooperation. UNDP were able to facilitate meetings and conduct both bi and tri party discussions by means of satellite audio visual equipment. In addition installation of web camera and conference facility helped in execution of job.

Throughout its implementation phase, the project remained under security threat. In several occasion, delays were incurred because of the general security situation, unexpected curfew and harm caused to subcontractors’ employees. The most tragic incident occurred on 14 January 2007, approx 15 km from the power plant, 4 subcontractor employees at Taji were kidnapped and murdered. Work was suspended for several weeks and brought about a 2-month delay to substantial completion.

The original implementation modalities, which were planned during the preparation stage of the project in the latter part of 2003, were no longer valid as the security situation evolved. New implementation modalities were adopted, where MoE engineers will play a larger role in overseeing the installation works. All the achievements of milestones were confirmed by the station engineers at different stages.

Establishment of a camp at the work site, with essential facilities and food for the staff, accelerated the speed of work and mitigated the risk of daily transportation of staff to and from the site. This also increased work time per day.

  - List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

As a consequence of the restrictions placed on the movement of UN staff in Iraq, UNDP Iraq sought other ways to overcome the situation on the ground in order to reach the target populations of its interventions. Hence, a strong partnership was developed with line ministries and station management. This arrangement allowed UNDP to assess the local institutions’ capacities for project implementation and to support counterparts in identifying priorities.

These de-facto partnerships with beneficiaries and contractors are a flexible and efficient operational modality in Iraq’s difficult conflict environment.

Key Partnerships:   MoE and HTC

Inter-Agency Collaboration: There was limited inter-agency collaboration due to the very specialized nature of the works.

  - Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

  - During rehabilitation stage, the project provided employment to skilled and

  - Semi skilled workers plus general labourer. Approximately 40 – 50 persons were employed at different stages of works.

  - Created employment opportunities: numerous employment opportunities will be created as a result of restoration of power supply.

  - Direct beneficiaries: About 5 million inhabitants residing in Baghdad and the central region.

Moreover, project implementation will indirectly result in:

- Generating commercial activity and employment opportunities for national contractors

- Creating and sustaining employment opportunities within MoE.

- Enhancing the employment terms, conditions and future opportunities through the capacity building of the relevant MoE staff.

- Future Work Plan

  - Summarize the projected activities up to the end of June 2008

Resolution of day to day operational problems during the rest of the defect liability period.

Finalization of spare part list with quantities for oil firing of Unit No. 6 and necessary conversion works (to be completed by August 2008)

Final report in preparation of financial closure