# United Nations Development Group Iraq Trust Fund

# Project #:E4-14

# Date and Quarter Updated: 31 December 2007/4th Quarter 2007

# Part One: Summary

| Participating UN Organisation: UN HABITAT | Sector: Shelter Sector Outcome team |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Construction & Housing and Ministry of Municipalities & Public Works |
| Title | Rehabilitation of Community Facilities and Infrastructure |
| Geographic Location | Baghdad, Basrah, Samawa, Najaf and Erbil |
| Project Cost | US$ 16,025,007 |
| Duration | 32 months (pending approval of project extension until June 2008) |
| Approval Date | 29 August 2005 | Starting Date | September 2005 | Completion Date | 31 Mar 2007 |
| Project Description | Rehabilitation of houses, construction & rehabilitation of water supply, sewerage & storm water networks. |

# Development Goal and Immediate Objectives

Improve the living conditions of the most vulnerable groups in Iraqi Society, primarily the urban poor, women headed households and/or persons living in disadvantaged neighbourhoods of the Iraq cities and towns.

# Outputs, Key activities and Procurement

| Outputs | Housing conditions improved for 2,425 vulnerable families (16,807 persons) and adequate shelter and ancillary facilities provided for about 500 orphans Improved water supply and sanitation infrastructure in 8 urban areas benefiting about 650,000 persons. Community based approaches to solid waste management in place Job opportunities for about 1,000 construction workers (on average) during the implementation phase of the project (amounting to about 570,000 person-days of direct employment). |
| --- | --- |
| Activities | Rehabilitation of 2,425 housing units (720 in Basrah, 456 in Baghdad, 500 in Najaf, 649 in Samawa and 100 in Erbil) Construction of 1 new orphanage in Samawa Rehabilitation of water supply and sewerage systems through the rehabilitation of 14 water treatment plants and related pumping facilities, 2 storage reservoirs, and over 80 km of water and sewer networks as well as the procurement of tools and equipment to enhance the capacity of the Municipalities to undertake better operation and maintenance of the water and sewer networks |
| Procurement (major items) | Procure waste management equipment and work with the Municipalities and local councils to set up community based approaches to the provision of basic services Procure of inspection equipment for sewer lines and cleaning equipment |

# Part Two:

# Situation as of 31/12/2007

| Funds Committed | $16,025,007 | % of approved | 100% |
| --- | --- | --- | --- |
| Funds Disbursed | $ 14,492,697 | % of approved | 90.4% |
| Forecast final date | 30 June 2008 | Delay (months) | 20 |

# Quantitative achievements against objectives and results

| Rehabilitation of 2,425 housing units (this figure has been increased to 2,460 housing units) | Rehabilitation of 2,385 housing units (720 in Basrah, 374 in Baghdad, 500 in Najaf, 687 in Samawa and 104 in Erbil) has been completed | % of planned | 97% |
| --- | --- | --- | --- |
| Construction of 1 new Orphanage Care Center in Samawa | Completed | % of planned | 100% |
| Rehabilitation of 2 water treatment plants and 1 associated storage tank in Samawa and 13 potable water compact units in Basrah villages. | Completed | % of planned | 100% |
| Supply of pipelines and construction of storm water networks for 5 neighbourhoods in addition to 2 related pumping stations in Samawa & 1 neighbourhood in Basrah | The works for storm water network in 3 neighbourhoods in Samawa are still ongoing while the other rehabilitation works in both Samawa & Basrah are completed. | % of planned | 75% |
| Construction of one Primary health centre in Samawa serving 1,500 patients per week. | Completed | % of planned | 100% |
| Rehabilitation of one Youth Center in Samawa | Completed | % of planned | 100% |
| Expansion of Samawa Maternity and Children Hospital & rehabilitation of its external walkways, parks, drainage networks and open areas benefiting a number of 200,000 of women & children. | On going | % of planned | 68% |
| Rehabilitation of 1 public hospital in Samawa with a capacity of 64 beds. | On going | % of planned | 65% |
| Procurement of Solid Waste Management Equipment; 8 garbage collection vehicles & 5 tippers | Completed | % of planned | 100% |
| Procurement of sewerage inspection system and cleaning tools for Baghdad Sewerage Directorate | On going | % of planned | 30% |
| Local employment generation | 224,681 persons–days of local employment generated. | % of planned | 112% |

# Qualitative achievements against objectives and results

Enhanced quality of life through improved housing conditions for 3,578 vulnerable families (25,046 persons) Improved quality of life for 500 orphans through provision of adequate shelter and ancillary facilities. Improved access to drinking water in Basrah & Samawa cities, outskirts, and villages by upgrading the water supply capacity of 1000 M3/hr in Basra and 4,500 M3/hr in Samawa through the replacement of old pumps with new one of a larger capacity. Improved quality of water production in existing water treatment plants in Samawa by replacement of sand & gravel in the filters in addition to replacement of old scrapers in the settling tanks. Improved sanitation services in Samawa & Basrah Cities by constructing new storm water networks in 6 neighbourhoods in addition to construction of 2 new disposal pumping stations. Improved garbage collection system for both Basrah & Dywaniyah cities through increase in the fleet capacity by 60 ton of municipal waste per day. Enhanced public facilities and services in Samawa City through the rehabilitation & construction of 2 hospitals, 1 primary health centre, and 1 youth centre benefiting a total population of 304,000.