EIGHTH Six-month progress report for project

IRFFI/UNDG IRAQ TRUST FUND (UNDG ITF)

| Participating UN Organization: |  | Old Cluster: Infrastructure Rehabilitation |
| --- | --- | --- |
| UN HABITAT |  | New Sector: Housing and Shelter |

| Project No. and Project Title: |  | Report Number: |
| --- | --- | --- |
| E4-14 Rehabilitation of Community Facilities and Infrastructure |  | 8 |

| Reporting Period: |  | Project Budget: |
| --- | --- | --- |
| 1 January – 30 June 2008 |  | UNDG ITF: $ 16,025,007 |

| List Implementing Partners: |  | Geographic Coverage/Scope: |
| --- | --- | --- |
| Ministry of Construction and Housing, Ministry of Municipalities and Public Works, Ministry of Health, Ministry of Labour and Social Affairs, Local Municipal Councils, Iraqi Contractors and Consultants |  | Baghdad, Basrah, Samawa, Najaf and Erbil |

| Abbreviations and Acronyms: |  | Project Status: Duration/ Timeline Extension/Closed Project: |
| --- | --- | --- |
| MoCH: Ministry of Construction and Housing MoMPW: Ministry of Municipalities and Public Works DoH : Directorate of Health BoQ: Bill of Quantities MoH : Ministry of Health HQ: Headquarters |  | 14 months starting 9 September 2005 1st budget revision and extension was up to 31 March 2007 2nd budget revision and extension was up to 31 December 2008 |

# NARRATIVE REPORT FORMAT

# Purpose

a.     Main objectives, outcomes, outputs of the programme/project:

Main Objective

The main objective of the project is to improve the living conditions of the most vulnerable groups in Iraqi society, primarily the urban poor, women-headed households and/or persons living in disadvantaged neighbourhoods of Iraq cities and towns.

Immediate Objectives:

- Improve housing conditions for 2,000 families (15,000 persons and 1,100 orphans)

- Improve the living environment in 8 urban areas (650,000 persons) by rehabilitating water supply and sewerage system and re-establishing solid waste disposal systems.

- Promote community based approaches in the operation and maintenance of basic services.

- Assist in reducing the level of unemployment in Iraq by expanding employment opportunities in the construction sector.

Outputs:

The main outputs as per the approved project document are as follows:

- Housing conditions improved for 2,000 vulnerable families (15,000 persons) and adequate shelter and ancillary facilities provided for about 1,100 orphans.

- Improved water supply and sanitation infrastructure in 8 urban areas benefiting about 650,000 persons.

- Community based approaches to solid waste management in place.

- Job opportunities for about 3,000 construction workers (on average) during the implementation phase of the project (amounting to about 570,000 person-days of direct employment).

However, the targeted number of projects and scope of work have been changed to meet the counterpart needs, as follows:

- The number of rehabilitated houses has increased from 2,000 to 2,460.

- Rehabilitation of public facilities including (maternity and children hospital, public hospital, and youth centre)

- Rehabilitation of a dispensary

- Additional three Water Treatment Plants (WTP) were rehabilitated, increasing the total number from 14 to 17.

- The rehabilitation works for sewerage networks have been changed into construction of new sewerage networks.

- The rehabilitation works for one dispensary centre in Samawa was changed to construction of a new dispensary centre.

Outcomes:

- Improved housing, water & sanitation infrastructure, and consequently living conditions for vulnerable groups (urban poor, women, orphans and other disadvantaged segments of the Iraqi society in the 5 targeted governorates).

- Reduced poverty levels through employment generation in the targeted governorates.

- Explain how the programme/project is relevant to the following benchmarks:  UN Assistance Strategy for Iraq, MDGs, Iraq NDS and ICI

- UN Assistance Strategy for Iraq,

The project is an integral component of the Programme being implemented by both Housing & Shelter and WATSAN Sector Outcome Teams (SOT) within the framework of the UN Assistance Strategy for Iraq.  The project will contribute to the achievement of at least three objectives, which are outlined in the SOT strategic plan: (1) to improve shelter conditions for vulnerable groups; (2) increase access to potable water in urban areas and (3) increase solid waste collection and disposal.

- UN Millennium Development Goals,

The project contributes to Millennium Development Goal 7, Targets 10 and 11, which aim at ensuring environmental sustainability through the following actions: (1) reduce by half the proportion of people without sustainable access to safe drinking water, and (2) achieve significant improvement in the lives of at least 100 million slum dwellers by 2020.

- Iraqi National Development Strategy (NDS),

The project is responding to the NDS goals of improving living conditions: Goal 5 - Reduce maternity deaths, Goal 6 - Full access to water and health services, Goal 7 - Decent housing for all.

- International Compact with Iraq (ICI),

4.4.1.5: Reduce population without access to drinking water and sanitation to 10% urban, 30% rural

- Human Resources

  - National Staff: Provide details on the number and type (operation/programme)

Two national operations staff and 3 national programme staff, supported by 6 national field personnel

  - International Staff: Provide the number and role (operation/programme)

Three international staff for operations and programme work

- Programme Manager

- Rehabilitation Expert

- Programme Management Officer

Methods of Operating

  - Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

- UN-HABITAT national consultants, with the active participation of representatives from the Municipal Councils, the Ministry of Health (MoH), and the Water & Sewerage Local Authorities, undertakes detailed assessments of the needs for both rehabilitation of facilities, procurement of supplies and other commodities. The assessment reports cover the basic and complementary needs that could be addressed within the allocated budget. Revisions are made in the UN-HABITAT Office in Amman in order to proceed with the preparation of the bills of quantities (BoQs) by the field personnel who usually show in precise details, the scope of work and specifications.

- The BoQs and the technical specifications are sent to UN-HABITAT Office in Amman for review by the rehabilitation team and for final approval by the National Officer who authorizes the preparation of tender documents. Most of the rehabilitation works are packaged into small contracts with a budget ceiling between $50,000 and $150,000, which can be carried out by small Iraqi Contractors.

- UN-HABITAT maintains a roster of 149 Iraqi Contractors with different specialties and grades in the targeted governorates. The “Vendors Evaluation Committee” reviews the vendors against the office standard criteria, and the approved vendors are included in the office database. Normally, between 10 to 20 Iraqi contractors are invited to a bidding process for rehabilitation works, depending on the estimated value of each contract.

- Implementation supervision is carried out on a daily basis by UN HABITAT field consultant engineers.

  - Provide details on the procurement procedures utilized and explain variances in standard procedures.

- The tender evaluation process incorporates a system of checks and balances with a clear segregation of functions.  Tenders are opened publicly by a Tender Opening Committee and evaluated by a separate “Tender Evaluation Committee” (TEC).  Agency cost estimation is done in Amman Office for each contract, using quarterly updated market prices for construction materials and skilled & unskilled labour.  This estimation is considered a reference for the TEC during the evaluation process

- For contracts that exceed $150,000, the tender evaluation report is subject to review and approval by the Local Contracts Committee of the United Nations Office in Nairobi (UNON). Contracts that are less than $150,000 are locally reviewed and approved by the Programme Manager under the terms of a special delegation of authority.

- Once the lowest acceptable tender is identified, the contract is awarded.

  - Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

- The rehabilitation works are supervised and monitored by Iraqi national consultant engineers and architects. The progress of works is monitored and approved through time-series photographs, daily briefings from the consultants, videos & telecommunication, and laboratory test reports for quality control of construction materials.  In addition, initial handing over certificate is issued upon completion and receipt of the rehabilitated facility by the direct beneficiaries.

- Payment requests for are submitted by the contractors according to a certain percentage of completion of works in line with the terms and conditions of the contract. The payment request including detailed measurements of implemented items and photos reflecting the progress of works before and after completion are thoroughly checked by the Senior Engineer & the Rehabilitation Expert in Amman Office to ensure that the works are completed in high quality and timely., The payment request will be then certified by the Programme Management Officer and finally approved by Programme Manager before being sent to HQ for processing.

.

- During the maintenance period, constant checks of the implemented work are carried out by the field personnel to guarantee implementation sustainability and defects repair. This is further substantiated through interviews with local authority staff and beneficiaries on their perceived quality of works. All contracts incorporate a defects liability clause so that any defects, which emerge after completion have to be repaired by the contractor.

- Before the rehabilitated facility is finally accepted, a final inspection is undertaken by an Acceptance Committee, which comprises representatives of the Local Authority, the beneficiaries, the relevant department of the government and UN-HABITAT staff and consultants.  The final payment is not released until the Acceptance Committee certifies that all work has been satisfactorily completed.

  - Report on any assessments, evaluations or studies undertaken relating to the project and how they were used in support of the project(s).

No assessment, evaluation or studies were done during the reporting period

- Results

  - Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries.

- Housing: In Baghdad, 65 houses were renovated during the reporting period benefiting about 455 people. The total number of completed works in Baghdad has reached 439 (out of 449) houses achieving 97.5 % of the targeted number.

- Water & Sanitation: No water facilities were renovated during the reporting period since all those targeted were renovated in the previous months. In Samawa, HABITAT and partner rehabilitated the sewerage storm water networks in two neighbourhoods, while carrying out 76% of the targeted work in two additional neighbourhoods.

- Public Facilities: One public hospital and one youth centre were rehabilitated while one primary health centre was constructed; the expansion and rehabilitation of the maternity and children hospital has progressed 62%.

  - Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period and explain any variance in achieved versus planned outputs and outcomes during the six month reporting period.

- Enhanced quality of life through improved housing conditions for 2,450 vulnerable families (around 17,150 persons) in 5 governorates.

- Improved sanitation services in Samawa & Basrah cities by constructing new storm water networks in 6 neighbourhoods in addition to construction of 2 new disposal pumping stations benefiting around 55,000 persons.

- Enhanced public facilities and services in Samawa city through the rehabilitation and construction of 2 hospitals, 1 primary health centre, and 1 youth centre benefiting a total of 304,000 inhabitants including pregnant mothers, children, infants and youth.

- 11,154 person-days of local employment was generated during the reporting period contributing so far to providing total employment opportunities of 235,455 person-days.

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints and actions taken to mitigate future delays and lessons learned in the process.

The implementation of the various rehabilitation works has been delayed, largely due to security linked constraints.  Further, the supply of equipment has been affected by difficulties in border crossing and in obtaining custom clearances from the Iraqi authorities. Moreover, there were difficulties in importing some of the major items particularly for the construction of storm water networks and the paving of asphalt due to the shortage of row materials in the local market.

The implementation experience of this project has provided the following significant lessons:

Implementation planning of rehabilitation works:  Most rehabilitation works have taken much longer time than planned due to security-related problems.  This experience has helped to plan the implementation schedules more realistically, factoring in such unanticipated delays. Offshore procurement was also delayed due to long procedures to obtain customs clearances and transportation of goods across borders or through Um-Qasir port.

Fluctuations of market price:  Market prices of both labour and materials have been extremely volatile, affecting the final cost of the projects and scope of the project.  UN_HABITAT now carries our sensitivity analyses of all its designs to rationalize the use of those building materials which are seen to be highly price volatile.

  - List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

UN HABITAT is working closely with the following partners in the project implementation:

- The municipal councils for the residential areas, representatives of the local water and sewerage authorities in each targeted governorate, and representatives of the Directorate of Health (DoH) in Samawa conduct frequent field visits in collaboration with UN-HABITAT consultant engineers.  These partners continue to be involved in all procedures relating to identification of neighbourhoods and public facilities, bid opening, supervision of the works, and final approval of the delivered work. Also, representatives from Baghdad Mayoralty are involved in the process of proposing and approving technical specifications of the cleaning & inspection equipment for Baghdad sewerage network.

- Local contractors in order to maximize the employment impact of the project

- Local consultants and engineers are engaged to conduct technical assessments of scope of work, prepare bidding documents and undertake tender opening processes.  These consultants also supervise, follow up and control the rehabilitation works according to tender based requirements including:  quality of work and compliance with technical specifications and quantities according to the approved BoQ and timely completion of works.

- International suppliers for procurement of technical equipment, tools and instruments

  - Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

The specific achievements regarding various cross cutting themes are as follows:

- Security: Despite security constraints and unforeseen delays, the project achieved 92% completion at the end of the reporting period.  This was primarily because of deployment of local personnel and local contractors in project execution.  Further through generation of considerable local employment, the projects have been contributing to generating livelihood opportunities and linked to it, peace-building.

- Gender and Human Rights: The project addressed issues of human rights and gender equality taking into consideration the different needs, interests and conditions of women and men, in the design, implementation, monitoring and evaluation of the project activities.  The project has so far secured shelter, water and sanitation services for a vulnerable segment of the society in addition to its contribution to reducing mortality and improving maternity and child health facilities.   Sine the projects concerns itself primarily with the rehabilitation of community infrastructure, selection of sub projects, specific design approaches etc. are all subject to community consultation.   The housing rehabilitation component of this project has been executed in close partnership with client communities and preference have been given to poorer and women headed households as a matter of rule,

- Employment: Thus far, the project has generated 235,455 persons-days of local employment, of which 11,154 person-days were generated over the last six months.  During the reporting period, the project has contributed to significant capacity development of 2 new local contractors. .

- Environment: Through expanded access to potable water, the project has indirectly and potentially contributed towards environmental and health improvement, with more cleaning activities being undertaken.  Through improved sanitation facilities, the project has contributed directly to urban environmental and health improvement resulting in reduction of water-borne diseases. The supply of garbage collectors has increased systematic garbage collection and directly contributed to improvements in environmental health conditions.

- Future Work Plan

  - Summarize the projected activities up to the end of December 2008 indicating any major adjustments in strategies, targets or key outcomes and outputs planned.

- Ten remaining houses in Baghdad will be rehabilitated and handed over to the households.

- Storm water networks will be rehabilitated and access roads re-asphalted in 2 neighbourhoods in Samawa.

- One Hospital (Maternity and Children Hospital) in Samawa will be rehabilitated and expanded.

- A CCTV inspection system for sewerage networks to Baghdad Mayoralty will be procured and handed over to the beneficiaries.

# Text boxes

Report Formatting Instructions:

- Number all sections and paragraphs as indicated below.

- Format the entire document using the following font: 12point _ Times New Roman & do not use colours.

- Highlight any new challenges/constraints, mitigation strategies and lessons learned during the reporting period and monitoring processes and assessments, evaluations and studies undertaken/published in the period. Attach documents.

- Attach any available photos relevant to the project.