SEVENTH Six-month progress report for project

IRFFI/UNDG IRAQ TRUST FUND (UNDG ITF)

| Participating UN Organization: |  | Old Cluster: Infrastructure Rehabilitation |
| --- | --- | --- |
| UN HABITAT |  | New Sector: Housing and Shelter |

| Project No. and Project Title: |  | Report Number: 7 |
| --- | --- | --- |
| E4-14 Rehabilitation of Community Facilities and Infrastructure |  | Atlas Award Number: 54907 Atlas Project Number: 66907 |

| Reporting Period: |  | Project Budget: |
| --- | --- | --- |
| 1 June – 31 December 2008 |  | UNDG ITF: $ 16,025,007 |

| List Implementing Partners: |  | Geographic Coverage/Scope: |
| --- | --- | --- |
| Ministry of Construction and Housing, Ministry of Municipalities and Public Works, Ministry of Health, Ministry of Labour and Social Affairs, Local Municipal Councils, Iraqi Contractors and Consultants |  | Baghdad, Basrah, Samawa, Najaf, Missan and Erbil |

| Abbreviations and Acronyms: |  | Project Status: Duration/ Timeline Extension/Closed Project: |
| --- | --- | --- |
| MoCH: Ministry of Construction and Housing MoMPW: Ministry of Municipalities and Public Works DoH : Directorate of Health BoQ: Bill of Quantities MoH : Ministry of Health HQ: Headquarters |  | 14 months starting 9 September 2005 1st budget revision and extension was up to 31 March 2007 2nd budget revision and extension was up to 31 December 2008 3rd Budget revision and extension up to 30 June 2009 |

# NARRATIVE REPORT FORMAT

# Purpose

a.     Main objectives, outcomes, outputs of the programme/project:

Main Objective

The main objective of the project is to improve the living conditions of the most vulnerable groups in Iraqi society, primarily the urban poor, women-headed households and/or persons living in disadvantaged neighbourhoods of Iraq cities and towns.

Immediate Objectives:

- Improve housing conditions for 2,000 families (15,000 persons and 1,100 orphans)

- Improve the living environment in 8 urban areas (650,000 persons) by rehabilitating water supply and sewerage system and re-establishing solid waste disposal systems.

- Promote community based approaches in the operation and maintenance of basic services.

- Assist in reducing the level of unemployment in Iraq by expanding employment opportunities in the construction sector.

Outputs:

The main outputs as per the approved project document are as follows:

- Housing conditions improved for 2,000 vulnerable families (15,000 persons) and adequate shelter and ancillary facilities provided for about 1,100 orphans.

- Improved water supply and sanitation infrastructure in 8 urban areas benefiting about 650,000 persons.

- Community based approaches to solid waste management in place.

- Job opportunities for about 3,000 construction workers (on average) during the implementation phase of the project (amounting to about 570,000 person-days of direct employment).

However, the targeted number of projects and scope of work have been changed to meet the counterpart needs, as follows:

- The number of rehabilitated houses has increased from 2,000 to 2,460.

- Rehabilitation of public facilities including (maternity and children hospital, public hospital, and youth centre)

- Rehabilitation of a dispensary

- Additional three Water Treatment Plants (WTP) were rehabilitated, increasing the total number from 14 to 17.

- The rehabilitation works for sewerage networks have been changed into construction of new sewerage networks.

- The rehabilitation works for one dispensary centre in Samawa was changed to construction of a new dispensary centre.

- The rehabilitation of 11 schools in (5 in Baghdad, 4 in Missan, an 2 in Erbil)

- The rehabilitation of one PHC in Baghdad.

Outcomes:

- Improved housing, water & sanitation infrastructure, and consequently living conditions for vulnerable groups (urban poor, women, orphans and other disadvantaged segments of the Iraqi society in the 6 targeted governorates).

- Reduced poverty levels through employment generation in the targeted governorates.

- Explain how the programme/project is relevant to the following benchmarks:  UN Assistance Strategy for Iraq, MDGs, Iraq NDS and ICI

- UN Assistance Strategy for Iraq,

The project is an integral component of the Programme being implemented by both Housing & Shelter and WATSAN Sector Outcome Teams (SOT) within the framework of the UN Assistance Strategy for Iraq.  The project will contribute to the achievement of at least three objectives, which are outlined in the SOT strategic plan: (1) to improve shelter conditions for vulnerable groups; (2) increase access to potable water in urban areas and (3) increase solid waste collection and disposal.

- UN Millennium Development Goals,

The project contributes to Millennium Development Goal 7, Targets 10 and 11, which aim at ensuring environmental sustainability through the following actions: (1) reduce by half the proportion of people without sustainable access to safe drinking water, and (2) achieve significant improvement in the lives of at least 100 million slum dwellers by 2020.

- Iraqi National Development Strategy (NDS),

The project is responding to the NDS goals of improving living conditions: Goal 5 - Reduce maternity deaths, Goal 6 - Full access to water and health services, Goal 7 - Decent housing for all.

- International Compact with Iraq (ICI),

4.4.1.5: Reduce population without access to drinking water and sanitation to 10% urban, 30% rural

- Human Resources

  - National Staff: Provide details on the number and type (operation/programme)

Two national operations staff and 3 national programme staff, supported by 6 national field personnel

  - International Staff: Provide the number and role (operation/programme)

Three international staff for operations and programme work (part time)

- Programme Manager

- Rehabilitation Expert

- Programme Management Officer

Methods of Operating

  - Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

- UN-HABITAT national consultants, with the active participation of representatives from the Municipal Councils, the Ministry of Health (MoH), and the Water & Sewerage Local Authorities, undertakes detailed assessments of the needs for both rehabilitation of facilities, procurement of supplies and other commodities. The assessment reports cover the basic and complementary needs that could be addressed within the allocated budget. Revisions are made in the UN-HABITAT Office in Amman in order to proceed with the preparation of the bills of quantities (BoQs) by the field personnel who usually show in precise details, the scope of work and specifications.

- The BoQs and the technical specifications are sent to UN-HABITAT Office in Amman for review by the rehabilitation team and for final approval by the National Officer who authorizes the preparation of tender documents. Most of the rehabilitation works are packaged into small contracts with a budget ceiling between $50,000 and $150,000, which can be carried out by small Iraqi Contractors.

- UN-HABITAT maintains a roster of more than 200 Iraqi Contractors with different specialties and grades in the targeted governorates. The “Vendor Evaluation Committee” reviews the vendors against the office standard criteria, and the approved vendors are included in the office database. Normally, between 10 to 20 Iraqi contractors are invited to a bidding process for rehabilitation works, depending on the estimated value of each contract.

- Implementation supervision is carried out on a daily basis by UN HABITAT field consultant engineers.

  - Provide details on the procurement procedures utilized and explain variances in standard procedures.

- The tender evaluation process incorporates a system of checks and balances with a clear segregation of functions.  Tenders are opened publicly by a Tender Opening Committee and evaluated by a separate “Tender Evaluation Committee” (TEC).  Agency cost estimation is done in Amman Office for each contract, using quarterly updated market prices for construction materials and skilled & unskilled labour.  This estimation is considered a reference for the TEC during the evaluation process

- For contracts that exceed $150,000, the tender evaluation report is subject to review and approval by the Local Contracts Committee of the United Nations Office in Nairobi (UNON). Contracts that are less than $150,000 are locally reviewed and approved by the Programme Manager under the terms of a special delegation of authority.

- Once the lowest acceptable tender is identified, the contract is awarded.

  - Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

- The rehabilitation works are supervised and monitored by Iraqi national consultant engineers and architects. The progress of works is monitored and approved through time-series photographs, daily briefings from the consultants, videos & telecommunication, and laboratory test reports for quality control of construction materials.  In addition, initial handing over certificate is issued upon completion and receipt of the rehabilitated facility by the direct beneficiaries.

- Payment requests for are submitted by the contractors according to a certain percentage of completion of works in line with the terms and conditions of the contract. The payment request including detailed measurements of implemented items and photos reflecting the progress of works before and after completion are thoroughly checked by the Senior Engineer & the Rehabilitation Expert in Amman Office to ensure that the works are completed in high quality and timely., The payment request will be then certified by the Programme Management Officer and finally approved by Programme Manager before being sent to HQ for processing.

.

- During the maintenance period, constant checks of the implemented work are carried out by the field personnel to guarantee implementation sustainability and defects repair. This is further substantiated through interviews with local authority staff and beneficiaries on their perceived quality of works. All contracts incorporate a defects liability clause so that any defects, which emerge after completion have to be repaired by the contractor.

- Before the rehabilitated facility is finally accepted, a final inspection is undertaken by an Acceptance Committee, which comprises representatives of the Local Authority, the beneficiaries, the relevant department of the government and UN-HABITAT staff and consultants.  The final payment is not released until the Acceptance Committee certifies that all work has been satisfactorily completed.

  - Report on any assessments, evaluations or studies undertaken relating to the project and how they were used in support of the project(s).

No assessment, evaluation or studies were done during the reporting period

- Results

  - Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries.

- Housing: In Baghdad, 10 houses were renovated during the reporting period benefiting about 72 people. The total number of completed works in Baghdad has reached 449 houses achieving 100 % of the targeted number.

- Water & Sanitation: No water facilities were renovated during the reporting period since all those targeted were renovated in the previous months. In Samawa, UN-HABITAT in collaboration with the partner local authority completed rehabilitation of the storm water networks in two neighbourhoods. Also sewer cleaning equipment for sewer networks for Baghdad Mayoralty is under procurement.

- Public Facilities: The expansion and rehabilitation of the maternity and children hospital has also been completed 100%.

- Education facilities: rehabilitation of 7 schools (5 in Baghdad-Sadr City and 2 in Erbil) has started.

  - Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period and explain any variance in achieved versus planned outputs and outcomes during the six month reporting period.

- Enhanced quality of life through improved housing conditions for 2,474 vulnerable families (around 18,500 persons) in 5 governorates.

- Improved sanitation services in Samawa & Basrah cities by constructing new storm water networks in 6 neighbourhoods in addition to construction of 2 new sewage pumping stations benefiting around 55,000 persons.

- Enhanced public facilities and services in Samawa city through the rehabilitation and upgrading of 2 hospitals, 1 primary health centre, and 1 youth centre benefiting a total of 304,000 inhabitants including pregnant mothers, children, infants and youth.

- 5,200 person-days of local employment was generated during the reporting period contributing so far to providing total employment opportunities of 240,655 person-days.

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints and actions taken to mitigate future delays and lessons learned in the process.

The implementation of the various rehabilitation works has been delayed, largely due to security linked constraints.  Further, the supply of equipment has been affected by difficulties in border crossing and in obtaining custom clearances from the Iraqi authorities. Moreover, there were difficulties in importing some of the major items particularly for the construction of storm water networks and the paving of asphalt due to the shortage of row materials in the local market.

The implementation experience of this project has provided the following significant lessons:

Implementation planning of rehabilitation works:  Most rehabilitation works have taken much longer time than planned due to security-related problems.  This experience has helped to plan the implementation schedules more realistically, factoring in such unanticipated delays. Offshore procurement was also delayed due to long procedures to obtain customs clearances and transportation of goods across borders or through Um-Qasr port.

Fluctuations of market price:  Market prices of both labour and materials have been extremely volatile, affecting the final cost of the projects and scope of the project.  UN-HABITAT now carries our sensitivity analyses of all its designs to rationalize the use of those building materials which are seen to be highly price volatile.

Procurement of Hi tech equipment: There are very few suppliers of Hi tech equipment willing to undertake supplies to Baghdad due to security concerns.  This is primary due to the requirement to also conduct on site training of personnel involved in the O&M of such equipment.  This not only limits competition as is desired under UN Financial Rules and Regulations but often there are no willing suppliers. This also has implications for post-supply maintenance and repairs support services.

  - List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

UN-HABITAT is working closely with the following partners in the project implementation:

- The municipal councils for the residential areas, representatives of the local water and sewerage authorities in each targeted governorate, and representatives of the Directorate of Health (DoH) in Samawa conduct frequent field visits in collaboration with UN-HABITAT consultant engineers.  These partners continue to be involved in all procedures relating to identification of neighbourhoods and public facilities, bid opening, supervision of the works, and final approval of the delivered work. Also, representatives from Baghdad Mayoralty are involved in the process of proposing and approving technical specifications of the cleaning & inspection equipment for Baghdad sewerage network.

- Local contractors in order to maximize the employment impact of the project

- Local consultants and engineers are engaged to conduct technical assessments of scope of work, prepare bidding documents and undertake tender opening processes.  These consultants also supervise, follow up and control the rehabilitation works according to tender based requirements including:  quality of work and compliance with technical specifications and quantities according to the approved BoQ and timely completion of works.

- International suppliers for procurement of technical equipment, tools and instruments

  - Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

The specific achievements regarding various cross cutting themes are as follows:

- Security: Despite security constraints and unforeseen delays, the project achieved 92% completion at the end of the reporting period.  This was primarily because of deployment of local personnel and local contractors in project execution.  Further through generation of considerable local employment, the projects have been contributing to generating livelihood opportunities and linked to it, peace-building.

- Gender and Human Rights: The project addressed issues of human rights and gender equality taking into consideration the different needs, interests and conditions of women and men, in the design, implementation, monitoring and evaluation of the project activities.  The project has so far secured shelter, water and sanitation services for a vulnerable segment of the society in addition to its contribution to reducing mortality and improving maternity and child health facilities.   Sine the projects concerns itself primarily with the rehabilitation of community infrastructure, selection of sub projects, specific design approaches etc. are all subject to community consultation.   The housing rehabilitation component of this project has been executed in close partnership with client communities and preference have been given to poorer and women headed households as a matter of rule,

- Employment: Thus far, the project has generated 240,655 persons-days of local employment, of which 5,200 person-days were generated over the last six months.  During the reporting period, the project has contributed to significant capacity development of 4 new local contractors. .

- Environment: Through expanded access to potable water, the project has indirectly and potentially contributed towards environmental and health improvement, with more cleaning activities being undertaken.  Through improved sanitation facilities, the project has contributed directly to urban environmental and health improvement resulting in reduction of water-borne diseases. The supply of garbage collectors has increased systematic garbage collection and directly contributed to improvements in environmental health conditions.

- Future Work Plan

  - Summarize the projected activities up to the end of June 2009 indicating any major adjustments in strategies, targets or key outcomes and outputs planned.

- Complete the rehabilitation of 7 schools ( 5 in Baghdad- Sadr City and 2 in Erbil)

- Start the rehabilitation of 4 schools in Missan

- Start the rehabilitation works of one Primary Health Center (PHC) in Baghdad

- Six monthly Performance Indicators assessment

|  | Performance Indicators | Indicator Baselines | Planned Indicator Targets | Achieved Indicator Targets | Means of Verification | Comments (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| IP Outcome 1 To improve the living conditions of the most vulnerable groups in Iraqi Society, primarily the urban poor, women headed households and/or persons living in disadvantaged neighborhoods of Iraqi Cities and Towns |
| IP Output 1.1 Housing conditions improved for 2,369 vulnerable families (24,500 persons) in five selected locations (Baghdad, Basra, Samawa, Najaf and Erbil) and adequate shelter and ancillary facilities provided for about 1,100 orphans/physically challenged persons. | Indicator 1.1.1 # of vulnerable families with improved shelter conditions | Nil | 2000 families | 2474 families | Project records |  |
|  | Indicator 1.1.2 # of community facilities rehabilitated/constructed. | Nil | 1 orphanage 1 institute for deaf and mute | 1 maternity and children’s hospital 1 public hospital 1 primary health center 1 youth center 7 schools 1 orphanage 1 institute for deaf and mute |  | 1 maternity and children’s hospital;1 public hospital; 1 primary health center; 1 youth center; were added to the scope of the project on the special request of the donor partner. Rehabilitation of five schools were included in the scope of works following the military operations in Sadr City. Another 2 schools were included in Erbil from savings |
| IP Output 1.2 Improved water supply and sanitation infrastructure in 8 locations benefiting about 650,000 persons. This will involve rehabilitation of 14 water treatment units and 1 sanitary utility each in Basra and Samawa. Construction of 5 storm water net works, 1 sanitary network and 2 pump stations in two other locations with necessary access roads. | Indicator 1.2.1 # of WatSan rehabilitation works |  | 14 Water treatment plants 1 sanitary utility 5 storm water networks 1 sanitary network 2 pump stations | 17 Water treatment plants 5 storm water networks 1 sanitary network 2 pump stations |  | In discussions with the partners the rehabilitation works for a sanitary utility was dropped and replaced by supply of solid waste management equipment for Basra municipality |
|  | Indicator 1.2.2 # of persons benefiting from improved access to WatSan facilities | Nil | 650,000 | Tabulation under process |  |  |
|  | Indicator 1.2.3 # of urban areas with improved WatSan facilities | Nil | 8 locations | 18 locations Samawa (7) and Basra (11) |  |  |
| IP Outcome 2 To improve local employment opportunities generated in rehabilitation works and skills of professionals/ workers strengthened. |
| IP Output 2.1 Community based approaches to solid waste management in place Job opportunities for construction workers during the implementation phase of the project (amounting to about 570,000 person-days of direct employment through local contractors selected in the area of specific intervention. | .Indicator 2.1.1 # of person days of project generated local employment. |  | 570,000 person days | 240,655 person days |  | The actual number of person days of employment generated was less than the target due to mechanized technologies used for the rehabilitation of WatSan works to reduce the period of disruption |
| IP Output 2.2 Skills developed for construction workers and young engineering professionals involved in the rehabilitation activities | Indicator 2.2.1 # of construction workers with improved skills | Nil | 500 persons | Under tabulation |  |  |
|  | Indicator 2.2.2 # of engineering professionals with improving skills | Nil | 20 persons | 42 persons |  |  |

# Text boxes

Report Formatting Instructions:

- Number all sections and paragraphs as indicated below.

- Format the entire document using the following font: 12point _ Times New Roman & do not use colours.

- Highlight any new challenges/constraints, mitigation strategies and lessons learned during the reporting period and monitoring processes and assessments, evaluations and studies undertaken/published in the period. Attach documents.

- Attach any available photos relevant to the project.