# United Nations Development Group Iraq Trust Fund

# Project #:E4-14

# Date and Quarter Updated: 30 June 2008

# Part One: Summary

| Participating UN Organisation: UN HABITAT | Sector: Shelter Sector Outcome team |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Housing & Ministry of Municipalities & Public works |
| Title | Rehabilitation of Community facilities Infrastructure |
| Geographic Location | Baghdad, Basrah, Samawa, Najaf and Erbil |
| Project Cost | US$ 16,025,007 |
| Duration | 40 months |
| Approval Date | August 2005 | Starting Date | September 2005 | Completion Date | December 2008 |
| Project Description | Rehabilitation of Houses, construction & rehabilitation of Water Supply, Sewerage & Storm Water networks. |

# Development Goal and Immediate Objectives

Improve the living conditions of the most vulnerable groups in Iraqi Society, primarily the urban poor, women headed households and/or persons living in disadvantaged neighbourhoods of the Iraq Cities and Towns.

# Outputs, Key activities and Procurement

| Outputs | Improve housing conditions for 2,000 families (15,000 persons) and 1,100 orphans. Improve the living environment in 8 urban areas (650,000 persons) by rehabilitating water supply and sewerage systems and re-establishing solid waste disposal systems Contribute to the promotion of community based approaches to the operation and maintenance of basic services. Assist in reducing the level of unemployment in Iraq by expanding employment opportunities in the construction sector. |
| --- | --- |
| Activities | Rehabilitation of 2,000 housing units (500 in Basrah, 400in Baghdad, 500 in Najaf, 500in Samawa and 100 in Erbil. Rehabilitation of 3 Orphanages (1 in Baghdad 2 in Kirkuk) and construction of 1 new orphanage in Samawa. Rehabilitation of water supply and sewerage systems through the rehabilitation of 14 water treatment plants and related pumping facilities,2 storage reservoirs ,and over 80 km of water and sewer networks as well as the procurement of tools and equipment to enhance the capacity of the municipalities to undertake better operation and maintenance of the water and sewer networks. Undertake the immediate clean up of 8 neighbourhoods and re-active the systems of solid waste management. Procure solid waste management equipment and work with the municipalities an local councils to set up community based approaches to the provision of basic services. Implement the project through small sub-contracts to local contractors and suppliers. Additional activities : Rehabilitation of 460 housing units ( 220 in Basrah , 49 in Baghdad ,4 in Erbil,187 in Samawa). Rehabilitation of 2 public hospitals in samawa. Rehabilitation of 1 youth Centre in Samawa Construction of 1 primary health Centre in Samawa |
| Procurement (major items) | Procure Solid Waste Management Equipment (10 No. garbage collection vehicles & 5 No. tippers) to both Basrah & Dywaniyah. Procure sewerage inspection system and safety equipment and cleaning tools for sewer sub mains & lateral pipelines. Baghdad Sewerage directorate |

# Part Two:

# Situation as of 31/5/2008

| Funds Committed | $15,208,896 | % of approved | 95% |
| --- | --- | --- | --- |
| Funds Disbursed | $ 14,374893 | % of approved | 90 % |
| Forecast final date | 31 December 2008 | Delay (months) | 26 |

# Quantitative achievements against objectives and results

| Rehabilitation of a target 2,460 house and dwelling unit (720 in Basrah, 449 in Baghdad, 500 in Najaf, 687 in Samawa and 104 in Erbil. | Rehabilitation of 2,450 housing units (720 in Basrah, 439 in Baghdad, 500 in Najaf, 687 in Samawa and 104 in Erbil) has been completed | % of planned | 99.5% |
| --- | --- | --- | --- |
| Construction of 1 new Orphanage Care Center in Samawa | Completed | % of planned | 100% |
| Rehabilitation of 2 water treatment plants and 1 associated storage tank in Samawa and 13 potable water compact units in Basrah villages. | Completed | % of planned | 100% |
| Supply of pipelines and construction of storm water networks for 5 neighbourhoods in addition to 2 related pumping stations in Samawa & 1 neighbourhood in Basrah | The work for storm water network in 3 neighbourhoods in Samawa is still ongoing while the other rehabilitation works in both Samawa & Basrah are all completed. | % of planned | 93 % |
| Construction of one primary health centre in Samawa serving 1,500 patients per week. | Completed | % of planned | 100% |
| Rehabilitation of one Youth Center in Samawa | Completed | % of planned | 100% |
| Expansion of Samawa Maternity and Children Hospital & rehabilitation of its external walkways and. sanitation facilities | On going | % of planned | 80 % |
| Rehabilitation of 1 public hospital in Samawa with a capacity of 64 beds. | Completed | % of planned | 100% |
| Procurement of Solid Waste Management Equipment; 10 garbage collection vehicles & 5 tippers | Completed | % of planned | 100% |
| Procurement of sewerage inspection system and cleaning tools for Baghdad Sewerage Directorate | On going | % of planned | 50 % |

# Qualitative achievements against objectives and results

Enhanced quality of life through improved housing conditions for 2,450 vulnerable families (17,150 persons) Improved quality of life for 500 orphans through provision of adequate shelter and ancillary facilities. Improved access to drinking water in Basrah & Samawa cities, outskirts, and villages by upgrading the water supply capacity of 1,000 M3/hr in Basra and 4,500 M3/hr in Samawa through the replacement of old pumps with new one of a larger capacity. Improved water quality in Samawa existing water treatment plants by replacement of sand & gravel in the filters in addition to replacement of old scrapers in the settling tanks which improved the sediment removal quantity and the enhanced the chemical treatment and disinfection of the treated water. Improved sanitation services in Samawa & Basrah Cities by constructing new storm water networks in 6 neighbourhoods in addition to construction of 2 new disposal pumping station benefiting about 55,000 persons. Improved garbage collection system for both Basrah & Dywaniyah cities through the increase in the fleet capacity by 60 ton of municipal waste per day serving around 120,000 inhabitants on daily basis. Enhanced public facilities ,medical and maternity services in Samawa City through the rehabilitation & construction of 2 hospitals, 1 primary health centre, and 1 youth centre benefiting a total of 304,000 inhabitants including pregnant mothers, children, infants and youth. Local employment generation of 235,455 person–days.