# United Nations Development Group Iraq Trust Fund

# Project #: E4-17

# Date and Quarter Updated: October-December 2008 (4th Quarter 2008)

| Participating UN Organisation: UNESCO | Sector: Cluster E – Infrastructure Rehabilitation |
| --- | --- |
| Govt of Iraq – Responsible Line Ministry: Ministry of Planning and Development Cooperation (MOPDC) |

| Title | Technical Assessment for the development of Agro-Industries Sector in Iraq. |
| --- | --- |
| Geographic Location | Country wide |
| Project Cost | US$ 586,800 (UNDG ITF) |
| Duration | 12 months |
| Approval Date (SC) |  | Starting Date | 4th May 2007 | Completion Date | 4th Nov. 2008 including 6 months extension, another 6 months submitted on 24-12-2008 |
| Project Description | This project carries out an in-depth assessment of the agro-industries sub –sector in Iraq and assists to develop and update the industrial data information system to provide up to date information required by the existing industries for strategic planning to maintain its sustainability and enhance new investments in the industrial sector. National capacities will be developed for collection, analysis of industrial data and formulation of industrial policies and strategies. The ultimate aim of the whole project is to assist the Government and stakeholders to develop a consensus on the country’s industrial strategy by utilizing up-to-date industrial statistics. |

# Development Goal and Immediate Objectives

Contribute to the economic recovery of the country through the development of local industries. This will be achieved through developing the local capabilities to carryout industrial surveys and formulate appropriate policies and strategies to develop the industrial sector. Assist the Government of Iraq to launch a programme for the development of agro-industries. Enhance local capacity and capabilities to carry out industrial surveys and formulate appropriate policies and strategies for industrial development.

# Outputs, Key activities and Procurement

| Outputs | A comprehensive agro-industrial sector survey carried our focusing on assessing the processing technologies, competitiveness, growth potentials and investment opportunities. Industrial statistics operations in the Central Organization for Statistical & Information Technology (COSIT) upgraded and capabilities strengthened for collection, analysis and dissemination of industrial statistics. National capacity and capabilities for industrial strategy formulation, implementation and monitoring upgraded. |
| --- | --- |
| Activities | Collect, review, analyse information on business environment, policy matters and legal/regulatory framework. Assess the processing technologies applied by the agro-industries, analyse quality management practices. Conduct analytical survey at enterprise level, identify constraints, weaknesses and deficiencies as perceived by Agro-industries. Training of core staff in local institutions in carrying out industry surveys and competitiveness analysis. Review/assess raw material availability in the agro-industries sector, identify products to be produced, carry out in-depth analysis of sub-sectors. Prepare draft comprehensive Agro-industrial sector survey and organize a national consultative workshop to review survey. Finalize survey for submission to the government. Assess current industrial statistics operations, prepare work plan and establish Industrial Statistics Steering Committee (ISSC). Provide materials on industrial survey methods. Construct register of industrial establishments. Install computer and software and provide training in industrial statistics and computer operations. Prepare questionnaire, formulate and implement enumeration/register-updating strategy. Tabulate questionnaires and prepare and implement dissemination strategy. Formulate and implement test survey for quarterly index of industrial production. Calibrate and implement quarterly survey. Publish annual survey results. Prepare contributions for international workshop. Prepare final reports and documentation and conduct training review to ensure sustainability. Awareness creation workshop on the Industrial Governance and best international practices in strategies formulation and implementation. Setting up/strengthening industrial policy unit in the ministry of industry. Setting up/strengthening unit for economic analysis and monitoring in the chamber of Industry. Training of Ministry staff in the development of agro- and non-agro SMEs and promoting investments in the sub sectors. Study tour to selected countries to review international experience in competitive development in agro-industries. Improve capacities of the ministry to produce, use and document industrial statistics and industrial indicators for the development of agro related and other enterprises. 3.7 Design and set up industrial policy monitoring system. |
| Procurement (major items) | PDA handheld sets, computers, copy machine |

| Funds Committed | US$ 464,791.09 | % of approved | 84% |
| --- | --- | --- | --- |
| Funds Disbursed | US$ 412,443.46 | % of approved | 75% |
| Forecast final date | 3rd May 2009 | Delay (months) | 12 |

# Quantitative achievements against objectives and results

| A comprehensive agro-industrial sector survey carried our focusing on assessing the processing technologies, competitiveness, growth potentials and investment opportunities. | % of planned | 95 |
| --- | --- | --- |
| Industrial statistics operations in the Central Organization for Statistical & Information Technology (COSIT) upgraded and capabilities strengthened for collection, analysis and dissemination of industrial statistics. | % of planned | 100 |
| National capacity and capabilities for industrial strategy formulation, implementation and monitoring upgraded. | % of planned | 95 |

# Qualitative achievements against objectives and results

A full capacity building for the MOPD/COSIT was done for the data collection using advanced technology (PDA) with all the required training for enumerator who done the survey. Two surveys was done, basic survey which identify the small, medium and large enterprises with some basic information. After that 10% from the small enterprises and all the medium and large was covered with intensive and detailed survey. COSIT was supplied with all the required equipments for the survey and new way of collecting the data was introduced to cosit using the PDA’s for the data collection. Several meeting took place to establish the policy formulation manual, this manual is now in the reviewing stage.