# United Nations Development Group Iraq Trust Fund

# Project #: G11-16

# Date and Quarter Updated: January- March, 1st Quarter 2009

| Participating UN Organisation: UNOPS and UNAMI | Sector: Governance |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: IHEC |

| Title | Support to Electoral Observer Groups in Iraq Phase III |
| --- | --- |
| Geographic Location | Iraq, Baghdad and 18 Governorates - Jordan, Amman |
| Project Cost | USD 6,243,599 |
| Duration | 15 months |
| Approval Date (SC) | 17 Jan 2008 | Starting Date | 24 Jan 2008 | Completion Date | 24 April 2009 |
| Project Description | This project was developed to provide support to Iraqi national electoral observer networks through the training of initially 20,500 domestic electoral observers and media monitors, in observation, reporting skills and media monitoring, and, at a later stage to facilitate their work during the next electoral event in Iraq. To guarantee impartiality and independence the project was implemented through two international Non-Governmental Organisations (NGOs): Friedrich-Ebert-Stiftung (FES) and Amman Centre for Human Rights Studies (ACHRS). After the successful completion of these activities during the Voter Registration Update in July/August 2008, and utilizing remaining funds (savings achieved from relocation of activities from Jordan to Iraq), the project was revised to support the training of an additional 1,250 electoral observers and their mobilisation for the governorate elections in January 2009. |

Development Goal and Immediate Objectives

To contribute to an enhanced implementation of electoral processes in Iraq in line with UNCT Goal 4 (Promote good governance and democratic processes, assist to uphold the rule of law and establish a human right regime) through the provision of electoral observation and media monitoring training and support to Electoral Observers during the next electoral event in Iraq. The project identified as immediate objectives: Support election observation networks through Training of Trainer (ToT) capacity building workshops on election observation and media monitoring in Amman and cascade training on these topics in Iraq. Facilitate the work of electoral and media observers during an actual electoral event through the provision of mobilisation allowances for elections observers and media monitors on Election Day.

| Outputs, Key activities and Procurement |
| --- |
| Outputs | 1.1 80 personnel from Iraqi national observer groups will have received ToT at workshops in Amman on election observation and reporting skills. 1.2 20 personnel from Iraqi Media Monitoring groups will have received ToT at a workshop in Amman. 1.3 21,750 national electoral observers will have attended 860 training workshops on electoral observation and reporting skills delivered by those trainers who attended the courses in Amman. 1.4 500 media monitors will have attended 20 workshops delivered by those trainers who received training on media monitoring during electoral processes. 2.1 21,750 electoral observers and media monitors will have been mobilised and will have received an allowance to cover food, transportation and communication on Election Day. |
| Activities | During the reporting period, 1,250 electoral observers were to be trained and mobilised on Election Day on January 31st 2009. |
| Procurement (major items) | None |

| Funds Committed | USD 5,930,102.70 | % of approved | 95 % |
| --- | --- | --- | --- |
| Funds Disbursed | USD 5,809,681.66 | % of approved | 93 % |
| Forecast final date | 24 April 2009 | Delay (months) | 0 |

| Direct Beneficiaries | Number of Beneficiaries during the reporting period | % of planned (current status) |
| --- | --- | --- |
| Men | 1250 (no breakdown between men and women available for this project) | 94 % |
| Women |  |  |
| Children |  |  |
| IDPs |  |  |
| Others |  |  |
| Indirect beneficiaries | By contributing to a transparent democratic election process, the mobilisation of electoral observers benefits the population of Iraq and in extension also the populations of the neighbouring countries |  |
| Employment generation (men/women) |  |  |

| Quantitative achievements against objectives and results |
| --- |
| 80 personnel from Iraqi national observer groups will have received ToT at workshops in Amman on election observation and reporting skills. | 100 | % of planned |  |
| 20 personnel from Iraqi Media Monitoring groups will have received ToT at a workshop in Amman. | 100 | % of planned |  |
| 21,750 national electoral observers will have attended 860 training workshops on electoral observation and reporting skills delivered by those trainers who attended the courses in Amman. | 100 | % of planned |  |
| 500 media monitors will have attended 20 workshops delivered by those trainers who received training on media monitoring during electoral processes. | 100 | % of planned |  |
| 2.1 21,750 electoral observers and media monitors will have been mobilised and will have received an allowance to cover food, transportation and communication during electoral events. | 94 | % of planned |  |

Qualitative achievements against objectives and results during this reporting period

Output 2.1 On election day 31st January; 1250 independent national observers were mobilised having been trained earlier in the month. However monitoring and evaluation requirements are still ongoing to provide confirmation of complete mobilisation.

Main implementation constrains & challenges (2-3 sentences)

EIN Network has submitted documentation for the mobilisation of 5000 observers (1250 are funded by this project). The documentation has irregularities and is being questioned. An explanatory dialogue has been opened and is ongoing. Although monitoring of the elections ran smoothly, recommendations for future mobilisations of independent observers suggest that a greater clarification of the appropriate relationship between IHEC and independent observers, as well as the role that IHEC plays in elections, would be of value. In order to enhance results, there should also be a call centre available to advise election observers on how appropriately to implement their observation tasks during elections.