# United Nations Development Group Iraq Trust Fund

# Project #: 57985 (G11-15)

# Date and Quarter Updated: January 15th 2009, 4th Quarterly report, October-December 2008

| Participating UN Organisation: UNOPS | Sector: Governance |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Independent High Electoral Commission (IHEC) |

| Title | Electoral Education Campaign (G11-15) |
| --- | --- |
| Geographic Location | Complete national coverage (19 electoral governorates) |
| Project Cost | 5,006,147 USD |
| Duration | October 2007 – March 2009 |
| Approval Date (SC) | 30/09/2007 | Starting Date | 03/10/2007 | Completion Date | 31/03/2009 |
| Project Description | The Electoral Education Campaign Project (EECP)seeks to raise public awareness of and create discussion around all aspects of electoral processes by supporting initiatives developed by the Iraqi civil society and by the Independent High Electoral Commission (IHEC) of Iraq, so that Iraqi voters will be better prepared for and participate more actively in the upcoming electoral events. The two core objectives of the EECP are: 1. To establish around the electoral process at national and governorate levels appropriate structures to create close cooperation between the IHEC and Iraqi civil society as a means to increase transparency, independence and success of the electoral processes. These structures will aim to remain a permanent coordination body between the civil society and the IHEC after the conclusion of the project. 2. To enhance public awareness of electoral processes and principles using grant-funded civil society projects as well as opportunities to link local opinion leaders with the IHEC, following policies set by the Electoral Education Forum. |

# Development Goal and Immediate Objectives

Establish and support an Electoral Education Forum (EEF) around the electoral process, composed of prominent civic education-oriented networks and NGOs, the IHEC, as well as IEAT and other international representatives, in which a strategy and action plan for the Electoral Education Campaign can be negotiated, planned and monitored collegially. Enhance public awareness of electoral processes and principles using grant-funded civil society projects and opportunities to link local opinion leaders with the IHEC, following policies set by the Electoral Education Forum. Create long-term support of the IHEC towards the Iraqi civil society involvement in electoral education as a means to increase transparency, independence and success of the electoral processes. The objectives of this project are not immediately related to the MDGs, however could be said to indirectly refer to MDG8.

# Outputs, Key activities and Procurement

| Outputs | The 7 expected outputs of the Electoral Education Campaign Expected output 1: An Electoral Education Forum composed of prominent civic education-oriented networks and NGOs and the IHEC is created at the national level, gathers representatives of IHEC and of Iraqi civil society and meets on a regular basis. Expected output 2: In each governorate, a Governorate Electoral Education Committee, composed of representatives from the IHEC, civil society and the media, is created to coordinate the planning, implementation and monitoring of the Campaign at the local level and meets regularly. Expected output 3: A group of NGOs is selected through a grant fund mechanism and trained about project and financial management. Expected output 4: The selected group of NGOs implements public outreach action plans in each electoral governorate in order to ensure that at least 55,000 Iraqi citizens have gained accrued understanding of and interest for the electoral processes, thus leading to a higher participation rate on the Election Day. Expected output 5: A National Electoral Education Plan which sets policies and implementation mechanisms for the national Electoral Education Campaign, including an overall strategy for the Campaign and detailing key messages to be delivered, roles and responsibilities of governmental and non-governmental actors, methods and materials, as well as oversight and coordination mechanisms, is developed. Expected output 6: In each electoral governorate, Opinion Leaders Sessions targeting political entities, civil servants, youth leaders, traditional leaders, etc. are implemented and allows raising public awareness of at least 2.500 Opinion Leaders across the country. Expected output 7: A promotional campaign involving media materials (publications, radio, TV) is launched across the country to support key messages of the Campaign. |
| --- | --- |
| Activities | As per project documents: 1.1.1 An implementing partner is selected to establish the Service Providerof the Electoral Education Forum, organize the launch meeting and subsequent meetings of the Forum and support the implementation of governorate-based activities. 1.1.2. Finalize with the IHEC, the list of representatives invited to sit in the EEF 1.1.3. Organize a 4-day launch meeting of the EEF. 1.1.4. A website and e-Forum facility is set up for the EEF. 1.1.5. An EEF newsletter is produced on a monthly-basis. 1.1.6. A Monitoring Agent is selected to monitor and evaluate all activities undertaken by the EEF. 1.2.1. The EEF reaches consensus on key themes to be tackled during the Electoral Education Campaign, identifies key messages for public outreach and appropriate methods for dissemination, all presented in a National Electoral Education Plan (NEEP). 1.2.2. The EEF agree on the division of responsibilities under the National Electoral Education Plan between the IHEC and civil society and nominates a Board for the Forum (with representation of the IHEC). 1.3.1. The EEF Board meets on a bi-weekly basis in Baghdad with support from the EEF Secretariat. 1.3.2. The EEF convenes in plenary every 2 months in Baghdad for coordination meetings, under the leadership of the Board and with operational support of the Secretariat, to review progress and impact of campaign and discuss necessary adjustments in relation to the actual situation of the electoral processes. 1.4.1. The EEF Service Providerdevelops terms of reference for a promotional campaign on the EEF and NEEP, to be approved by the EEF Board. 1.4.2. A graphic design company is contracted by UNOPS to design, based on the Terms of Reference, promotional materials made of: posters, banners, pamphlets, accessories (Tshirts, pens, notebooks, caps, stickers, etc.) as well as radio spots (x 3) and TV spots (x 2). 1.4.3. Materials are produced and dispatched to 18 GEECs. 1.4.4. Distribution to end-users through meetings with opinion leaders, Grant Fund projects and media outlets. 1.4.5. Radio and TV spots are aired on national and local channels for a total of 3 months (to be split according to actual schedule of the Electoral Education Campaign on the ground). 1.5.1. The Monitoring Agent produces a final evaluation report on the EEF’s work, including a post-campaign impact survey run on a sample of direct and indirect project beneficiaries. 1.5.2. A final Conference of the EEF is held after completion of the project. 1.5.3. Decisions are made on the future and the statutes of the EEF including its funding strategy. 2.1.1 Terms of Reference for the Electoral Education Grant Fund (EEGF) are prepared and discussed with the IHEC, with a breakdown of funds made available per region and per recipient institutions (1. NGOs, 2. Universities, 3. Schools, 4. Media outlets). A special allocation is reserved as well for women & youth projects. 2.1.2. The Grant Fund is advertised throughout the country and receives proposals. 2.1.3. The Project Management Committee (PMC) made of the IHEC and IEAT selects proposals for funding (target of 70 grants country-wide). 2.1.4. UNOPS staff and the EEF Service Providerassist selected NGOs in finalizing their proposal and enhance their project management and reporting capacities. 2.2.1. Up to 70 electoral education projects are funded across the country, covering a large spectrum of target groups and involving a diverse range of activities such as workshops, seminars, art/culture events, production of materials, research and opinion polls, etc. Each project reaches in average 600 beneficiaries. 2.2.2. Other rounds of small projects are funded at a later stage of the electoral process through the same mechanism. 2.2.3. The Monitoring Agent monitors the Grant Fund projects and measures their efficiency (number of persons actually reached). 3.1.1. With support from the Secretariat, Governorate Electoral Education Committees (GEEC) are formed. Each GEEC is composed of representatives of grantees selected under the Grant Fund and from IHEC Governorate Offices staff. 3.1.2. Training of trainers for GEEC members4 on all relevant electoral themes and on the National Electoral Education Plan, run on a regional basis (Erbil, Baghdad, Basrah) by the EEF Secretariat. 3.1.3. Each GEEC meets regularly to coordinate the various activities taking place at governorate level for the Electoral Education Campaign (see Grant Fund under 2.2. and debate / awareness sessions under 3.2). 3.2.1. Each GEEC defines an action plan to run consultations and training with opinion leaders on electoral themes. Plans are reviewed and endorsed by the Board of the EEF and funds to support them released by UNOPS. 3.2.2. Each GEEC reaches at least 125 opinion leaders (depending on governorate size) through 2-day focus group meetings of about 25 persons each, resulting in at least 2500 civic leaders reached nation-wide. 3.2.3. The Monitoring Agent attends and reports on all GEEC outreach meetings 3.3.1. Each GEEC convenes for a wrap-up meeting after series of awareness trainings with civic leaders carried out, and compiles outcomes of the process (suggestions, critics, questions, appreciations raised by civic leaders on new electoral framework) in a Governorate Report. Each wrap-up meeting is facilitated by the Secretariat. 3.3.2. The 18 Governorate Reports are received by the Service Providerand compiled in a National Report. 3.3.3. The National Report is presented to the EEF and to the IHEC Board of Commissioners. 4.1.1. Two Iraqi civil society experts are recruited, briefed and seconded to the IHEC Public Outreach Division for the duration of the project. 4.1.2. The Public Outreach Division (POD) ensures optimal participation level from the IHEC to initiatives run by the EEF. 4.1.3. The Public Outreach Division represents the IHEC in the Project Management Unit. 4.2.1. The IHEC staff directly involved with the EEF (members of the Forum and governorate staff seating in the GEECs) receive a two-day orientation training on the civil society (rights, laws) in Erbil, organized by the Secretariat. 4.2.2. The Public Outreach Division provides regular briefings to IHEC staff and commissioners on the progress of the Electoral Education Campaign. 4.3.1. The IHEC chairs the Grant Selection Committee established within the Project Management Committee. 4.3.2. After completion of the first round of grants [for a total of 1,5 m USD], and assuming that evaluation by the monitoring agent has proven the efficiency of the mechanism, the IHEC provides additional funds to the Grant Fund (with a target of 20% co-funding). |
| Procurement (major items) | Processing Mid-Term reports and disbursement of payments to NGO’s Following the disbursement of Funds for the 75 granted NGO’s, NGO’s started the implementation of their projects at the local level in all 19 governorates in Iraq. During the reporting period, and starting from October, UNOPS office started to receive mid-term reports from grantees. The methodology of processing those reports is as follows: NGO prepares both narrative and financial reports based on UNOPS regulations Field Staff conduct initial check on NGO reports Narrative and Financial reports sent to EECP in Amman Narrative reports are checked along with financial reports against support documents sent by the organization. 64 mid-term narrative and financial reports have been received. The process of checking and finalizing this large number of reports meant that the Project must apply high levels of flexibility in terms of time and method, and thus successfully finalized 38 reports. Moreover, the Field Staff in Iraq staff played a big role in following up and constantly monitoring the activities and the performance of the granted NGO’s. Also, this process provided a greater opportunity for project team in Amman and grantees to communicate and interact trying to solve any problem that might arise in terms of support documents ensuring full commitment to UNOPS regulations. Operational implementation: Following the termination by UNOPS of AYC contract on the 10th of September, monitoring has been -as previously- assumed by UNOPS Field Staff until a new contract was signed with the new Service Provider (Stars Orbit Company - SOC). SOC will play a key role in administrating the Forum Coordination Committee (FCC) meetings on a monthly basis and well as Forum meetings. Furthermore, since the signature of the contract with SOC, they have been working in close coordination with UNOPS in conducting Opinion Leaders Sessions (OLS) all over Iraq (49 conducted until December). SOC managed also to issue a draft newsletter for the EECP, as well as a compiled National Campaign Update including all activities covering September and December. With regards to the monitoring activities of the campaign, and as planned in the previous quarter, a total of 19 Liaison Officers and another 19 Monitoring Assistants were deployed across Iraq to provide further support to the Field Staff and the Service Provider. |

| Funds Committed | 568,046.19 | % of approved | 11.3% |
| --- | --- | --- | --- |
| Funds Disbursed | 312,153.35 | % of approved | 6.2% |
| Forecast final date | 31/03/2009 | Delay (months) | 0 |

# Quantitative achievements against objectives and results and Qualitative achievements against objectives and results

Expected Output 1

Results: The Electoral Education Forum is composed of 19 representatives from various Iraqi civil society organizations and 4 members are from the IHEC. IHEC nominated its members to the Forum through a decision made by the Board of Commissioners. Civil society members on the Forum were jointly selected by UNOPS and IHEC: UNOPS submitted a draft list of NGOs to IHEC who endorsed and approved the final list. Membership in the Forum is on a voluntary basis. All Forum members have signed a Code of Conduct that calls for respect to the role of IHEC and complete neutrality and impartiality in the conduct of their work. A Forum Coordination Committee composed of one IHEC representative as well as civil society representatives was also elected during the Forum launch meeting and empowered to act as the equivalent to a ‘Steering Committee’ for the Electoral Education Forum. The committee meets on a bimonthly basis. In 2008, until December, the Forum held 6 meetings, to plan and follow up the Electoral Education Campaign. The Forum also revised and approved the National Electoral Education Plan in addition to a press conference. Seven Forum newsletters have been produced during the reporting period.

100 % of planned

Expected Output 2

Results: Members of the GEEC have the responsibility for the overall coordination of the Election Awareness Campaign, and are making sure that all OLS meetings were planned appropriately. They were also responsible to invite CSOs, the Religious Leaders and others to attend the meetings. Since the beginning of the EECP and until December, more than 108 (out of 114 planned) GEEC were held. 50 of which were conducted during the reporting period. Around 3 GEEC meeting took place in each of the 18 governorates. There was high coordination between GEEC members and the media to insure their presence in the major events in order to get maximum media coverage.

94 % of planned

Expected Output 3

Results: In December 2007, UNOPS launched a Call for Proposals open for one month to all NGOs in Iraq. It was disseminated through a wide network of NGO contacts, IHEC, and other national and international partners. UNOPS did not publish the Call for Proposals in newspapers for security reasons. UNOPS received 252 proposals. Selection criteria were: technical quality of proposal, feasibility of project, reasonableness of budget, number of targeted beneficiaries, experience of the NGO in similar work, attention given to gender aspects. All proposals were submitted by UNOPS to IHEC (cf. receipt signed on 22 January 08 by Commissioner Ayad, IHEC, and Mr. Nicolas Garrigue, UNOPS). EECP management proposed to IHEC that a Commissioner will participate as voting member in the selection process of the NGOs (letter of Ms. Fiona Bayat to the Chairman of IHEC Board of Commissioners on 23 January 2008). On the 4th of February 2008, UNOPS accepted the proposal of the IHEC BoC Chairman to nominate Com. Ayad and Mr. Abdulrahman Khalifa, Director of IHEC Public Outreach Division. IHEC submitted evaluation grids completed by several IHEC staff (grids signed by Mr. Abdelrahman Khalifa, Ms Hind Ali Sayid, Mr. Moayed Rashed, Mr. Ahmed Mubher, Mr. Aziz al Rafaji, Ms Gulshan Kamal, etc... dated between 31st of January and 7th February 2008). Commissioner Ayad and Mr Abulrhaman Khalifa, Director of POD, signed as “member of the UNOPS evaluation team” the confidentiality affidavit on 21 February 2008. However, in order to avoid having to provide justifications to civil society for the selection, IHEC decided to unofficially request from UNOPS to present their involvement in the process as an observer role. Therefore, UNOPS and UNAMI officially carried out the selection of 75 NGOs out of the 252, under the ‘observance’ of IHEC. IHEC (Commissioner Ayad) wrote to UNOPS on 15 March 2008: “Independent High Electoral Commission in Iraq officially approves the below list of names of organizations selected to receive funds through the Electoral Education grant fund [list attached]”. The final selection list was co-signed by Ms. Fiona Bayat, UNOPS, Ms. Samantha Aucock, UNAMI, Commissioner Ayad al Kinani, IHEC and Mr Abdelrahman Khalifa, IHEC. In March 2008, four regional four-day training sessions for pre-selected grantees were held in Erbil (1) and Baghdad (3) on proposal writing and grants management. Trainings for the Southern region were also held in Baghdad due to poor security conditions in Basra. In June 2008, four regional four-day training sessions for GEEC members (both grantees and IHEC staff – GEO directors and GEO media officers) were held in Erbil (1) and Baghdad (3) on holding electoral education activities and how to use the National Electoral Education Plan.

100 % of planned

Expected Output 4

Results: On 30.11.2008 all signed MOA’s with granted NGO’s came to an end, except for the NGO’s which signed the no cost extensions, their MOA’s expired on 30.12.2008, thus concluding the outreach activities conducted by the grantees. Through the 75 NGOs granted under the Electoral Education Campaign Project, an average of 2000 public awareness activities a month have been implemented from July to December 2008, in the 18 governorates of Iraq, targeting minorities, women, youth, IDPs, disabled people, first time voters, etc. According to the reports obtained until December from granted NGOs have successfully reached 162,106 individuals in Iraq by implementing 11,272 activities including public debates, meetings, training workshops, conferences, cultural and theatrical shows, sports activities, and home visits.

100 % of planned

Expected Output 5

Results: After the endorsement of the NEEP by the Electoral Education Forum, The National Electoral Education Plan has been published in Arabic and English and distributed during NGO activities as well as all held OLS. In addition to the NEEP, the Electoral Education Manual providing concrete blue prints for electoral education sessions developed in the previous quarter of the project, was printed and disseminated during this reporting period to GEOs and granted NGOs across Iraq. Another achievement under this output, is the translation of both the NEEP and the EEM into Kurdish Language; the EECP brochure is also now available in Kurdish, thus allowing more visibility to the EECP and easier access to information to the people of Iraq at all levels.

100 % of planned

Expected Output 6

Results: In spite of the long delay on holding the OLS which affected this component in the previous project quarter, thanks to the new service provider, and the presence of LO’s, the implementation of OLS has resumed with exceptional success nationwide. OLS for are planned for the following clusters: Political Entities Religious and Tribal Leaders Civil Servants, Academics and Professional Associations Women and Youth Associations 49 Opinion Leaders’ Sessions have been implemented in all Iraqi governorates, targeting political entities, tribal and religious leaders, civil servants and academics, youth and women associations. The opinion leaders sessions reached 3988 opinion leaders until December. Once all the opinion leaders’ sessions are implemented, more than 6000 opinion leaders will be reached.

90 % of planned

Expected Output 7

Results: A comprehensive promotional campaign has been designed and foresees the production of the following materials: Printed materials EECP brochure: 1000 Arabic / 500 Kurdish / 500 English: Done National Electoral Education Plan: 500 Arabic /500 Kurdish: Done Electoral Education Manual: 1500 Arabic / 500 Kurdish: Done Forum Newsletter (monthly) 1500 Arabic / 300 Kurdish: Done Posters: 3000 Arabic /600 Kurdish: Ongoing Pins: 5,200 bilingual: Done Banners: 200 bilingual: Done Audio-visual materials Radio spots: 1-3 min long Two spots: Arabic and Kurdish Broadcast: National / Local Channels TV Spots: 30” long One spot: Arabic and Kurdish Broadcast: National / Local Channels Documentary: 10 minutes Produced after end of Phase 1 of the Campaign. 40% of this output is still to be implemented, however, based on needs assessment in the field, other needs emerged and thus a reallocation of the funds is under consideration.

60 % of planned

OPERATIONAL SITUATION OF THE ELECTORAL EDUCATION CAMPAIGN

| Expected outputs | Delivered results |
| --- | --- |
| 1 | 100% |
| 2 | 94% |
| 3 | 100% |
| 4 | 100% |
| 5 | 100% |
| 6 | 90% |
| 7 | 60% |
|  | average operational delivery: 92% |

# Footnotes

Total membership should remain around 20

To avoid conflicts of interest, civil society members of the EEF cannot set in this selection committee

Exact size of membership in each GEEC will vary but a rule will be applied making civil society representation in these committees higher than IHEC’s

This TOT will be run as soon as recipients of grant fund support are selected so that these CSOs can apply the knowledge acquired in these training sessions in their own projects