Sixth Six-month progress report for project

# REPORT COVER PAGE

| Participating UN Organization: |  | Cluster: |
| --- | --- | --- |
| UNHCR, UNOPS |  | F - Refugees, IDPs and Durable Solutions |

| Project No. and Project Title: |  | Report Number: |
| --- | --- | --- |
| F8-04 Support to Iraq’s National, Regional and Local Authorities and Civil Society Organizations in Developing a Draft National Policy and Addressing Displacement Needs and Gaps |  | 3 |

| Reporting Period: |  | Project Budget: |
| --- | --- | --- |
| 1 January – 31 December 2007 |  | UNDG ITF: 1,535,135 USD Other: 640,000 USD Total: 2,175,135 USD |

| List Implementing Partners: |  | Project Coverage/Scope: |
| --- | --- | --- |
| Ministry of Displacement and Migration (MoDM) Kurdistan Regional Government (KRG) NGOs: e.g., Kurdish Human Rights Watch, Mercy Hands, Cooperazione Italiana (COOPI) |  | Iraq-wide interventions (national consultations, intentions survey, policy development), Dahuk, Erbil, Sulaymaniyah, Baghdad, Diyala and Kirkuk Governorates |

| Abbreviations and acronyms: |  | Project Duration/Closed Project: |
| --- | --- | --- |
| PACS – Legal Aid and Information Centre KRG – Kurdish Regional Government MoDM – Ministry of Displacement and Migration MoERA- Ministry of Region for Extra-Regional Affairs GoI – Government of Iraq |  | 1 May 2006 – 31 August 2007 (A no-cost budget revision requesting a prolongation was submitted to SCSO on 17.07.2007 and again in December 2007. The requested project final date is now December 2008. |

# NARRATIVE REPORT FORMAT

# Purpose

  - Main objectives, outcomes and outputs of the programme/project:

The key immediate objectives of the programme/project are:

1) To address current capacity gaps of Iraqi authorities in the protection and assistance of persons of concern, providing support to impacted individuals and communities pending full capacity.

2) To enable communities impacted by displacement and witnessing rising tension to peacefully resolve conflict through income-generation activities alongside alternative dispute resolution learning programmes.

The expected outcomes of the programme project are:

(Please note that the below outcomes are on the Cluster Outcome Level as outcomes are not defined in the project submission)

For Objective 1&2:

- Cluster Planned Outcomes (11) An Iraqi-led vision on how to address displacement challenges.

- Cluster Planned Outcomes (12) Enhanced respect for human rights through tailored protection tools.

The expected outputs of the programme/project within this reporting period are:

For Objective 1:

- A draft of the National Policy on Displacement Challenges and Durable Solutions (now called National Policy on Internal Displacement) has been developed and addresses Iraq’s internal displacement context and challenges.

- Consensus is reached at the National Conference on Displacement Challenges and Durable Solutions (National Conference), which provides a forum for consultations and negotiation between central, regional and local authorities along with civil society actors.

- The KRG authority dealing with displacement issues has effective structures and methods and skilled staff to collect and analyze the protection and assistance needs and gaps of IDPs and their host communities as well as regularly exchange data with MoDM.

- Governorate Assessment Reports for Diyala and Baghdad are issued based on comprehensive monitoring of returnee villages/households, and development of responses to identified protection and assistance gaps.

- A Legal Aid and Information Centre (now called PACS: Protection and Assistance Centre) in Kirkuk and its legal aid mobile teams are fully operational and provide legal counseling, information and legal representation in select cases.

For Objective 2:

- Areas of latent tension identified in preparatory works for the National Policy receive targeted assistance, particularly through income-generation with a conflict transformation component.

  - Relevance of programme/project to the following benchmarks:

- UN Assistance Strategy for Iraq,

The Government of Iraq, regional authorities and civil society actors will be able to fulfill their obligations towards displaced and vulnerable populations, in terms of policy, response and durable solutions in a transparent and equitable manner, keeping in line with democratic principles and international human rights standards and responding to national conditions, thereby enhancing national unity of Iraq.

- UN Millennium Development Goals

The project contributes indirectly to the attainment of Millennium Development Goals 1-7 by enhancing governmental protection and assistance to persons of concern in all sectors, including hunger alleviation/ food security, education, health and nutrition and disease control, while promoting self-reliance with sensitivity to vulnerability factors.

- Joint Needs Assessment

The project addresses directly the cluster and matrix outcomes from the Joint UN Iraq Assistance Strategy 3.1, 4.3, 4.5 and 4.7 of Cluster F: Refugees, IDPs and Durable Solutions and indirectly contributes to achieving outcomes of Cluster C as follows:

3.1 Enhanced national cohesion (unity and diversity) and democratic values.

Cluster F: Reconciliation and increased tolerance promoted through education.

Cluster C: A national commitment to dialogue and reconciliation.

4.3 Local and central institutions are accountable and have the capacity to make informed decisions and implement them in a transparent manner./4.5 Institutions and law enforcement agencies effectively promote and protect human rights

Cluster F: Capacitated local and central institutions protecting and assisting refugees, IDPs, returnees and stateless persons. An Iraqi led vision on how to address displacement challenges.

Cluster C: Respect for the rule of law and a national system of human rights.

4.7 Enhanced respect for human rights especially of women, children and vulnerable groups.

Cluster F: Enhanced respect for human rights through tailored protection tools.

- Iraqi National Development Strategy

The project contributes indirectly to INDGs 1-7 (see also above).

  - Main Implementing Partners: Their roles, responsibilities, and their interaction with the Agency

MoDM and KRG

UNHCR, IOM and MoDM have signed a Memorandum of Cooperation covering the activities for the development of the National Policy; in addition, UNHCR and the KRG have signed a similar Memorandum of Understanding. The activities included in this project were discussed and agreed upon with the Iraqi authorities, who have been closely involved in the overall design of the Project and are fully engaged in its implementation.

Project activities have been contracted by UNHCR and UNOPS:

- Monitoring of returnees in the Governorates of Diyala and Baghdad, the PACS in Kirkuk as well as support to MoDM and KRG in drafting the different parts of the National Policy are directly supported by UNHCR;

- Capacity building of the institution in KRG responsible for IDP issues, and the IDP Intentions Survey in the three Northern Governorates are directly supported by UNOPS;

- Preparation for the National Conference is jointly supported (logistically and technically) by UNOPS and UNHCR (UNOPS on preparation, organisation and logistics; UNHCR on content).

- Implementation of pilot Conflict Management activities by NGO partners is managed by UNHCR in Baghdad and by UNOPS in Northern Iraq.

Implementing Partners:

The following implementing partners have been contracted:

National Conference and National Policy on IDPs

MoDM, KRG and other line Ministries lead the process of drafting and developing the National Policy on IDPs. The National Conference will be organized and co-chaired by MoDM, KRG and the Prime Minister’s Office to guarantee national ownership of the outcomes of the process. UNOPS and UNHCR will provide technical and logistical support.

Monitoring of displaced populations in Diyala and Baghdad

Mercy Hands (national NGO): under UNHCR contract.

IDP Intentions Survey in the Kurdistan Regional Area

Cooperazione Italiana (COOPI) under UNOPS contract.

Conflict transformation pilot activities

Local and international NGOs: Mercy Hands for Humanitarian Aid in Baghdad (under UNHCR contract) and two national NGOs – KEDO and INSAN in Northern Iraq (under UNOPS contract).

Legal Aid and Information Centre in Kirkuk

Kurdish Human Rights Watch (KHRW): under UNHCR contract.

The criteria for the selection of these partners were based on their level of knowledge of communities, nature of displacement, previous experiences with monitoring, surveying and holding community meetings as well as experience with conflict transformation activities in the Iraqi context and/or in other contexts. Selection of UNOPS implementing partners is based on competitive procurement processes in line with UNOPS Standard Operating Procedures.

Insecurity is a significant concern in the implementation of all programmes in the Centre and South of Iraq, and to a lesser degree in the three Northern KRG Governorates. To address operational safety and security restrictions in the Iraq context, UNOPS and UNHCR have developed an extensive network of in-country partners with strong track records in efficient and accountable delivery through mechanisms attuned to the security situation, through which the agencies have implemented activities with strong monitoring, evaluation and support for several years.

NGO partners maintain a low profile for security reasons, and are familiar with targeted communities through extended cooperation on activities including monitoring along with emergency and development support. The trust relationship usually allows NGOs to benefit from protection of the communities, from information sharing through early warning to actual physical protection.

In the absence of international staff or limited movement of international staff in the north the following monitoring mechanisms have been adopted by UNHCR to ensure full transparency and project delivery in accordance with the established objectives, outputs and indicators of the project:

- Partners are required to submit a monthly progress report on implemented activities, accompanied by photos, if relevant, to UNHCR.

- Financial reports are submitted on a bimonthly or quarterly basis with supporting documents to ensure verification of expenditures. Supporting documents are closely scrutinized individually by UNHCR staff.

- Security permitting, UNHCR national staff responsible for monitoring projects undertake field visits to project sites and obtain information from municipal authorities and other actors regarding the implemented activities, which is reported to UNHCR Amman and CBB-K.

- Sub-agreements upon completion of activities have to be scrutinised by an independent audit company.

- UNHCR has established a peer monitoring system whereby NGOs monitor each other’s progress of project activities regularly.

UNOPS monitors and evaluates project implementation through the following mechanisms:

  - UNOPS implementing partner for the IDP Intentions Survey, and those for the Conflict Management sub projects are required to submit interim progress reports and final reports on implemented activities.

  - Interim and final financial reports are required to be submitted, along with supporting documents to ensure verification of expenditures.

  - All data collected during the survey will be transferred to UNHCR for inclusion in the National Survey.

  - The service provider contracted to undertake the capacity building for KRG will be subject to similar reporting requirements.

  - All institutions engaged by UNOPS are selected through a competitive procurement process in line with UNOPS standard operating procedures.

  - Security permitting, UNOPS national staff will undertake field visits to project sites and obtain information from municipal authorities and other actors regarding the implementation of the survey.

  - All projects implemented by UNOPS are periodically subject to internal and external auditing.

- Resources

Financial Resources:

  - Provide total funds provided, disbursed and committed

Funds

The total fund provided by UNDG Iraq Trust Fund was: 1,535,135 US$. .

Amount disbursed as at December 2007: UNHCR: US$ 793,172 + UNOPS US$ 99,488.

Amount committed as at December 2007: UNHCR: US$ 793,172 + UNOPS US$ 141,488.

Amount still available to project as at 31 December 2007: (Non-disbursed):  UNHCR: 141,319 US$ + UNOPS US$ 501,157.

  - Variation(s) in projected versus actual spending for the reporting period indicating the reason for such variation(s).

- Publication of IDP Intentions Survey and Consultations reports was delayed: Cluster F regarded more useful to publish the IDP Intentions Survey on the whole country and the completion of this took longer than expected.

- Drafting of the National Policy was slower than expected because of the logistical difficulties due to the worsening security situation which impacted on the ability of meeting the different stakeholders. A draft version of the National Policy was discussed with relevant central and regional authorities and medications were made to reflect these discussions. The Policy was translated into Arabic and was awaiting further feedback or endorsement from MoDM and KRG authorities by end December 2007.

- As the organisation of the National Conference is dependent on a final draft of the National Policy on Internal Displacement, the event had been delayed.

- Conflict transformation projects were delayed due to the security situation but are being currently implemented.

- Capacity building activities with KRG were delayed by the lack of a defined focal point within the Ministry responsible for matters pertaining to displacement but the procurement process is ongoing and contractual engagement is expected at the beginning of January 2008

  - Programme/Project expenditures within the 10 budget categories, including security expenditures.

Use of funds (disbursement) as at 31 December 2007

Personnel: 159,071 US$

This includes costs for 12 months of a national Programme Assistant and 50% of an International Protection Officer supervising and coordinating projects from Amman as well as partial payment or the UNOPS Project manager

Contracts: 628,959 US$

Include costs of 12 months returnee monitoring and drafting of 2 Governorate Assessment Reports on Baghdad and Diyala, 12 months operation of a Legal Aid and Information Centre in Kirkuk, carrying out an IDP Intentions Survey in the three Northern Governorates including hiring of 2 project consultants, data collection, design of a data base and data entry and analysis, and drafting of a report, workshop and missions for the development of the National Policy on Internal Displacement  (before Policy Framework on Displacement Challenges in Iraq) and translation of relative documents. Two NGOs have been contracted by UNOPS (through a competitive procurement process) to undertake the Conflict Management /Income Generation sub-projects.

Training: 0

Transport: 0

Supplies: 0

Equipment: 0

Travel: 13,242 US$

Includes travel of UNOPS staff to Erbil to supervise and coordinate activities for the IDP intention survey.

Miscellaneous: 10,000- the miscellaneous budget line is being used to supplement the travel expenditure due to the project prolongation.

Security: 24,759

Agency management Support: UNHCR: 51,890 US$+ UNOPS US$ 4,738.

  - Indicate other funding sources, if applicable.

Other funding sources available to the project

The project was kick-started already in January 2006 with funds from other donors to carry out grassroots consultations for the National Policy on Internal Displacement and to start returnee monitoring and the PACS/LAIC in Kirkuk. In addition, IOM was funding the IDP Intentions Survey in 15 Southern and Central Governorates.

For 2007 and 2008, UNHCR own funding covered the cost of staff managing the project from Amman. For 2007, UNOPS Project Manager was funded by other projects in which she had a managerial role. For 2008, UNOPS Project Manager will be partially funded from this project (25%) and 75% from other projects.

  - Provide details on any budget revisions approved by the UNDG ITF Steering Committee, if applicable

A budget revision requesting a no-cost extension (up to end June 2008) was submitted to SCSO on 17 July 2007, re-submitted then in December 2007 and in March 2008 (up to December 2008). This is due to the delays imposed on the project by external circumstances (changes in the KRG administration, need to finalise the National Policy prior to organising the National Conference, agreement on the part of MoDM to organise a National Conference). In addition UNOPS requested the movement of funds between budget lines to ensure on-going project management (at a level of 25%) for the extended period of implementation. Approval is pending.

  - Project expenditures for the 1 January to 31 December 2008 period

Main areas of expenditure planned for January to December 2008

Personnel

Staffing costs for short-term national and international support staff for the National Conference (UNOPS US$ 6,000). Payment of part time support staff to monitor implementation of Conflict Transformation grants (UNOPS US$ 1,500).

Partial payment of international project manager (25%) for the period required to complete UNOPS activities (US$ 23,793)

Contracts

- Organization of the National Conference on Internal Displacement. UNOPS US$ 203,800

- Public Information Campaign on the National Policy  (UNOPS 88,000)

- Workshops and mission on further refinement of National Policy and consultations on its implementation (UNHCR: 86,107 US$)

- Translation and publication of reports on IDP Intentions Survey and Consultations with displaced-affected communities (UNHCR: US$ 45,967)

- Implementing partners’ projects on conflict management linked to income generation (UNOPS: US$ 40,000)

- Capacity building for KRG institution responsible for displacement issues (UNOPS: US$ 75,000)

Human Resources:

  - National Staff: The number and type (operation/programme)

The project covers the following staff:

National:

-1 Programme Assistant in Amman (UNHCR, G6) for 12 months (50%) until 30 June 2007.

-3 support staff (UNOPS) for National Conference (2 staff for one month) and conflict transformation activities (1 staff at 50% for 4 months).

  - International Staff: The number and type (operation/programme)

The project covers the following staff:

International:

- 1 Protection Officer in Amman (UNHCR, P3) for 12 months (50%) until 30 June 2007.

- 1 Project Manager in Amman (UNOPS) for 5 months, February to June 2007 (100%) US$ 43,250) and for 10 months in 2008 (25%) USD 23,793.

- Methods of Operating

  - Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

Most activities are implemented by UNHCR Implementing Partners through their national staff in the centre and south. The NGOs keep a low profile for security reasons.

The drafting of the National Policy was carried out through different modalities, ranging from video-conferences with authorities to Inter-Ministerial workshops in Amman, email correspondence, telephone calls and UNHCR missions to Iraq. The results of the consultations with IDPs and their communities as well as the IDP Intentions Survey were taken as the basis for the drafting of the National Policy.

UNHCR relies on international and national as well as other local capacities. A Conflict Management Centre in Baghdad was the main implementing partner for the conflict management component of the project.

  - Provide details on the procurement procedures utilized and explain variances in standard procedures.

- Contract with COOPI for the IDP Intentions Survey in the three Northern Governorates – the selection process was a Request for Proposal (RFP) sent to a shortlist of NGOs with the relevant expertise and presence in the region. An evaluation was carried out by a committee and the selection was based on a technical proposal submitted

- Contract for UNOPS Conflict Management pilot activities – UNOPS held a meeting with interested national and international NGOs in Erbil to explain the concept. Attendees were asked whether they were interested in participating and those who replied positively were included in the circulated RFP. In addition to terms of reference, NGOs were provided with guidelines on similar coexistence projects and on conflict management. The selection was carried out by a team of UNOPS and UNHCR; the NGOs were contracted by concluding a Memorandum of Agreement, and they were selected based on the technical proposal submitted.

- Contract for UNOPS Capacity Building activities with the MoERA office for Displacement - the selection of a service provider was also based on an RFP. Similarly, UNOPS contacted NGOs and consultancies with the requisite capacities and based on their positive responses circulated an RFP. The selection was based on technical proposals which conformed to the concept expressed in the ToR and also on cost effectiveness.

- No variance in standard procedures for UNHCR

  - Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

UNHCR project monitoring mechanisms include the following:

- UNHCR implementing partners are required to submit a monthly progress report on implemented activities, accompanied by photos, if relevant, to UNHCR on the 4th day of each month. Information on progress is consolidated in one master progress report to assist programme staff in tracking implementation according to sub-agreements.

- The financial reports are submitted on a bimonthly or quarterly basis with supporting documents to ensure verification of expenditures. Supporting documents are closely scrutinized individually by UNHCR staff. Any deviation from UNHCR standards is noted in a “note for file” and the IP is notified in order to rectify the situation.

- Security permitting, UNHCR national staff responsible for monitoring projects are to undertake field visits to project sites and obtain information from municipal authorities and other actors regarding the IP-implemented activities, which is reported to UNHCR Amman and CBB-K.

- Sub-agreements upon completion of activities have to be scrutinised by an independent audit company.

- Like all other UN Agencies, all projects implemented by UNHCR are periodically subject to internal and external auditing.

UNHCR implementing partners must maintain separate project records and accounts containing current information and documentation which shall comprise:

- Copies of the Agreement(s) and all revisions thereto;

- Payment vouchers, clearly showing the Sub-Project symbol, the name of the payee, the amount, the purpose and date of disbursement, evidencing all payments made and with all pertinent supporting documentation attached;

- Vouchers evidencing the receipt of all remittances, cash or any other form of credit to the Sub-Project account;

- Periodic analyses of actual expenditure against the Sub-Project budget;

- Records of all financial commitments entered into during the duration of the Sub-Project;

- Reports by auditors on the accounts and activities of the Sub-Project.

Implementing partners are also required to maintain as part of the project records:

- A general ledger accounting system;

- Bank statements and reconciliations;

- Cash book(s);

- Separate accounts of sales and taxes incurred on domestic purchases;

- Planned staffing tables showing actual staffing;

- Complete purchase order file including; tender documents, offers, bid tabulation, evaluation, shipping/insurance inspection document, invoices and receiving reports;

- Inventories of assets and stock (food and non-food items);

- Employment contracts; and

- Building and construction contracts and subcontracts.

UNHCR IP procurement guidelines are available upon request.

  - Report on any assessments, evaluations or studies undertaken.

LAIC/PAC reports have been produced; evaluations and reports on conflict management activities are not available at this stage, but they will be available when the projects are finalized; the Reports on the Consultations will be available at the beginning of April and the IDP Intentions Survey will be available a few weeks later.

- Results

  - Summary of programme/project progress in relation to planned outcomes and outputs; explain any variance in achieved versus planned outputs during the six month reporting period.

June – December 2006

Project implementation went smoothly and according to plan with the exception of the capacity building for the KRG RIMC (see below under lessons learned). In the course of the first six-month reporting period of the project, information on displaced groups were gathered countrywide, whereby UNHCR, through a UNOPS contract with COOPI, collected information on the three Northern Governorates and IOM for the 15 Central and Southern Governorates. The information was analyzed and entered into a central database. The process of publishing the results in a joint report and sharing them with the authorities in the North was under way.

Activities to provide on-the-job training to the KRG authorities in monitoring persons of concern (IDPs, returnees, refugees) and sharing information had to be deferred to 2007 due to structural changes and turn-over of staff in the KRG.

Cluster F, MoDM and KRG jointly developed the concept underlying the National Policy on Internal Displacement, enhancing the authorities' ownership of the process. Nationwide grassroots consultations were conducted in 18 governorates, complemented by awareness-raising on IDP rights. It was envisaged to publish the expressed needs, challenges and actions to be taken to pursue their durable solutions in March 2007.

A core group to develop the structure and coverage of the National Policy was established in MoDM and was expected to closely liaise with the different line Ministries, the PM Office, Cluster F and other stakeholders to start the drafting process in 2007. In light of the post-Samarra displacement, it was agreed that the National Policy will also focus on emergency interventions.

Monitoring of persons of concern (returnees and IDPs) took place in Baghdad and Diyala Governorates. The results were entered into a central database and Governorate assessment reports drafted and published for Diyala and drafted for Baghdad. Needs were assessed in 82 locations in Diyala Governorate and 36 locations in Baghdad Governorate. In addition, 355 households were monitored.

The independent PAC/LAIC in Kirkuk and mobile teams were strengthened, expanded and further operationalized, providing professional and unbiased services in line with local communities’ needs. More that 3,000 persons benefited from the services of the PAC.

January- June 2007

An initial draft of the National Policy was developed on the basis of issues identified during the consultations with IDPs and their communities, as well as with concerned Governmental Officials, line Ministries of GoI and KRG. The draft will then be subject to further discussions with MoDM, KRG-relevant authorities before being submitted for adoption.

The delay in endorsing the National Policy and also the prevailing security situation made it inevitable to postpone the National Conference on International Displacement (National Conference) to 2008. This Conference will provide a forum for consultations and negotiations between central, regional and local authorities along with civil society actors.

Activities to provide on-the-job training to the KRG authorities in monitoring persons of concern (IDPs, returnees, refugees) and sharing information was further deferred to the second half of 2007 due to initial lack of a focal point for displacement issues in the KRG, and later a need to redefine the scope of the training following the establishment of a new department within the Ministry having overall responsibility for displacement in the KRG-administered areas.

Two areas were identified in Baghdad (Noor Al Huda, Khathra) where coexistence between IDPs and host communities was characterized by latent conflict, caused by scarcity of resources, lack of trust and mutual suspicions. Training on conflict transformation for IDP and host communities’ leaders was implemented.  Field visits were carried out, in order to select beneficiaries and evaluate business proposals. Grants will be disbursed and the selected business proposals will be implemented during the second half of 2007. Two more projects were envisaged to be carried out in the second part of the year in two communities in Northern Iraq (Kirkuk, Ninewa, Dahuk, Erbil and Sulaymaniyah). UNOPS scheduled a meeting in early July to discuss the concept with NGOs and planed to select two NGOs to carry out similar projects based on a competitive procurement process.

July- December 2007

Conflict Transformation activities were successfully implemented in Baghdad and reports were provided.

## NGOs were selected and engaged by UNOPS to undertake replica activities in Northern Iraq and by end December, the sub-projects were midway to completion concerning the conflict management activities and selection of beneficiaries for the Income Generation was on-going

## In November, agreement from the Directorate of Displacement (KRG) on the modality for capacity building activities was received and subsequently potential service providers were identified. UNOPS selected one consultancy and contractual engagement will be in early 2008.

Report on Consultations was finalized and sent for printing.

The draft of the National Policy on Internal Displacement was discussed with relevant central and regional authorities and modifications were made to reflect these discussion. The draft was translated into Arabic and by end 2007, UNHCR expected further feedback or endorsement from MoDM and KRG authorities.

  - Progress made towards the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period.

## Main activities undertaken and achieved:

Output1 – IDP Intentions Survey:

- IDP Intentions Survey carried out.

- KRG authorities received data on intentions of IDPs in Kurdish Regional Area.

- Survey data of 3 Northern Governorates s is included in nation-wide survey.

- Database with relevant information from grassroots consultations established.

- Reports on outcomes of consultations on displacement challenges with stakeholders on grassroots level held in Iraq drafted and translated.

- National Conference Core Group established within MoDM.

- Draft of National Policy on Internal Displacement finalized and submitted to relevant authorities for further feedback. The draft includes necessary modifications to the initial structure due to the new displacement situation in Iraq. The feedback from relevant authorities was received and incorporated in the 2nd draft. The latest draft was translated into Arabic and is currently under discussion with MoDM and relevant KRG authorities.

Output 2 – National Conference

- Since the organization of the National Conference depends on the endorsement of the National Policy by the authorities (MoDM and KRG), this activity will be carried out during 2008.

Output 3 – KRG structures

The planned training on monitoring and data analysis for the RIMC to be undertaken by UNOPS has not been carried out for the following reasons

  - RIMC –the institution which formerly monitored the IDP situation in the 3 Northern Governorates has been transferred to the Ministry of Planning and no longer is involved in IDP monitoring

  - There has been a long delay in the identification of the new focal points for displacement issues in the KRG

However progress was made and in a meeting with MoERA approval from the Ministry was given for UNOPS to prepare for such capacity building activities. Subsequently the Directorate of Displacement approved the proposed modality for the capacity building, and in line with this terms of reference were drafted and a procurement process was undertaken. Selection took place at the end of December and the selected consultancy will be engaged to start the activities in 2008

Output 4 – Governorate Assessment reports and monitoring

- New returnee sites visited and registered and monthly visits to old/registered returnee sites in Baghdad and Diyala carried out and findings entered into database.

- Monthly narrative and statistical reports on conditions of returnees produced and sent to UNHCR. Governorate Assessment reports drafted and published on Diyala and one drafted for Baghdad.

- Identified needs of monitored populations included in projects of UNHCR in 2007.

Output 5 – Protection and Assistance Centers

- Staff selected and hired; office and 3 out reach teams established. Daily visits to IDP communities and other communities by reach out teams. Provision of free of charge legal advice and representation for 600 beneficiaries (75% were IDP returnees, 20% new IDPs) as well as provision of information on their rights for some 2,500 IDPs (125 IDP locations) through mobile times.

- PACs staff visited women jail in Kirkuk to speed up trials.

- Visits to authorities, to facilitate access of clients and other IDPs to public services.

- Adult literacy classes for IDP women (50) and support of Qara Hanjeer Women Centre in Kirkuk carried out.

Output 6 – Conflict transformation

UNHCR

- Two out of four areas identified.

- Training on conflict transformation for IDP and host communities’ leaders implemented.

- Field visits for selection of beneficiaries carried out

- Business proposals evaluated.

- Grant distributed and business started.

- Project finalized and reports received.

UNOPS

- Terms of reference for the Conflict management projects in the KRG area have been developed (UNOPS).

- A meeting with potential implementing partners took place in July, and following this a procurement exercise was undertaken to identify two partner NGOs. The two organizations were engaged by UNOPS in October and the activities are now midway to completion.

  - Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries by end 2007.

| Output | Events/Activities | Completion | Beneficiaries |
| --- | --- | --- | --- |
| Draft Policy Framework on Displacement Challenges and Durable Solutions (now: National Policy on Internal Displacement) | - Survey on IDP intentions carried out in 3 Northern Governorates - Reports on IDP intentions drafted - Database to analyze outcomes and draft reports on findings from grassroots consultations in the process of being developed - Translation of reports in English and Arabic finalized - Core Group to draft National Policy formed in MoDM - Initial Draft of National Policy developed, submitted to concerned ministries for further consultations -Second draft submitted to authorities and further feedback received | 100% 85% 100% 75% 100% 100% 100% | 1,233 IDP families in Northern Governorates MoDM and KRG |
| National Conference on Displacement Challenges and Durable Solutions | - Preparatory activities underway - Conference postponed to May 2008 | 5% | ------- |
| KRG relevant authorities collect and analyze the protection and assistance needs and gaps of IDPs and their host communities | A meeting was held with MoERA to request clarification on the institution responsible for monitoring displacement, and latterly with the Directorate of Displacement. With their agreement a procurement process to identify the service provider has been undertaken and activities are scheduled to begin in early 2008 | 25% | ----------- |
| Legal Aid and Counselling provided to IDPs, returnees and refugees in Kirkuk | - Continuous training of lawyers and information officers in Kirkuk PAC and its mobile team took place as well as 3 training sessions together with other PAC in Iraq. - PAC team provided free legal advice to 600 clients (opened cases of which 75% were IDP returnees and 20% IDPs) and legal information to 580 beneficiaries (walk-in clients without cases) and free legal representation in 20 select cases, awareness raising on issues relating to the rights of IDPs (2500 IDPs in 125 IDP locations visited by mobile team) -Cases solved reached more than 60% and related mainly to property issues (35%), access to health care (5%), employment (5%) and social welfare services (40%), food rations (3%) and utilities (15%) such as electricity and water. | 100% | - 600 IDPs, returnees and refugees and local community members (direct clients) - 2,500 IDPs (information dissemination) |
| Governorate Assessment Reports for Diyala and Baghdad | - Monitoring teams collected and analyzed data on the protection and assistance needs of 355 IDP and returnee families and host communities (of which 90% were IDP returnees and 10% refugee returnees) and entered them into a database. - Through research and information-gathering, produce - Governorate Assessment Reports for Diyala and Baghdad drafted and disseminated to persons of concern inside and out of Iraq, host governments, UN agencies and NGOs active in the Iraq context. | 95% | - 355 IDP and refugee returnees |
| Income Generation and Conflict Transformation | - Areas of intervention identified, conflict management workshops and income generation activities designed. - Two of the four projects implemented and reported. - Partners to implement replica projects in the North of Iraq were identified through a competitive process and are now midway through their activities. | 75% | UNHCR: * 984 individuals for training * 57 families for income generation grants * 300 individuals are indirect beneficiaries (estimating 6 persons per family) UNOPS: 82 individuals for training |

  - Relevant Delays in Programme/Project Implementation: Nature of the constraints, lessons learned in the process and actions taken to mitigate future delays.

Security remained one of the main challenges in the implementation of the projects imposing restrictions of access to project areas for UN staff and staff of implementing partners. As this was anticipated, it posed only minor constraints in the carrying out of planned activities: visits of monitoring teams had to be postponed, the PAC mobile teams had to adapt their schedule of site visits according to the security in the target area and teams carrying out the IDP Intentions Survey were observant of security restrictions as well. Generally, partner NGOs kept a low profile and obtained information on the security situation through their own networks so as not to endanger any staff. This proves that the measures taken by partners and the UN system are efficient.

Another obstacle to achieving one of the planned outputs was due to the merger of the two Kurdish Administrations in February 2006. The ministries previously responsible for displacement issues were dissolved, and the institution planned to benefit from the capacity building was transferred to the Ministry of Planning. Only in 2007 was it announced that the Ministry of Region for Extra-Regional Affairs would undertake the monitoring of, and assistance to the displaced. UNOPS requested a meeting with the Minister and gained his approval to conduct some capacity building activities. He agreed that a new Committee with responsibility for displacement would be created and following the establishment of this department UNOPS has made contact with the Director.

UNOPS sourced possible service providers to implement the activity. A procurement process was undertaken and a local consultancy was selected. Contractual engagement will see the start of activities in early 2008.

Another important lesson learnt during the first 18 months of the project relates to the need of increased participation of central government counterparts of MoDM in drafting the National Policy. MoDM has been more active in the past 6 months and feedback on the first draft was provided.

By end 2007, the relevant authorities were not able to set a date for the National Conference on Internal Displacement, and therefore the conference has been tentatively postponed to May 2008. The date must be decided by the relevant central authorities in agreement with the regional authorities; it remains to be seen whether the holding of the Conference needs to be further postponed to the second half of 2008.

No project evaluation has taken place so far as projects will be evaluated only after completion. UNHCR has designed an NGO peer monitoring and evaluation system and is in the process of training NGOs. It will be used upon finalization of the project.

  - List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

The project is being jointly carried out by UNHCR and UNOPS, who are implementing activities in close coordination with one another.

UN Agencies, which are also in Cluster F (and IDP WG), are actively involved in consultations on all project stages that pertain to the development of the National Policy on Internal Displacement. Other Cluster F agencies contributed directly to the National Policy through sectoral expertise or targeted activities (e.g. IOM carried out the IDP Intentions Survey in fifteen Central and Southern Governorates). Cluster F members, such as UNICEF, UN-HABITAT, the IDP Working Group and UNIFEM provided inputs to the design of the process, including feedback related to the activities of their respective counterpart ministries. UNHCR and UNOPS will maintain close consultations, reporting and information-sharing throughout the process.

The project has been developed and is implemented in close cooperation and coordination with the existing ministerial structures (MoDM and KRG), builds on their existing capacity and envisages to strengthen coordination between central and regional structures.

MoDM and relevant KRG ministries are among UNHCR’s and UNOPS’s counterparts in Iraq, and the support provided by the agencies in the course of implementation will significantly build their capacities, including on-the-job training.

The role of MoDM as a Ministry capable of coordinating the work of and liaising with other Ministries will be strengthened, particularly its capacity to develop effective and comprehensive policies for the benefit of the populations of concern.

Through interventions such as trainings and workshops on human rights, the PAC contributed to the capacity of MoDM Branch Office and local authorities to assist persons of concern. Transparency and accountability was increased through effective monitoring and interventions. Activities were closely coordinated with IOM to avoid duplication.

  - Summary achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

Security:

To address operational safety and security restrictions in the Iraq context, UNOPS and UNHCR developed an extensive network of in-country partners with strong track records in efficient and accountable delivery through mechanisms attuned to the security situation, through which the agencies implemented activities with strong monitoring, evaluation and support for several years.

NGO partners maintained a low profile for security reasons, and were familiar with targeted communities through extended cooperation on activities including monitoring along with emergency and development support. The trust relationship usually allowed NGOs to benefit from protection of the communities, from information sharing through early warning to actual physical protection.

Gender:

Though the Project took into consideration the needs of all displaced persons, specific attention was accorded to women and children in displacement through actively supporting their involvement in all stages of the process; i.e. women, youth and men expressed their needs, challenges, preferred options and solutions in grassroots consultations that were incorporated into the Draft National Policy on Internal Displacement.

The PAC teams consisted of male and female lawyers so as to enable and encourage women to approach the PAC. All PAC staff attended trainings which included how to address gender issues and on how to deal with cases of sexual and gender based violence, trafficking and early marriage. PAC mobile teams paid special attention to disseminate information to female IDPs and collecting information on their needs. Subsequently, the PACs offered literacy classes for female IDPs and supported the opening of a women’s centre in Kirkuk which focused on providing skills training for IDP women.

The returnee monitoring teams focused on collecting information on the situation and needs of female returnees. This information was reflected in the Governorate assessment reports enabling potential women IDPs to make an informed decision about returning to these areas in Iraq. UNHCR’s 2007 projects were partly based on the observations of the monitoring teams and addressed especially the needs of women and children.

Human Rights:

The design and planning of the projects took into consideration the principles and standards of the international human rights instruments. Staff of the PAC received training in international human rights standards and how to address violations of human rights. Dissemination campaigns to IDPs carried out by the PAC included information on basic human rights of the IDPs and how to realize them in the current context.

The development of the National Policy on Internal Displacement aims at enabling the Government to accord full human rights to all displaced populations in Iraq. In order to fulfill this, authorities were also made aware of human rights standards.

Monitoring and the IDP Intentions Survey focused on the situation of IDPs with regards to the realization of their human rights. Questionnaires were designed around basic human rights principles.

Employment:

Short-term professional job opportunities were generated during the interviews of the IDP Intentions Survey; approximately 20 staff.

PACS are designed to continue as independent structures to serve people of concern beyond the duration of this project, and employ fully Iraqi staff (currently 14 staff) in a professional services capacity. The Centres are being trained on means to attain financial self-sufficiency, toward fulfilment of their role in an independent Iraqi civil society.

Environment:

The project did not have a direct environmental impact during its implementation. However, technical expertise was sought to ensure that environmental concerns are adequately addressed within the National Policy, particularly through cooperation with the Ministry of Environment.

- Future Work Plan

  - Summarize the projected activities up to the end of December 2008.

- Capacity Building with KRG – following endorsement from MoERA on the proposed capacity building modality UNOPS issued an RFP to identify and select a service provider. Experts will be seconded to the departments of the Directorate of Displacement to mentor the newly appointed staff there – and the activities will last for five months and should include all DDM offices

- Conflict Management pilot projects – UNOPS disseminated an RFP to NGOs having expressed interest in implementing pilot projects. Two project proposals deemed to meet the ToR were selected and activities are due to be completed by end February 2008 with a final report which will determine impact on both displaced and host communities

- National Conference – due to circumstances external to UNOPS and UNHCR the National Conference was deferred until 2008 – at this stage, the Conference is tentatively scheduled for May 2008.

- Drafting National Policy: a second draft was finalized and shared with relevant stakeholders; UNHCR will assist MoDM and KRG to further refine the Policy in light of their comments.

- Report on Consultations published by beginning of April 2008; Report on IDP Intentions Survey will be finalized at the beginning of May 2008.

# Text boxes

Report Formatting Instructions: We kindly ask that you review the instructions below and follow them in the preparation of your report:

- Do not put the narrative text into boxes as was done in the previous report and do not incorporate boxes, graphs, etc into the narrative report.

- Add additional information including charts, graphs, etc as annexes to the report and clearly reference the annexes using footnotes or endnotes within the body of the narrative

- Number all sections and paragraphs as indicated below

- Format the entire document using the following font: 12point _ Times New Roman & do not use colours.