LEBANON RECOVERY FUND

ANNUAL project NARRATIVE progress report

# REPORT COVER PAGE

| Participating UN Organization: |  | Report Number: |
| --- | --- | --- |
| UNDP |  | 2 |

| LRF Project No: New Atlas Project No: (as per enclosed list) 65541 65550 65556 |  | LRF Project Title: |
| --- | --- | --- |
|  |  | Country energy efficiency and renewable energy demonstration project for the recovery of Lebanon (CEDRO) |

| Reporting Period: |  | Project Budget: |
| --- | --- | --- |
| 1 January to 31 December 2008 |  | LRF-funding: Phase 1: $2.73 million Phase 2: $3.50 million Phase 3: $3.50 million Other funding: N/A |

| List Implementing Partners: |  | Project Coverage/Scope: |
| --- | --- | --- |
| International Partners: Spanish Agency for International cooperation National Partners: Council for Development and Reconstruction; Ministry of Energy and Water; Ministry of Finance, Ministry of Interior and Municipalities |  | CEDRO 1: South, Bekaa and Aakkar CEDRO 2: National coverage CEDRO 3: National coverage |

| Abbreviations and acronyms: |  | Project Duration/Closed Project: |
| --- | --- | --- |
| CEDRO: Community energy efficiency and renewable energy demonstration project for the recovery of Lebanon CO: Country Office DEX: Direct Execution LCECP: Lebanese center for energy conservation project LRF: Lebanon Recovery Fund PMU: Project Management Unit UNDP: United Nations Development Programme. |  | CEDRO 1: Oct 2007 – Jun 2009 CEDRO 2: Jan 2009 – Jan 2011 CEDRO 3: Jan 2010 – Oct 2012 |

REPORT FORMATTING INSTRUCTIONS Kindly review the instructions below and follow them in the preparation of your report: Do not put the narrative text into boxes and do not incorporate boxes, graphs, etc into the narrative report. Add additional information including charts, graphs, etc. as annexes to the report and clearly reference the annexes using footnotes or endnotes within the body of the narrative. Number all sections and paragraphs as indicated below. Format the entire document using the following font: 12-point Times New Roman and do not use colours.

# NARRATIVE REPORT FORMAT

# Purpose

  - Lebanon imports around 97% of its energy needs in the form of fossil fuel. In 2004, the national energy bill amounted to around 1.6 billion USD (around 20% of the annual public expenditure), and in 2005 it reached 2.1 billion USD (around 26% of the annual public expenditure). Despite major steps taken by the Government of Lebanon since 1990 towards improving the electricity sector, the sector is still facing major challenges including inability to meet increasing national energy demand and large financial subsidies for Electricite du Liban (around 1.0 billion USD in 2006).

  - As a result of the July 2006 conflict, the situation of the energy sector in Lebanon was further aggravated, resulting in a reduction in electricity supply on a national level and an increase in electricity rationing.  This only added to the existing electricity supply challenges faced by Lebanon and further deteriorated the living conditions in the country.

  - In light of this draining situation, the government of Lebanon has placed the reform of the power sector among its highest national priorities, as outlined in the recovery, reconstruction and reform paper submitted at the Paris 3 conference. However, given the enormity of the challenges faced by the power sector, the reform strategy has concentrated on addressing the energy supply side, without extending the scope to the demand side of energy management. The proposed CEDRO project aims at complementing the national power sector reform strategy by targeting the necessary counterpart and that is end-use energy conservation.

As such, the objective of the CEDRO project is to support recovery, reconstruction and reform activities through the implementation of an energy efficiency and renewable energy program for public sector buildings and facilities. To achieve this, the first phase of the CEDRO project (Oct 2007 – Mar 2009) will target around 50 to 60 public sector buildings and facilities in three recovery areas (South, Bekaa and Akkar) highly affected by the July 2006 conflict, and the second phase of the CEDRO project (Jan 2009 – Jan 2011) will target around 60 to 70 public sector buildings and facilities across Lebanon. Furthermore, the second phase of the CEDRO project will also involve the setting of an enabling environment for the conversion of all public sector buildings and facilities into energy efficient modalities.  The third phase of the CEDRO project (Jan 2009 – Jan 2011) further supplements the aforementioned two CEDRO objectives, by a third key objective which is the setting of an enabling environment for the development and implementation of a national sustainable energy strategy and detailed action plan. The third phase of the CEDRO project is the final key component to enable sustainability and a nationwide multi-sectoral scope.

  - The key outputs of the CEDRO project include: 1) installation of energy efficiency and renewable energy equipments and systems in public sector buildings and facilities; 2) increased public sector awareness and knowledge on energy efficiency and renewable energy applications; 3) availability of validated data on reduced energy consumption and cost; and 4) establishment of relevant policies and procedures to enable the continued implementation of sustainable energy measures in public sector buildings and facilities.

  - The CEDRO project builds on the objectives of the Ministry of Energy and Water to meet increased national energy demand, and the objectives of the Ministry of Finance to reduce government financial burdens.

  - The project’s main national implementing partners are: the Council for Development and Reconstruction, the Ministry of Energy and Water, and the Ministry of Finance, who are parties to the project formulation and approval, as well as parties to strategic decision making and evaluation throughout the project lifetime.

- Resources

Financial Resources:

  - The Lebanese Centre for Energy Conservation project (LCECP), which is a UNDP nationally executed project executed by the Ministry of Energy and Water, has committed an in-kind contribution to the CEDRO project, in the range of 78,000 USD.

  - No budget revisions were undertaken.

Human Resources:

  - National Project Staff:

- Project Manager (x1)

- Research Assistant (x1)

- Site Engineers (x3)

- Driver/clerk (x1)

  - International Staff: None

- Implementation and Monitoring Arrangements

  - The Project is executed under the UNDP Direct Execution modality (DEX), whereby UNDP acts both as the implementing and the executing agency. For the day-to-day management of the project, the UNDP CO has set-up a Project Management Unit (PMU). The PMU works under the direct supervision of the UNDP CO, and in close collaboration with the donor, the Lebanese Government, the local direct and indirect beneficiaries, as well as with the international team of experts and the local contractors recruited for this project. The PMU is led by a full time national Project Manager and is supported by the required national professional and administrative staff as well as national and international consultants.

  - The UNDP CO is responsible for monitoring the progress towards intended results, and for ensuring high-quality managerial and financial implementation of the project, including the responsibility for ensuring proper use of administrated funds to assigned activities, timely reporting of progress, as well as undertaking of mandatory and non-mandatory evaluations.  The UNDP CO undertakes quarterly reports and reviews of the project activities, annual tripartite review meetings in addition to regular and bi-weekly follow-up with the PMU. Furthermore, the procurement of goods and services and the recruitment of personnel are effected in accordance with UNDP standard guidelines, procedures and regulations.

- Results

Programmatic and Reporting Approach

With the approval of the 3 phases of the CEDRO project (CEDRO 1, CEDRO 2 and CEDRO 3) CEDRO became part of a larger project framework which aims not only at supporting Lebanon’s recovery activities, but also at supporting Lebanon’s recovery, reconstruction and reform activities, namely the power sector recovery, reconstruction and reform plan.

As such, the overall CEDRO project (Country energy efficiency and renewable energy demonstration project for the recovery of Lebanon) now three objectives:

1) Implementation of end-use energy efficiency and renewable energy projects to reduce national energy consumption and costs

2) Setting an enabling environment for the conversion of all public sector buildings and facilities into energy efficient modalities

3) Setting an enabling environment for the development of a national sustainable energy strategy and action plan

The overall CEDRO programme, if defined as being composed of CEDRO 1 - 3 projects, has a total budget of over 9.7 million USD and and total time frame of over 5 years.  Accordingly, and based on a more programmatic approach, all future reporting will cover achievements and financial disbursements for both projects together as is presented here.

Furthermore, it must be noted that a strategic decision was taken to group target projects by technology in order to optimize cost. This would imply that the renewable energy projects under CEDRO 2 may be launched directly after the renewable energy projects of CEDRO 1 and before the energy efficiency projects of CEDRO 1; and the energy efficiency projects of CEDRO 1 and 2 could be launched together.  This optimises on resources and increases implementation efficiency.

Delays

  - Although the LRF project proposal and document were approved on 12 June 2007, the UNDP Project Document of the CEDRO 1 was not signed until 10 October 2007. As such, the actual start date of the CEDRO 1 activities was 10 October 2007.  On the other hand, although CEDRO 2 was approved on 10 October 2007, the expected start date is not until 01 January 2009; therefore CEDRO 2 will not be covered within this report.  Similarly, CEDRO 3 was approved by the LRF of 19 September 2008 but will not be initiated until January 2010.

CEDRO 1 experienced some delays related to two major issues: the technical backstopping agency and the security situation in Lebanon.  Initially, some delays were experienced in undertaking the necessary procurement clearances from UNDP headquarters for contracting the technical backstopping agency; later on during the year, additional delays were experienced in the delivery of the required technical tender documents for the procurement of equipment from the technical backstopping agency.  On the other hand, the security situation in Lebanon and related UN security requirements caused delay in identifying a project office that meets security standards while clearances for site visits and field missions of the international consultants had to be rescheduled many times as a result of the unstable security situation in the country.

Progress on Outputs

- Project Management

- Development of Project Documents and Proposals for CEDRO 1, and 2

- Set-up of Project office premises;

- Recruitment of Technical Backstopping Agency;

- Set up of project management unit ;

- Recruitment of project Staff

- Set up of Project Coordination Committee;

- Preparation of regular progress reports;

- Carry-out  project review meetings with the LRF Technical Committee (Feb 2008 and Jul 2008);

- Organization of field missions and stakeholder meetings;

- Implementation of end-use energy efficiency and renewable energy demonstration projects for public sector buildings and facilities

- Preparation of targeted assessment and identification of beneficiary sites including:

- Development of site identification strategy;

- Carrying out of detailed field visits and stakeholder meetings to assess the compatibility of potential building types with envisaged EE/RE applications;

- Analysis of site features and Identification of site selection filters and criteria;

- Development and posting of Needs Identification Form to assess the needs for EE/RE equipments and systems;

- Receipt of over 600 Forms and analysis of data including energy consumption data;

- Coordination with LCECP on ongoing energy audits;

- Carrying out of outreach and coordination including a project coordination committee meeting and one-on-one meetings

- Preparation of the related evaluation report

- Preparation of the final list of 60 beneficiary sites

- Development of Technical Specifications and Tender documents for the envisaged implementation sites, and launching of the bidding and procurement process for the supply and installation of EE/RE equipments/systems, including:

- Preparation and posting of an Expression of Interest (EOI); Evaluation of the received EOIs and announcement of the short-listed companies;

- Launching of a Request for Proposal (RFP) for the supply and installation of photovoltaic lighting systems;

- Launching of a Request for Proposal (RFP) for the supply and installation of solar water heater systems for 4 public hospitals;

- Setting an enabling environment for the conversion of public sector buildings and facilities into energy efficient modalities

- Development and dissemination of the first project brochure (English/Arabic) ;

- Arrangement of the official Project Signature event at the Council for Development & Reconstruction;

- Participation in the annual Energy Week at the Order of Engineers and Architects, Beirut (Outreach to around 150 engineers)

- Participation in the Omsar municipalities workshop at the Grand Serail (Outreach to around 200 municipalities);

- Identification of all  relevant project partners and potential members of the project steering committee followed by the organization of the CEDRO First Stakeholder meeting  (Outreach to around 100 stakeholders);

- Issuing of newspaper releases and magazine articles (national coverage);

- One-on-one consultation meetings with stakeholders and beneficiaries;

- Organization of the Project Coordination Committee meeting;

- Organization of press conference for the launch of the CEDRO implementation phase

- Networking and Coordination with national project partners and stakeholders such as the Lebanese Order of Engineers, Ministry of Energy and Water, Ministry of Public Works, etc.,

- Synergy with the on-going UNDP project at the Ministry of Energy and Water, Lebanese Centre for Energy Conservation project (LCECP), on ongoing energy audits and activities to build on the project’s technical know-how, experience on the ground, and lessons learnt during the implementation of energy efficiency and renewable energy activities.  This entails exchange of technical data and lessons learnt as well as brainstorming session to coordinate and maximise efforts for project implementation,

- Future Work Plan

Detailed future work plan for CEDRO 1 and 2 can be found in Annex 1.  Total expected budget for 2009 is 1.4 million USD.  In summary, for 2009 the project will:

- Award the Contracts for the tenders that were launched in 2009 which include the installation of Solar Water Heater and Energy Efficient appliances in over 30 sites;

- Monitor and supervise the installation and commissioning of these equipment in the different sites;

- Continue undertaking technical site assessments for the first batch of beneficiary sites;

- Accordingly develop new tender documents for the installation of additional renewable energy and energy efficiency technologies based on needs and technical criteria;

- Initiate a second round of call for beneficiaries in the target areas and undertake technical evaluations to short-list another 30 sites for this year;

- Launch a second international call for expression of interest for suppliers of renewable energy and energy efficiency equipment with technical and financial requirements based on the lessons learnt from the first round;

- Issue tender documents to the second round of pre-qualified firms;

- Undertake at least 5 technical training workshops, including the development of appropriate training material;

- Continue with awareness raising activities and material, including the launch of the project website;

- Initiate the establishment of a project database that integrates energy data from all national public facilities and is GIS based.

Given the time delays mentioned earlier, the CEDRO 1 will be extended to end on 31 December 2009 instead of in June 2009.

Annex 1 – Detailed Work Plan for 2009

| CEDRO 1 - 2009 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Expected Outputs | Planned Activities | Target Year | Status | Q1 | Q2 | Q3 | Q4 |
| Implementation of energy efficiency & renewable energy applications for public sector buildings & facilities (50-60 sites in South, Bekaa & Akkar) | 1 - Identification of pilot projects |  |  |  |  |  |  |
|  | 1.1 - Identification of Needs for EE/RE | 2008 | Complete |  |  |  |  |
|  | 1.2 - Identification of Technologies | 2008 | Complete |  |  |  |  |
|  | 1.3 - Identification of Beneficiary sites | 2008 | Complete |  |  |  |  |
|  | 1.4 - Preparation of Tender Documents | 2008/2009 | Complete |  |  |  |  |
|  | 2 - Implementation of pilot projects |  |  |  |  |  |  |
|  | 2.1 - Pre-qualification of firms | 2008 | Complete |  |  |  |  |
|  | 2.2 - Issuing of Request for Proposal | 2008/2009 | Ongoing | X | X |  |  |
|  | 2.3 - Commissioning & supervision of works | 2009 | Ongoing | X | X |  |  |
|  | 2.4 - Hand-over of Installations | 2009 | Planned |  | X |  |  |
|  | 3 - Capacity building & Info dissemination |  |  |  |  |  |  |
|  | 3.1 - Development of training material | 2008/2009 | Ongoing | X |  |  |  |
|  | 3.2 - Implementation of training workshops | 2008/2009 | Ongoing | X | X |  |  |
|  | 3.3 - Development of awareness tools | 2008/2009 | Ongoing | X |  |  |  |
|  | 3.4 - Dissemination of awareness material | 2008/2009 | Ongoing |  | X |  |  |
|  | 4 - Project validation and replication |  |  |  |  |  |  |
|  | 4.1 - Enabling project replication | 2008/2009 | Ongoing |  | X |  |  |
|  | 4.2 - Monitoring of site results | 2009 | Planned |  | X | X | X |
|  | 4.3 - External Project Evaluation | 2009 | Planned |  |  | X |  |
| CEDRO 2 - 2009 |  |  |  |  |  |  |  |
| Expected Outputs | Planned Activities | Target Year | Status | Q1 | Q2 | Q3 | Q4 |
| Implementation of energy efficiency & renewable energy applications for public sector buildings & facilities (60-80 sites across Lebanon) Setting an enabling environment for the conversion of public sector buildings and facilities into energy efficient modalities | 1 - Identification of pilot projects |  |  |  |  |  |  |
|  | 1.1 - Identification of Needs for EE/RE | 2009 | Planned | X | X |  |  |
|  | 1.2 - Identification of Technologies | 2009 | Planned | X | X |  |  |
|  | 1.3 - Identification of Beneficiary sites | 2009 | Planned | X | X |  |  |
|  | 1.4 - Preparation of Tender Documents | 2009 | Planned | X | X |  |  |
|  | 2 - Implementation of pilot projects |  |  |  |  |  |  |
|  | 2.1 - Pre-qualification of firms | 2009/2010 | Planned | X | X |  |  |
|  | 2.2 - Issuing of Request for Proposal | 2009/2010 | Planned |  | X |  |  |
|  | 2.3 - Commissioning & supervision of works | 2009/2010 | Planned |  |  | X | X |
|  | 2.4 - Hand-over of Installations | 2009/2010 | Planned |  |  |  | X |
|  | 3 - Establishment of data base |  |  |  |  |  |  |
|  | 3.1 - Collection of data on public facilities | 2009 | Planned | X | X |  |  |
|  | 3.2 - Set-up of GIS database | 2009 | Planned | X | X | X | X |
|  | 3.3 - Collection of data on energy savings | 2009 | Planned |  |  | X | X |
|  | 4 - Capacity Building & Info Dissemination |  |  |  |  |  |  |
|  | 4.1 - Development of training material | 2010 | Planned |  |  |  |  |
|  | 4.2 - Implementation of training workshops | 2010 | Planned |  |  |  |  |
|  | 4.3 - Development of awareness tools | 2010 | Planned |  |  |  |  |
|  | 4.4 - Dissemination of awareness material | 2010 | Planned |  |  |  |  |
|  | 5 - Establishment of policies / procedures |  |  |  |  |  |  |
|  | 5.1 - Development of procurement tools | 2010 | Planned |  |  |  |  |
|  | 5.2 - Proposal of O&M schemes | 2010 | Planned |  |  |  |  |
|  | 5.3 - Establishment of best practices | 2010 | Planned |  |  |  |  |
|  | 6 - Project validation and sustainability |  |  |  |  |  |  |
|  | 6.1 - Monitoring of site results | 2010/2011 | Planned |  |  |  |  |
|  | 6.2 - Development of sustainability plan | 2010/2011 | Planned |  |  |  |  |