THREE-MONTH PROGRESS REPORT

LEBANON RECOVERY FUND

Reporting UN Participating Organisation: FAO

### Country: Lebanon

### Project No. and Project Title:

LRF-4 OSRO/LEB/702/UNJ - Early recovery assistance to war-affected, resource-poor livestock keepers in south Lebanon

### Reporting Period:     1 April to 30 June 2009

### LRF-4 OSRO/LEB/702/UNJ - Early recovery assistance to war-affected, resource-poor livestock keepers in south Lebanon

- Main objectives and outcomes expected as per approved Project/Programme/project Document.

The development goal of the project is to improve the food security, nutritional and economic status of low-income rural families by initiating comprehensive recovery measures to support the war-affected livestock smallholders, mainly by restocking and distribution of animals (dairy cattle, goats, and animal feed).  The immediate objectives are the improvement of the lives and livelihoods of 715 war-affected livestock owners with special emphasis on female-headed households, through restocking of animals.

- Reference to how the project relates to the national priorities and how it aims to support national reconstruction goals of Lebanon.

The project is the outcome of the joint FAO-Ministry of Agriculture (MOA) “Damage and Early Recovery Needs Assessment of Agriculture, Fisheries and Forestry” completed in November 2006. It is to be noted that the exercise evaluated the overall damage caused to the farming and fishing communities and elaborated an early recovery programme for the immediate needs of the most vulnerable farming and fishing communities in the affected areas. Since the assessment was carried out jointly, the priorities of the MOA are thus reflected in the proposal.

- A listing of the main international and national implementing partners involved.

FAO and the Ministry of Agriculture

### II. RESOURCES

Total Programme/Project Budget:  US$1,900,000

LRF:  US$ 1,900,000

Government Input: US $ 0

Other: US $ 0

Total:  US$1,900,000

MAIN BUDGET ACTIVITIES:

All planned procurement and distribution of livestock and feed are complete and the project has reached a delivery rate of 99.6 per cent. Training on livestock dairy production and animal health was completed in October 2008.  The below budget reflects all expenditures up to 30 April 2009.

Budget: commitment and disbursement:

| OSRO/LEB/702/LEB |
| --- |
| Item | Approved Budget (in US$): | Estimated Disbursement/ Commitment (in US$) |
| Personnel and travel: | 422 524 | 418,013 |
| Livestock and supplies: | 1 206 006 | 1 206 006 |
| Miscellaneous/Other: | 147 170 | 146 512 |
| Agency Support Costs: | 124 300 | 121 982 |
| TOTAL: | 1 900 000 | 1 892 513 |

Personnel and travel costs:

FAO expenditures for personnel and travel cover four missions from the Chief Technical Advisor (CTA) and six missions from the FAO Headquarters Animal Production Officer to Lebanon and missions to Holland and Hungary for selection of dairy cows, which was carried out in the previous reporting period. The mission of the Evaluation Mission’s livestock expert is included under this budget line along with the staff costs of local staff working under the livestock project.

| Item: | Approved Budget cost (US$): | Estimated Disbursement/Commitment (US$) |
| --- | --- | --- |
| Personnel and travel: | 422 524 | 418 013 |

Livestock and animal feed:

All procurement for livestock and animal feed was completed in the previous reporting period. FAO procured inputs valued at US$1 206 006 and includes Holstein-friesian heifers, female baladi goats, male shamee goats, animal feed concentrate and alfalfa pellets.

| Item: | Approved Budgeted cost (US$): | Estimated Disbursement /Commitment (US$) |
| --- | --- | --- |
| Livestock and feed: | 1 206 006 | 1 206 006 |

Other costs (Training, General Operating Expenses, and Miscellaneous):

Expenses under “Other”, which groups budget lines such as training, general operating expenses, miscellaneous and overhead costs are indicated below. Full charge to support costs appears only on delivery of project activities.

| Item: | Approved Budget cost (US$): | Estimated Disbursement/Commitment (US$) |
| --- | --- | --- |
| Other: | 147 170 | 146 512 |

### RESULTS

Outcome:

Improve the lives and livelihoods of 750 war-affected livestock owners (benefiting 4 550 people - average of seven members per household). The project focused on female headed and low income households through restocking of animals, veterinary drugs, feed, and artificial insemination.

Outputs:

Output 1: Support to war-affected livestock smallholders through restocking and distribution of animals (cattle, female baladi goats, male shame goats);

Output 2: Improved animal production through provision of supplementary livestock feed and improved veterinary healthcare.

Output 3: Training farmers on improved animal husbandry and animal production techniques

Progress:

All activities of the project are complete and carried out in accordance to the established project workplan which was approved by the first Project Steering Committee on 1 December 2007. The project closing date was revised to 30 April 2009 and the project was operationally closed during the reporting period. FAO continued to provide livestock farmers with technical assistance and advisory services until closure of the project in order to strengthen the capacity of beneficiaries in improved animal production practices.

1.	Identification of Project Sites

FAO provided support to livestock farmers located in 50 villages south of the Litani River. The criteria for selection were as follows: 1) farmers must be from villages hit by the heaviest battles during the conflict, with the most damage and losses of animals; 2) villages with the most vulnerable populations in terms of poverty and deprivation in the area; and 3) livelihoods of the beneficiaries based traditionally on animal production activities.

2. Identification of Project Beneficiary Farmers

All project beneficiaries were identified and validated in collaboration with the MOA. The categorization and prioritization of project inputs and beneficiaries were approved by the first PSC and endorsed by the second PSC.

3. Procurement and delivery of project inputs:

As reported in previous progress reports, all FAO planned inputs were delivered to beneficiaries between May and July 2008 and include 202 dairy heifers originating from Holland and Germany, 99 male shamee goats from Cyprus, 1 500 local baladi goats and 1 500 kids, 200 tonnes of animal feed concentrate from Holland and 190 tonnes of alfalfa pellets from a local supplier in Lebanon.

4. Training and Capacity Building:

Training to livestock farmers was conducted before and after the distribution of animals during previous reporting periods. Advisory services on milk processing technologies and animal feed resources was given until 30 April 2009.

Implementation constraints, lessons learned from addressing these and knowledge gained from evaluations and studies that have taken place during the reporting period.

The recommendation from the Independent Evaluation Mission fielded from 16 to 30 November 2008 was implemented and training took place until 30 April 2009 (closure of the project).

Key partnerships and inter-agency collaboration: impact on results.

- Close collaboration with the MOA as the main national counterpart is continuous.

- Close collaboration with United Nations Mine Action Coordination Centre of Southern Lebanon 	(UNMACC) is ongoing for the safety of the field interventions activities.

- Through the Livelihoods Sector Working Group at the field level, coordination is taking place with all 	related agencies and NGOs to ensure none duplication of assistance and properly identify gaps and 	needs to streamline all related activities.

Other highlights and cross cutting issues pertinent to the results being reported on.

### FAO’s livestock project has targeted the resource-poor livestock keepers in targeted villages and this support will help in various cross-cutting issues such as poverty alleviation and food security. Livestock around the world are considered a valuable asset and animal production provides needed household income and provides the necessary nutrients to supplement the family diet. In addition, by targeting women and widows, FAO is able to empower these female headed households in order to provide for their families the basic household necessities.

### FUTURE WORK PLAN

- Priority actions planned for the subsequent reporting period to overcome constraints, build on achievements and partnerships, and use the lessons learned during the previous period.

None.

Indication of major adjustments in the strategies, targets or key outcomes and outputs.

- Project closure date was revised to 30 April 2009.

- Estimated Budget required (including any major funding shortfalls).

None.