LEBANON RECOVERY FUND (LRF)

ANNUAL project NARRATIVE progress report

| Recipient UN Organization: |  | Report Number: |
| --- | --- | --- |
| UNESCO |  | 2 |

| Project Number: |  | Project Title: |
| --- | --- | --- |
| LRF-6 222LEB4000 |  | Capacity building of human resources for digital documentation of World Heritage Sites affected by 2006 war in Lebanon |

| Reporting Period: |  | Project Budget: |
| --- | --- | --- |
| 1 January to 31 December 2008 |  | 767 226 US $ |

| List Implementing Partners: |  | Project Coverage/Scope: |
| --- | --- | --- |
| UNESCO-Beirut Directorate General of Antiquities, Ministry of Culture of Lebanon |  | Baalbek World Heritage Site (Lebanon) |

| Abbreviations and acronyms: |  | Project Duration/Closed Project: |
| --- | --- | --- |
| DGA Directorate General of Antiquities Lebanon UL Lebanese University ESGT Institute of Topography |  | 26 months |

# REPORT

# Purpose

  - Main objectives and outputs of the project

UNESCO assessment mission for (July –August 2006) war damages on World Heritage Sites of Lebanon expressed concern regarding the routine maintenance of those sites and recommended to prioritize the establishment of an integrate action plan for tangible cultural heritage conservation all over the country. This Action Plan should be considered as an umbrella for few most important components such are:

- Establishment of risks’ map for World Heritage Site;

- Establishment of digital exhaustive technical documentation for World Heritage Site;

- Capacity building of human resources able to address above components;

- Main objective of the proposed activity is to build capacities of Human Resources in charge, or potentially linked with, the conservation, the development and the enhancement of tangible cultural heritage in Lebanon.

  - Explain how the project relates to the LRF Terms of Reference

UNESCO believes that the expressed urgent need for capacity building of Lebanese human resources in the field of conservation and management of heritage sites is beneficial for the reconstruction of Lebanon. Broad objective of the digital documentation for heritage sites and its risk mapping could be launched by a limited operation on one selected World Heritage Sites of Lebanon and be considered as a pilot experience that in the future will be extended to other sites. Establishment of a training tool concerning the digital documentation of heritage site with most advanced and sophisticate techniques, a tool, which should be disseminated as an on-line course, and an on-site training of DGA staff and potential sites managers, students of UL, will contribute to the development of the country. Promotion of new information technologies for the main purpose of heritage management: conservation and daily maintenance will ensure the impact of heritage components in Lebanon, country with rich in heritage and strong tourism potential.

UNESCO supports the choice of the Ministry of Culture of Lebanon for Baalbek World Heritage Site as pilot site for the digital documentation and on-site training on risk mapping. Mainly, the reasons are, as follows:

- First of all the temples of Baalbek are in an urgent need of daily maintenance and monitoring. Only detailed digital documentation that would be use as a reference for the state of conservation followed by an elaborated procedure of regular updating could facilitate the complicate and delicate conservation task;

- Surveys already undertaken within other projects, as the World Bank project, could facilitate the establishment of documentation for reference and enable the implementation of the activity with a very tight but reasonable time-table;

- Risk mapping one of the World Heritage Sites and the knowledge acquired by concerned DGA staff through risk mapping training will contribute to the long term management of WH site enabling to prioritize interventions and design conservation action plans for heritage sites all over the country.

- The site provides wide scope of maintenance problems: structural stability (mostly Jupiter Temple), decay of materials (Bacchus Temple), development of cracks, vegetation etc. Therefore, digital documentation tool will be highly educational covering broad conservation issues.

  - Main implementing partners

UNESCO

- Overall coordination and supervision of the activity

- Administrative and financial management of the activity

- Regular reporting to the donor

Directorate General of Antiquities (DGA), Ministry of Culture of Lebanon

- Manager of the World Heritage Site of Baalbek pilot site chosen for the implementation of the activity;

- Main beneficiary of the training component of the activity as well of the acquisition of new 3D tools and equipments as well as the of the digital documentation, procedure of updating and virtual reconstruction;

- DGA selects monuments for operations;

- DGA dispatch its staff for the training;

- DGA provides all existing reference documentation for Baalbek, deliver authorisations and facilitates the execution of the activity;

- DGA elaborates the necessary procedures of the continuous data gathering process for the diachronic monitoring purposes.

The training

The main target group will be the

- DGA staff

- Lebanese University (UL) ESGT

The International Consultants will:

- Deliver training for Laser scanning and risk mapping. This training should be based on most recent documentation including digital one;

- Provide separate training for conservation action plan that should be based on the assessment of risk through mapping and on clear protocol prioritizing interventions and establishing its short, medium and long term strategies

- Technical reports and financial statement on the execution of operations will be regularly submitted to UNESCO

- Resources

Financial Resources:

Grand Total requested from LRF 767,226 US $

Attached budget revision dated 10.6.08

Human Resources:

National Staff:

  - Eight persons from the DGA/UL/ESGT will follow a 3 weeks training session on laser scanning applied on the monuments of Baalbek WH. The local experts will assist the International Consultants on this training.

  - The training session will be followed by a Survey (Laser Scanning) of 8 weeks provided by the Local Experts (3p) on the monuments of Baalbek according to the working plan established by the DGA.

  - The second phase is a training session for 6 persons from the DGA on Risk Mapping. This session will last for 4 weeks

  - The Risk Mapping  work will be completed by the DGA staff in a field work survey of 10 weeks

International Staff:

- Three International Consultants will provide a training session on Laser Scanning for a duration of maximum 3 weeks

- The report of the Laser Scanning training session and survey will be provided by one International Consultant that will follow the entire work. The duration of this work is estimated to maximum 8 weeks.

- Three International Consultants will provide a training session on Risk Mapping for a duration of maximum 4 weeks

- Three International Consultants will follow up the field work on Risk Mapping delivered by the 6 DGA staff. Duration of the work maximum 2 weeks

- The report of the Risk Mapping training session and survey will be provided by one International Consultant that will follow the entire work. The duration of this work is estimated to maximum 8 weeks.

- Implementation and Monitoring Arrangements

  - The project is implemented by the UNESCO Beirut Office in collaboration with the Directorate General of Antiquities and the Ministry of Culture of Lebanon, the beneficiary of the project.

  - The recruitment of the Technical Coordinator was advertised on UNESCO-Beirut website. The evaluation of the candidature is based on the terms of reference established by the UNESCO Beirut Office. The contract launched has duration of the project. The technical coordinator will submit a activity report to UNESCO Beirut Office on the advancement of the project.

- Results

The implementation of the programme is resumed as follow:

- February 2008 recruitment of the Technical Coordinator

- 31 March 2008 This bid has been published on the UN Global market place under link http://www.ungm.org/default.aspx?pid=69 Procurement notice has been advertised on UNESCO-Beirut office website http://www.unesco.org/beirut/index.php?id=unescobid

- 02 April 2008 Announcement and contact of the International Institutions and National Contractors

- 18 April 2008 Opening of the tender of the OIC for the purchase of the Equipment (Leica ScanStation and Rolleiflex) at 14.00h

- 18 April 2008 Receiving letter of interest and documentation from the Contractors (National Geodesy and photogrammetry professional offices)

- 10 June 2008 Budget revision approved (initiated to acquire the entire needed equipment)

- 30 June 2008 Acquisition of the Scan Station and the Metric Camera approved and in process

- 14 July 2008 Finalization of the Contract for the Leica Scan Station and the Rollei Metric Camera

- 31 July 2008 Signature of the contractor for the acquisition of the Leica Scan Station and the Rollei Metric Camera

- August 2008 Acquisition of the Car and the computers delivered from the UNESCO to the DGA

- 10 October 2008 the International Consultants was selected the University of Leuven where selected by the committee of evaluation.

- November 2008 Delivery of the Leica Scan Station and the Metric Camera to the Unesco Beirut Office

- 13-16 December 2008 Three days of training to three DGA technical and specialized staff on Leica Scan Station and Rollei Metric Camera delivered by the provider Alpha Tech. s.a.r.l.

- 13 December 2008 official handing over of the material from Unesco/Beirut office to Directorate General of Antiquities In the presence of his Excellency the Minister of Culture, Director General of Antiquities the Unesco Beirut office and the CDR. This ceremony had taken place in the National Museum.

Partners involved in the action are:

UNESCO as the overall coordination and supervision of the activity

Directorate General of Antiquities (DGA), Ministry of Culture of Lebanon as the beneficiary

International Consultants as the performer of the training and the supervisor of the documentation work in coordination with the DGA

National Experts as the realization of all the documentation work on the monuments of Baalbek WH site in coordination with the International Consultant and the DGA

UL and DGA staff will follow the training session. DGA staff will be in charge of the management and the follow up of this heritage.

- Future Work Plan  1 January-30 December 2009

The main activities for this period are:  The implementation of the project and the launching of the first component of the project: the Laser scanning documentation and training session

January-April

International Consultants:

- Preparation of the contract of the International Consultant as for the University of Leuven that will undertake the training on laser scanning.

- Finalization of the schedule of the activities of the laser scanning of the International Consultant

- Implementation of the project on site

National Experts

- Re-advertisement for the prequalification of a local contractor, having experience in the documentation of cultural heritage.

- Finalization of the schedule of the activities of the laser scanning of the National Consultant

- Implementation of the work on site

- Signature of the contract

Training

- Identification of the trainees from the DGA and the UL.

- The training will also be followed by National experts for the Laser scanning documentation

- DGA staff following the implementation of the project on site

April-July

Laser scanning documentation

- The laser scanning of the monuments of Baalbek WH will be undertaken in close coordination with the DGA

- The documentation work will be executed by the National experts under the supervision of the International Consultant in charge of the final report and the documentation documents

| Activity | Type | schedule | Timing and consultant |
| --- | --- | --- | --- |
| Activity 1 (Annex 1) | Implementation meeting with the local contractor and the DGA | Week One | 20 – 25 April 2009 (Bjorn Van Genechten) (Travel to Lebanon) |
|  | Selection of the Local Consultant on bases of the work of implementation established The local Consultant perform the implementation of the general grid | Week Two and Three | 27 April – 8 May 2009 (Local consultant), four weeks in total to avoid delays |
| Activity 2 (Annex 1) | Training for DGA and ESGT/Lebanese University staff as well as for the local contractor | Week Four and Five | 10 – 16 May 2009 (Bjorn Van Genechten) (Jon Benford) (Mario Santana) (Travel to Lebanon) |
|  | - Training attended by DGA and ESGT/Lebanese University staff | Week Four | 16 - 23 May 2009 (Mario Santana 17 May 2009) (Bjorn Van Genechten leaves on 20 may) (Jon Benford leaves 23 may) |
|  | - Training attended by the local contractor | Week Five |  |
|  | Local consultant works on site | Week Six and Seven | 25 May – 5 June 2009 (Local consultant) |
| Activity 3 | Mid-term evaluation of the local contractor work on laser scanning | Week Eight | 20 – 24 June 2009 (Bjorn Van Genechten) |
|  | Local consultant works on site | Week Nine and Ten | 20 - 28 June 2009 Two weeks in total to avoid delays |
| Activity 4 | Final evaluation and establishment of a monitoring strategy for Baalbek | Week Eleven (overlapping with ten) | 28 June – 04 July 2009 (Bjorn Van Genechten) (Mario Santana) (Travel to Lebanon) |
| Activity 5 | Final report and submission of the documentation and manuals | Week Twelve | 06-10 July 2009 (Mario Santana) (In Belgium) |

August-November

Risk Mapping

- The Risk Mapping of the monuments of Baalbak WH will be undertaken in close coordination with the DGA

- The Risk Mapping work will be executed by the National experts under the supervision of the International Consultant in charge of work, the training and the final report

| Activity | Type | schedule | Timing and consultant |
| --- | --- | --- | --- |
| Activity 1 | Implementation | Week One | DGA-International Consultant |
| Activity 2 | Training for DGA | Week Two to Four | 6 p. DGA and 3 p. International Consultant |
| Activity 3 | Risk Mapping | Week Five to Eight | 6 p. DGA and 3 p. International Consultant |
| Activity 4 | Report (Risk Mapping) | Week Nine to Ten | 1 p. International Consultant |

December

- Final report

- Closing of the project

Annex 1

Activity 1 Implementation of the work

The draft programme of the International Consultant:

20 April: arrival to Beirut, transfer to the hotel

21 April: DGA, Departure to Baalbak (Site visit with the DGA team , technical meetings at the hotel)

22-24 April: Working in Baalbak with the DGA team

24 April: Technical Meetings at the DGA

25 April:  Departure

## Activity 2 Mission: Implementation of the project: The Training

The International consultants must assure the training of the team composed of:

- Geodesy and photogrammetry professionals (contractor).

- Geodesy engineers from the ESGT.

- One person with an MA of physics or mathematics.

- DGA staff as archaeologists and architects.

These training sessions have duration of 2 weeks for 3 International Consultants and are performed on and off site according to the requirements of the work.

Period: May 7 - 23, 2009

Expert: Bjorn Van Genechten, Mario Santana, Jon Bedford (English Heritage)

Proposed timetable

| Day 01: | 07/05/2009 TH |  |
| --- | --- | --- |
| Arrival to Beirut: Arrival Mario Santana |

| Day 2: | 08/05/2009 FR |  |
| --- | --- | --- |
| Hours | Activity | Location |
| 10:00 – 17:00 | Preparation of training material | Beirut |

| Day 3: | 09/05/2009 SA |  |
| --- | --- | --- |
| Hours | Activity | Location |
| 10:00 – 16:00 | Preparation of training material | Beirut |
| 16:00 | Travel to Baalbek |  |

| Day 4: | 10/05/2009 SU |  |
| --- | --- | --- |
| Hours | Activity | Location |
| 10:00 | Preparation of training lab | Baalbek |

Arrival to Beirut:  Arrival Bjorn Van Genechten

| Day 5: | 11/05/2009 MO (Baalbek) |  |
| --- | --- | --- |
| Hours | Activity | Equipment |
| 9:00 – 12:00* | Session 1: Introduction of Heritage Recording (M. Santana): Concepts; Illustrated examples. | Digital projector |
| 12:00 – 13:30 | Lunch |  |
| 13:30 – 17:00* | Session 2: Introduction to laser scanning (B. Van Genechten): Concepts Recording planning | Digital projector |
| 17:00 – 17:30 | Question and answers session |  |

(*): Break of 15 minutes foreseen

| Day 6: | 12/05/2009 TU |  |
| --- | --- | --- |
| Hours | Activity | Location |
| 9:00 – 12:00* | Session 3: Field demonstration (B. Van Genechten - M. Santana) | Laser scanning equipment |
| 12:00 – 13:30 | Lunch |  |
| 13:30 – 17:00* | Session 4: Laser scanning Registration (B. Van Genechten - M. Santana) | Digital projector, PCs, Tutorial |
| 17:00 – 17:30 | Question and answers session |  |

(*): Break of 15 minutes foreseen

| Day 7: | 13/05/2009 WE |  |
| --- | --- | --- |
| Hours | Activity | Location |
| 9:00 – 12:00* | Session 5: Laser scanning: processing using Cloudworx (B. Van Genechten - M. Santana) | Digital projector, PCs, Tutorial |
| 12:00 – 13:30 | Lunch |  |
| 13:30 – 17:00* | Session 6: Laser scanning: processing using Cloudworx (B. Van Genechten - M. Santana) (cont.) | Digital projector, PCs, Tutorial |
| 17:00 – 17:30 | Question and answers session |  |

(*): Break of 15 minutes foreseen

| Day 8: | 14/05/2009 TH |  |
| --- | --- | --- |
| Hours | Activity | Location |
| 9:00 – 12:00* | Session 7: Fieldwork: participant are split in groups and area assigned to record a monument | Digital projector, PCs, Tutorial |
| 12:00 – 13:30 | Lunch |  |
| 13:30 – 17:00* | Session 8: Fieldwork and office: participants are split in groups and area assigned to continue recording a monument and perform registration. | Digital projector, PCs, Tutorial |
| 17:00 – 17:30 | Question and answers session |  |

(*): Break of 15 minutes foreseen

Departure of Mario Santana to Beirut

| Day 9: | 15/05/2009 FR |  |
| --- | --- | --- |
| Hours | Activity | Location |
| 9:00 – 12:00* | Session 9: Laser scanning: processing using Geomagic(B. Van Genechten) | Digital projector, PCs, Tutorial |
| 12:00 – 13:30 | Lunch |  |
| 13:30 – 17:30* | Session 10: Laser scanning: processing using Geomagic (B. Van Genechten) (cont.) | Digital projector, PCs, Tutorial |

(*): Break of 15 minutes foreseen

Departure of Mario Santana to Europe

| Day 10: | 16/05/2009 SA |  |
| --- | --- | --- |
| Hours | Activity | Location |
| 9:00 – 12:00* | Session 11: Laser scanning: processing using Geomagic (B. Van Genechten) (cont.) | Digital projector, PCs, Tutorial |
| 12:00 – 13:30 | Lunch |  |
| 13:30 – 17:30* | Session 12: Laser scanning: processing Wrap up (B. Van Genechten) | Digital projector, PCs, Tutorial |

(*): Break of 15 minutes foreseen

| Day 11: | 17/05/2009 SU |  |
| --- | --- | --- |
| Day-off |

Arrival of Jon Bedford

| Day 12: | 18/05/2009 MO |  |
| --- | --- | --- |
| Meeting Jon Bedford and Bjorn Van Genechten |
| Hours | Activity | Location |
| 13:30 – 17:30* | Session 13: 3D Laser Scanning for Heritage: procedures by English Heritage (J. Bedford) | Digital projector |

(*): Break of 15 minutes foreseen

Departure of Bjorn Van Genechten to Beirut

| Day 13: | 19/05/2009 TU |  |
| --- | --- | --- |
| Hours | Activity | Location |
| 9:00 – 12:00* | Session 14: Field work, participants to scan a monument following English Heritage guidelines (J. Bedford) | Laser scanning equipment |
| 12:00 – 13:30 | Lunch |  |
| 13:30 – 17:30* | Session 15: Field work, participants to scan a monument following English Heritage guidelines (J. Bedford) (cont.) | Laser scanning equipment, Digital projector, PCs |

(*): Break of 15 minutes foreseen

Departure of Bjorn Van Genechten to Europe

| Day 14: | 20/05/2009 WE |  |
| --- | --- | --- |
| Hours | Activity | Location |
| 9:00 – 12:00* | Session 16: Processing, participants to model the monument following English Heritage guidelines (J. Bedford) | Digital projector, PCs |
| 12:00 – 13:30 | Lunch |  |
| 13:30 – 17:30* | Session 17: Processing, participants to model the monument following English Heritage guidelines (J. Bedford) (cont.) | Digital projector, PCs |

(*): Break of 15 minutes foreseen

| Day 15: | 21/05/2009 TH |  |
| --- | --- | --- |
| Hours | Activity | Location |
| 9:00 – 12:00* | Session 18: Groups to prepare presentation about results (J. Bedford) | Digital projector, PCs |
| 12:00 – 13:30 | Lunch |  |
| 13:30 – 17:30* | Presentations and course evaluation (J. Bedford) | Digital projector, PCs |

| Day 16: | 22/05/2009 FR |  |
| --- | --- | --- |
| Departure of Jon Bedford to Beirut |

| Day 17: | 23/05/2009 SA |  |
| --- | --- | --- |
| Departure of Jon Bedford to Europe |

| EXTRABUDGETARY FUNDS PROJECT BUDGET - IN THE COURSE OF EXECUTION |
| --- |
| Project code: 222LEB4000 | PROJECT OFFICER : | 10.06.2008 |
| Sector/Fund center (HQ Div or Field Off): CLT/PFF | MR. JOSEPH KREIDI |  |  |
| Source of Funds: BILAT. | SECTOR'S AO : |  |  |
| SISTER'S C/5 Programme (at activity level): |  |  |  |
|  |  | Revised allocation |  | Additional allotment requested for 2008 |
|  | PROJECT COMPONENTS |  |  | $ |
| TOTAL | PERSONNEL COSTS (PC) 10'+11+13 | 65,971.00 |  |  |
| 10 | 10' Other Personnel costs (BLs 14,16,17) | 5,971.00 |  |  |
|  | 11 Consultants / International Experts | 50,000.00 |  |  |
|  | 13 Administrative Support Personnel | 10,000.00 |  |  |
| 20 | SUB-CONTRACTS | 350,062.00 |  |  |
| 30 | TRAINING | 10,000.00 |  |  |
| 40 | EQUIPMENT | 285,000.00 |  |  |
| 50 | MISCELLANEOUS | 6,000.00 |  |  |
|  | TOTAL, PROJECT COST 10'+11+13+20+30+40+50 | 717,033.00 |  | - |
| 80 | PROGRAMME SUPPORT COSTS (P.S.C.) | 50,193.00 |  |  |
|  | - for Other components % | 50,193.00 |  |  |
|  | - for Equipment % |  |  |  |
| TOTAL | PROJECT, with P.S.C. | 767,226.00 |  |  |
| REVENUE: |  |  |  |
| REMARKS: |  |  |  |
| FOR BB USE: |  |  |  |
|  | ALLOCATION Nº: | RELEASE ALLOCATION Nº: | ALLOTMENT Nº: |