LEBANON RECOVERY FUND

ANNUAL project NARRATIVE progress report

# REPORT COVER PAGE

| Participating UN Organization: |  | Report Number: |
| --- | --- | --- |
| UNDP |  | 3 |

| LRF Project No: New Atlas Project No: (as per enclosed list) 65549 65557 |  | LRF Project Title: |
| --- | --- | --- |
|  |  | Flood Risks Management and Water Harvesting for Livelihood Recovery in Baalback-Hermel. |

| Reporting Period: |  | Project Budget: |
| --- | --- | --- |
| 1 January to 31 December 2009 |  | LRF-funding: Flood I: $ 2,834,880 Flood II: $ 3,800,000 Other funding: $ - |

| List Implementing Partners: |  | Project Coverage/Scope: |
| --- | --- | --- |
| Arab Center for the Studies in Arid Zones and Drylands (ACSAD), German Agency for Technical Cooperation (GTZ). Ministry of Agriculture Ministry of Water & Energy/Bekaa Municipalities of Aarsal and Fakeha in North Bekaa |  | Baalback-Hermel region Flood I: Aarsal and Fakhe villages Flood II: Ras Baalback village |

| Abbreviations and acronyms: |  | Project Duration/Closed Project: |
| --- | --- | --- |
| ACSAD: Arab Center for Studies in Arid Zones and Drylands CO: Country Office DEX: Direct Execution GTZ: German Agency for Technical Cooperation. LRF: Lebanon Recovery Fund ARDA: Aarsal Rural Development Association. MoA: Ministry of Agriculture MoEW: Ministry of Energy and Water PMU: Project Management Unit |  | Start Date: Flood I: Original start date :7 Nov 2007 Flood II: Original start date :26 Sep 2008 End date: Flood I: Original end date : Sept. 2009 Revised end date : Dec. 2009 Flood II: Original end date : Feb 2011 |

# NARRATIVE REPORT FORMAT

# Purpose

The project aims at assisting the Government of Lebanon in its recovery efforts in the conflict-affected and desertification-prone region of Baalback – El Hermel through better land management practices, namely: flood risk reduction, restoration of vegetation cover and improved availability of irrigation water needed to increase crop productivity and improve standards of living.  This will be achieved through the construction of stone walls, check dams and water collection reservoirs to prevent runoff water from reaching villages and farms and through the restoration of land cover to reduce soil erosion. The objectives related to water management will be achieved through construction of several membrane-lined reservoirs to collect unused water from springs, rainfall and snow melts and through installation of water-use efficient irrigation networks and systems that will be used by local farmers to improve their crop diversity and productivity

The project objectives will be met through the following outputs:

- Coordination and linkage with on-going projects established and strengthened

- Risks and damages caused by floods in target area managed and reduced

- Water for irrigation harvested, managed and made available to farmers

- Land cover in risk areas increased and soil erosion reduced

- Sustainability, capacity building and public awareness

The expected outcomes from the current project particularly those related to water harvesting, increased vegetation cover and higher productivity will serve very well the national efforts and plans aiming at  combating desertification and alleviating poverty in North Bekaa. They will also serve the recovery efforts made by the Lebanese government in normalizing the living conditions of rural communities and in restoring the basic needs and infrastructure for practicing sound and profitable agriculture in the affected area.

The Ministry of Agriculture is the main national project partner responsible for the supervision and execution of the project through the National Action Programme to Combat Desertification project already established at the Ministry.  The local municipalities and communities in the region are the project stakeholders and will be involved in the project activities.  The Ministry of Energy and Water and GTZ will be involved in technical information sharing and coordination of the project, while ACSAD will have a technical backstopping role for the flood management component of the project.  Currently the consulting firm Earth Links and Arab Resources development has been contracted to design the flood management structures based on the modelling of the phase II watershed

- Resources

Financial Resources:

  - All the project’s funds were provided by the LRF. The MoA is hosting the project, it is providing the offices and other associated services but without any in cash contribution.

  - No budget revisions or financial changes were undertaken.

Human Resources:

  - National Project Staff:

- 1 project manager

- 3 full time technical assistants

- 3 part time technical assistants

- 1 driver

  - International Staff: One Jordanian expert (international SSA contract).

- Implementation and Monitoring Arrangements

  - The Project is executed under the UNDP Direct Execution modality (DEX), whereby UNDP acts both as the implementing and the executing agency. For the day-to-day management of the project, the UNDP CO has set-up a Project Management Unit (PMU). The PMU works under the direct supervision of the UNDP CO, and in close collaboration with the donor, the Lebanese Government, the local direct and indirect beneficiaries, as well as with the international team of experts and the local contractors recruited for this project. The PMU is led by a full time national Project Manager and is supported by the required national professional and administrative staff as well as national and international consultants.

  - The UNDP CO is responsible for monitoring the progress towards intended results, and for ensuring high-quality managerial and financial implementation of the project, including the responsibility for ensuring proper use of administrated funds to assigned activities, timely reporting of progress (quarterly progress reports), as well as undertaking of mandatory and non-mandatory evaluations. The UNDP CO follows up with the PMU on a semi-weekly basis on project implementation issues and undertakes annual tripartite review meetings. Furthermore, the procurement of goods and services and the recruitment of personnel are effected in accordance with UNDP standard guidelines, procedures and regulations.

- Results

The actual start date for the project’s activities was on 01 February 2008 following the signature of the project document by national counterparts.  With the approval of the Lebanon Recovery Fund of the Phase II of the Flood Project that targets the watershed of Ras-Baalback covering an area of approximately 220m2, a new UNDP Project Document was developed encompassing both phases of the project.  The two watershed targeted by the projects can be found in Annex 1. Both phases of the Flood project comprise a larger programme on Flood Management in the Bekaa region.  Accordingly, reporting will include progress on both projects in the same reports.

The total budget for both phases amounts to be $6,634,880 covering a 4 year timeframe in total (2008 – 2011).

During the current reporting period, procurement was undertaken for the required experts and contractors, flood management structures for Phase I were finished and modelling and design works for Phase II were initiated.

Progress on outputs

- Project Management and Coordination

- An international bidding process was launched for the modeling of the watershed in phase II and the contract was awarded to and signed with Earth Links and Advanced Resources Development ELARD

- A communication strategy was initiated by the Flood Project.

- A new project manager was recruited starting November 2009

- A tripartite review meeting was undertaken in the presence of concerned stakeholders and the Minister of Agriculture HE Elias Skaff.

- Flood Risk Management and Reduction

- Selection of land for the excavation of reservoirs and the construction of walls, check dams, gabions, etc… was done with the participation of the municipality and local community.

- The municipality of Aarsal was provided with funds by the Flood project in order to pay compensations for the land owners where ponds will be excavated

- Hands on capacity building for flood risk management was done by the ACSAD team

- Modifications of the original flood management plan were undertaken due to constraints in land ownership and access.

- The construction of 8 reservoirs of a total of 330,000 m3 capacity and 161 walls was contracted to 2 contractors.  Works were finished by end of 2009.

- A Caterpillar 320 DL excavator was purchased through a process of international bidding and will be provided to the Municipality of Aarsal in a media covered handover event involving the Minister of Agriculture and all concerned stakeholders. The excavator will allow the Municipality of Aarsal to undertake maintenance works on the flood structures.

- An estimation of the reduced damage was done by the project staff.  The cost of each flood event in Fakeha and Aarsal is around 2.5 M US$.  The project will help reduce considerably the costs for the Lebanese government

- Flood modeling, design of reservoirs and walls for phase II was initiated.

- A decision was made to allocate funds for a national assessment of flash floods with estimation of costs for management of risks

- Water harvesting for extending irrigation periods

- Rafik Khoury and Partners were selected as consulting firm for the design of the water harvesting works.

- Final designs and contractual documents were prepared  for two sites

- A request for bids was initiated

- The construction of a reservoir in Deir el Ahmar with a capacity of 33,000m3 was contracted to Farhat Group works were initiated on site

- Land Cover Increase and Soil Erosion Reduction

A soil erosion susceptibility map was developed by the project team and provided to the Aarsal Municipality, ARDA and the Ministry of Agriculture

- Site selection for planting was based on the erosion map, the possibility for protection from grazing by the municipality and land ownership.

- 20,000 seedlings were produced by ARDA and planting was initiated.  Delays are encountered due to land selection and possibility for protection from grazing.

- Selection of lands suitable for reforestation was initiated for Phase II.

- Work on a  soil erosion map, for Phase II, was started

- Capacity building and awareness raising

- An informative calendar including the flood project was designed, printed and distributed

- Continuous meetings and hands on training was done by the project  team for all stakeholders

- Meetings regarding Phase II were initiated with the municipality of Ras Baalback

- Cooperation has been initiated with universities

Implementation Constraints

Land ownership: Land ownership is a serious problem in North Bekaa region. Selection of land areas for planting trees has been affected by land ownership.

Overgrazing:  The selection of planting sites has been strongly influenced by the capacity of the municipality of Aarsal to protect the planted areas fro grazing herds.  Aarsal has the largest herd of sheep and goats in Lebanon.  Overgrazing is a majpr problem.  Plots were selected close to Aarsal with a possibility to be viewed from the village.  Far areas could not be planted because the municipality did have enough capacity to guard the planted trees.

Increased fuel costs: During the year 2008, sharp increases in fuel costs occurred; this had a direct effect on the costs of excavations which resulted in sharp differences from the offers originally submitted by the contractors. Consequently, this influenced the number of excavations and size of the proposed reservoirs/lakes which had to be adjusted in accordance with the available budget.

Partnerships and collaborations

A good partnership is established between UNDP, MoA, ACSAD and GTZ and the Municipality of Aarsal. The project’s working group is meeting whenever needed to discuss all major implementation steps and ensure lessons learnt from the initial pilot project implemented by GTZ, ACSAD and MoA in Al-Qaa are transferred.

- Future Work Plan

The projected activities and expenditures for the following reporting period (1 January-31 December 2010) are in the order of 2,100,000 USD divided as follows:

Remaining Activities					Allocated budget

- Water harvesting and irrigation networking:            	     692,028 USD

- Planting of trees and protection 			       61,000 USD

- Design of flood risk management structures 		     158,524 USD

- Flood strategy for Lebanon				     100,000 USD

- Field excavations of water collection reservoirs: 	     600,000 USD

- Establishment of stone walls and check dams:         	     250,000 USD

- Remaining

- Capacity building of target Municipality:                        22,000  USD

- Salaries of staff & Consultants                                	     225,000 USD

There will be no major changes in the strategy, targets or outputs.

Annex 1 – The Two Project Watersheds in North Bekaa Region

Watershed yield as modeled by ACSAD

| Pond | location | Pond capacity (m3) |
| --- | --- | --- |
| 4 | Wadi Zaarour | 45000 |
| 7 | Wadi Zaarour | 106000 |
| 8 | Wadi Al dam | 23000 |
| 10 | Wadi Al dam | 32000 |
| 11 | Wadi Hmeed | 54000 |
| 13 | Mrah Al Cheikh | 134000 |
| 16 | Wadi Al-Hosn | 24000 |
| 17 | Wadi Arnab | 16000 |

| Check Dam | Different reservoirs |
| --- | --- |
| Gabion wall | Different reservoirs |
| Contour Stone Wall | Different reservoirs |
| Gabion in preparation | Different reservoirs |
| Finished Gabion | Pond 13 largest pond |

|  | Nursery in Aarsal |
| --- | --- |
|  | Produced seedlings |
|  | Meetings with stakeholders and capacity building |
|  | Purchased excavator |

Final list of established walls and performed modifications

| Structure No. | Structure Type | Planned Volume | As Built volume | Remarks |
| --- | --- | --- | --- | --- |
| 1 | stone wall | 55 | 64 | constructed and accepted |
| 2 | stone wall | 13 | 15 | constructed and accepted |
| 3 | repair wall | 75 | 77 | constructed and accepted |
| 4 | stone wall | 4 | 6 | constructed and accepted |
| 5 | stone wall | 43 | 43 | constructed and accepted |
| 6 | check dam | 22 | 23 | constructed and accepted |
| 7 | stone wall | 80 | 84 | constructed and accepted |
| 8 | stone wall | 6.5 | 74 | constructed and accepted |
| 9 | check dam | 14 | 15 | constructed and accepted |
| 10 | stone wall | 45 | 45 | constructed and accepted |
| 11 | stone wall | 19 | 19 | constructed and accepted |
| 12 | stone wall | 30 | 40 | constructed and accepted |
| 13 | stone wall | 30 | 30 | constructed and accepted |
| 14a | check dam | 16 | 16 | constructed and accepted |
| 14b | stone wall | 20 | 20 | constructed and accepted |
| 15 | check dam | 8 | 46 | constructed and accepted |
| 16 | check dam | 53 | 0 | canceled |
| 17 | stone wall | 39 | 20 | constructed and accepted |
| 18 | stone wall | 66 | 0 | canceled |
| 19 | stone wall | 120 | 123 | constructed and accepted |
| 20 | stone wall | 16 | 16 | constructed and accepted |
| 21 | stone wall | 56 | 60 | constructed and accepted |
| 22 | check dam | 46 | 50 | constructed and accepted |
| 23 | stone wall | 32.5 | 31.5 | constructed and accepted |
| 24 | check dam | 5 | 5 | constructed and accepted |
| 25 | stone wall | 49 | 50 | constructed and accepted |
| 26 | stone wall | 26 | 0 | canceled |
| 27 | check dam | 11.5 | 15 | constructed and accepted |
| 28 | stone wall | 51 | 53 | constructed and accepted |
| 29 | check dam | 46 | 0 | canceled |
| 30 | stone wall | 4.5 | 0 | canceled |
| 31 | stone wall | 25 | 0 | canceled |
| 32 | 0 | 0 | 0 | no structure |
| 33 | Trench | 11 | 15 | accepted and excavated |
| 34a | repair wall | 42 | 43 | constructed and accepted |
| 34b | Gabion | 100 | 119 | constructed and accepted |
| 34c | repair wall | 13 | 15 | constructed and accepted |
| 35 | check dam | 11 | 15 | constructed and accepted |
| 36 | stone wall | 35 | 39 | constructed and accepted |
| 37 | stone wall | 115 | 118 | constructed and accepted |
| 38 | stone wall | 180 | 182 | constructed and accepted |
| 39 | stone wall | 190 | 213 | constructed and accepted |
| 40 | stone wall | 67.5 | 70 | constructed and accepted |
| 41 | check dam | 28 | 30 | constructed and accepted |
| 42 | Gabion | 112.5 | 129 | constructed and accepted |
| 43a | Road | 0 | 0 | done and accepted |
| 43b | check dam | 27 | 29 | constructed and accepted |
| 44 | stone wall | 23 | 22 | constructed and accepted |
| 45 | stone wall | 10.5 | 14 | constructed and accepted |
| 46 | stone wall | 60 | 124 | constructed and accepted |
| 47 | check dam | 46 | 55 | constructed and accepted |
| 48 | stone wall | 20 | 0 | merged with another structure |
| 49 | stone wall | 135 | 152 | constructed and accepted |
| 50 | stone wall | 40.5 | 40 | constructed and accepted |
| 51 | stone wall | 20 | 23 | constructed and accepted |
| 52 | stone wall | 15 | 15 | constructed and accepted |
| 53 | stone wall | 30 | 31.5 | constructed and accepted |
| 54 | stone wall | 20 | 0 | canceled |
| 55 | repair wall | 20.5 | 21 | constructed and accepted |
| 56 | stone wall | 30 | 30 | constructed and accepted |
| 57 | stone wall | 11 | 0 | canceled |
| 58 | stone wall | 18 | 0 | merged with another structure |
| 59 | stone wall | 18 | 0 | merged with another structure |
| 60 | repair wall | 11 | 31 | constructed and accepted |
| 61 | stone wall | 13 | 13.5 | constructed and accepted |
| 62 | Gabion | 60 | 75 | constructed and accepted |
| 63 | Gabion | 12 | 8 | constructed and accepted |
| 64 | stone wall | 125 | 119 | constructed and accepted |
| 65 | repair wall | 65 | 65 | constructed and accepted |
| 66 | check dam | 9 | 20 | constructed and accepted |
| 67 | Gabion | 25 | 27 | constructed and accepted |
| 68 | stone wall | 16 | 17 | constructed and accepted |
| 69 | repair wall | 21 | 26.5 | constructed and accepted |
| 70 | stone wall | 44 | 51 | constructed and accepted |
| 71 | Gabion | 72 | 0 | canceled |
| 72 | repair wall | 120 | 0 | canceled |
| 73 | stone wall | 90 | 90 | constructed and accepted |
| 74 | stone wall | 6.5 | 0 | canceled |
| 75 | stone wall | 32.5 | 33 | constructed and accepted |
| 76 | stone wall | 37 | 0 | canceled |
| 77 | stone wall | 10 | 0 | canceled |
| 78 | stone wall | 25 | 0 | canceled |
| 79 | stone wall | 35 | 0 | canceled |
| 80a | repair wall | 120 | 136 | constructed and accepted |
| 80b | stone wall | 49 | 80 | constructed and accepted |
| 81 | Gabion | 14 | 0 | canceled |
| 82 | check dam | 9 | 11 | constructed and accepted |
| 83 | stone wall | 24 | 0 | canceled |
| 84 | stone wall | 33 | 0 | canceled |
| 85 | stone wall | 41 | 0 | canceled |
| 86 | stone wall | 67 | 0 | canceled |
| 87 | stone wall | 11 | 0 | canceled |
| 88 | repair wall | 21 | 32 | constructed and accepted |
| 89 | stone wall | 79 | 80 | constructed and accepted |
| 90 | Gabion | 250 | 0 | canceled |
| 91 | Gabion | 52.5 | 0 | canceled |
| 92 | Gabion | 30 | 67 | constructed and accepted |
| 93 | stone wall | 25 | 30 | constructed and accepted |
| 94 | Gabion | 25 | 45 | constructed and accepted |
| 95 | stone wall | 15 | 105 | constructed and accepted |
| 96 | Gabion | 139 | 139 | constructed and accepted |
| 97a | stone wall | 30 | 30 | constructed and accepted |
| 97b | Gabion | 7 | 10 | constructed and accepted |
| 97c | stone wall | 57 | 57 | constructed and accepted |
| 98 | Gabion | 150 | 156 | constructed and accepted |
| 99 | check dam | 52 | 55 | constructed and accepted |
| 100 | check dam | 150 | 161 | constructed and accepted |
| 101 | repair wall | 21 | 21 | constructed and accepted |
| 102 | check dam | 21 | 22 | constructed and accepted |
| 103 | check dam | 16 | 52 | constructed and accepted |
| 104 | check dam | 14.5 | 14.5 | constructed and accepted |
| 105 | check dam | 32 | 32 | constructed and accepted |
| 106 | check dam | 13 | 51 | constructed and accepted |
| 107 | check dam | 30 | 30 | constructed and accepted |
| 108 | check dam | 21 | 21 | constructed and accepted |
| 109 | Gabion | 19 | 36 | changed to check dam |
| 110 | Gabion | 20 | 84 | constructed and accepted |
| 111 | check dam | 10 | 34 | constructed and accepted |
| 112 | stone wall | 10 | 45 | constructed and accepted |
| 113 | repair wall | 85 | 85 | constructed and accepted |
| 114 | repair wall | 22 | 23 | constructed and accepted |
| 115 | stone wall | 48 | 48 | constructed and accepted |
| 116 | stone wall | 84 | 84 | constructed and accepted |
| 117 | stone wall | 37 | 37 | constructed and accepted |
| 118 | stone wall | 30 | 30 | constructed and accepted |
| 119 | Gabion | 37.5 | 37.5 | constructed and accepted |
| 120 | check dam | 29 | 67 | constructed and accepted |
| 121 | check dam | 5 | 20 | constructed and accepted |
| 122 | Gabion | 38 | 38 | constructed and accepted |
| 123 | repair wall | 42 | 43 | constructed and accepted |
| 124 | repair wall | 46 | 169 | constructed and accepted |
| 125 | stone wall | 12 | 0 | merged with another structure |
| 126a | repair wall | 32 | 0 | merged with another structure |
| 126b | stone wall | 12 | 0 | merged with another structure |
| 127 | Gabion | 97 | 0 | merged with another structure |
| 128 | Gabion | 13.5 | 0 | merged with another structure |
| 129 | check dam | 37.5 | 41 | constructed and accepted |
| 130 | stone wall | 15 | 18.5 | constructed and accepted |
| 131 | stone wall | 30 | 31 | constructed and accepted |
| 132 | Gabion | 122.5 | 0 | canceled |
| 133 | stone wall | 51 | 0 | canceled |
| 134 | stone wall | 45 | 49 | constructed and accepted |
| 135 | check dam | 48 | 66 | constructed and accepted |
| 136 | check dam | 63 | 73 | constructed and accepted |
| 137 | repair wall | 19.5 | 19 | constructed and accepted |
| 138 | repair wall | 25 | 28 | constructed and accepted |
| 139 | check dam | 13 | 56 | constructed and accepted |
| 140 | stone wall | 32 | 0 | canceled |
| 141a | Gabion | 13 | 13 | constructed and accepted |
| 141b | repair wall | 10 | 10 | constructed and accepted |
| 142 | stone wall | 5.6 | 0 | canceled |
| 143 | check dam | 26 | 52 | constructed and accepted |
| 144 | check dam | 17.4 | 17.4 | constructed and accepted |
| 145 | stone wall | 19.5 | 0 | canceled |
| 146a | check dam | 35 | 0 | canceled |
| 146b | stone wall | 47 | 0 | canceled |
| 147 | check dam | 17 | 0 | canceled |
| 148 | check dam | 34 | 0 | canceled |
| 149 | stone wall | 72 | 75 | constructed and accepted |
| 150 | repair wall | 96 | 146 | constructed and accepted |
| 151 | repair wall | 200 | 205 | constructed and accepted |
| 152 | check dam | 6 | 25 | constructed and accepted |
| 153 | check dam | 34 | 70 | constructed and accepted |
| 154 | check dam | 6 | 15 | constructed and accepted |
| 155 | stone wall | 12 | 15 | constructed and accepted |
| 156 | check dam | 25 | 0 | canceled |
| 157 | check dam | 15.5 | 36 | constructed and accepted |
| 158 | check dam | 24 | 25 | constructed and accepted |
| 159 | check dam | 10 | 10 | constructed and accepted |
| 160 | stone wall | 16 | 17 | constructed and accepted |
| 161 | stone wall | 112 | 114 | constructed and accepted |
| 162 | stone wall | 10 | 12 | constructed and accepted |
| 163 | stone wall | 7 | 10 | constructed and accepted |
| 164 | stone wall | 6 | 6 | constructed and accepted |
| 165 | stone wall | 11 | 11 | constructed and accepted |
| 166 | check dam | 66 | 69 | constructed and accepted |
| 167 | check dam | 4 | 22 | constructed and accepted |
| 168 | check dam | 40.5 | 96 | constructed and accepted |
| 169 | stone wall | 20 | 21 | constructed and accepted |
| 170 | Gabion | 44 | 52 | constructed and accepted |
| 171 | stone wall | 43 | 0 | canceled |
| 172 | check dam | 15 | 18 | constructed and accepted |
| 173 | stone wall | 66 | 72 | constructed and accepted |
| 174 | stone wall | 132 | 142 | constructed and accepted |
| 175 | check dam | 10.5 | 14 | constructed and accepted |
| 176 | stone wall | 10 | 26 | constructed and accepted |
| 177 | check dam | 42 | 43.5 | constructed and accepted |
| 178 | check dam | 41 | 46 | constructed and accepted |
| 179 | Gabion | 17 | 18 | constructed and accepted |
| 180 | Gabion | 28 | 29 | constructed and accepted |
| 181 | Gabion | 8 | 12.5 | constructed and accepted |
| 182 | Gabion | 36 | 49 | constructed and accepted |
| 183 | check dam | 14 | 16 | constructed and accepted |
| 184 | check dam | 39 | 44.5 | constructed and accepted |
| 185 | stone wall | 15 | 16 | constructed and accepted |
|  | Totals | 7833 | 7535.4 |  |

# Text boxes

Ras Baalback

Target watershed for flood management in phase II. 220 km2

Fakhe

Target Watershed for phase I.

94 km2

Aarsal