Annex 1

|  | Insert Fund specific logo, if applicable |
| --- | --- |

[Lebanese Recovery Fund]

ANNUAL programme NARRATIVE progress report

REPORTING PERIOD: 1 january – 31 December 2009

| Submitted by: Raghed Assi, Poverty and Social Development Portfolio. United Nations Development Programme (UNDP). Email Address: raghed.assi@undp.org Telephone number: 70 188122. |  | Country and Thematic Area Country level |
| --- | --- | --- |

| Programme No: LRF- 7 MDTF Office Atlas No: 00058325 Programme Title: “Enhance Performance of the Social Sector” |  | Participating Organization(s): United Nations Development Programme (UNDP) |
| --- | --- | --- |

| Implementing Partners: National counterparts (government, private, NGOs & others): Ministry of Social Affairs acting as secretariat to Inter-Ministerial Committee on Social Issues (IMC includes representatives from the Ministries of Finance, Economy & Trade, Education & Higher Education, Interior & Municipalities, Public Health, and Labor in addition to the Council for Development and Reconstruction) |  | Programme Budget (from the Fund): USD 270,000 |
| --- | --- | --- |
| Programme Duration (in months): Start date: November 2007 End date: December 2010 Original end date: November 2008 Revised end date, if applicable: December 2010 Operational Closure Date, if applicable: N/A Budget Revisions/Extensions: List budget revisions and extensions, with approval dates, if applicable |

# NARRATIVE REPORT FORMAT

# Purpose

- Provide the main outputs and outcomes/objectives of the programme.

The Project “Support to the Social Inter Ministerial Committee” aims at supporting the implementation of a number of reform initiatives that were called upon in the Social Action Plan to be undertaken by the inter-ministerial committee for Social Issues.  The Project supports the Inter-Ministerial Committee to enhance the performance of the Social Sector in the country through increased coordination in the implementation of social programs and provision of social services as well as in devising and building consensus around a social development strategy.

The Project outputs can be summarized as the following:

  - Elaborate a national social development policy, strategy and related implementation plan.

  - Enhance effectiveness in social service delivery and implementation of social programs between public agencies, this is performed through in-depth revision of social services extended by public entities and identify the overlaps in order to reduce duplication in the delivery of social services among the ministries of Social Affairs, Education and Higher Education, and Public Health.

  - Enhance effectiveness in the implementation of local development initiatives through mapping of local development initiatives and defining a framework of national needs and priorities.

- Explain how the Programme relates to the Strategic (UN) Planning Framework guiding the operations of the Fund.

The Project is considered the implementation tool of many of the Social Action Plan recommendations. The Social Action Plan that was submitted by the government to the Paris III donors’ conference back in January 2008 called for a number of initiatives to enhance the performance of the social sector. The initiatives include the elaboration of a social strategy which represents the government’s vision and policy to improve the social conditions of the population and to push the social development forward.  In addition to the social strategy, the Social Action Plan emphasized the need for increasing coordination and synchronization in the delivery of social services and programs and the implementation of local development initiatives; both are crucial to improve efficiency in public social spending and implementation of social interventions.

# Resources

Financial Resources:

- Provide information on other funding resources available to the project, if applicable.

The project benefits from in kind contribution of the UNDP – Ministry of Social Affairs joint project “Capacity Building for Poverty Reduction”.  This subject project is fully managed and administered by the working team of the Capacity Building for Poverty Reduction Project at the Ministry of Social Affairs. Moreover, the administrative and logistical costs for the operations of the “Enhance the Performance of the Social Sector” are covered by the Poverty Reduction project.

- Provide details on any budget revisions approved by the appropriate decision-making body, if applicable.

Budget revisions took place for the extension of the project period with no substantive changes in the outputs and activities. No cost time frame extension was approved by the LRF committee.

- Provide information on good practices and constraints in the mechanics of the financial process, times to get transfers, identification of potential bottlenecks, need for better coordination, etc.

Under the support to Support to the National Implementation modality (NIM), the project is headed by the Minister of Social Affairs acting as the National Coordinator approving on all financial transactions and other logistic procedures of the project.  Accordingly, delays occurred in the progression of activities and achievement project objectives as planned given the change in the ministers and the stall of the Lebanese Government activities for some period before the presidential elections and following the parliamentarian elections.

Human Resources:

- The staff of the project of the “Capacity Building for Poverty Reduction” is actually providing the human resources support to this project as it falls within overall framework of its technical assistance to the Ministry of Social Affairs. This project covers a percentage of their salaries according to the time allocated for the management and implementation of the project activities. No international staff is recruited under this project.

# Implementation and Monitoring Arrangements

- Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the operating context.

Under the specific management arrangement of the “support to national implementation”(previously known as Support to NEX/national execution), MOSA supported by the UNDP “Capacity Building and Poverty Reduction Project” is implementing the project and all related activities; as such it is ensuring the proper management of the project by liaising with the Ministry of Social Affairs through the project manager of the mentioned project and direct support by UNDP. This team liaises closely with UNDP Country Office for the development of project work plan, monitoring the progress and substantively reviewing progress towards achievements.  Moreover, the project is steered by the Inter-Ministerial Committee for Social Issues which encompass seven ministries whose mandate relates in different aspects to the objectives and planned activities of the project.  The inter-ministerial committee is also supported by a technical team which includes a technical representative from each of the seven ministries.  The role of the technical team is to provide technical support to the project and ensure utmost cooperation and coordination in the implementation of the three activities.

- Provide details on the procurement procedures utilized and explain variances in standard procedures.

As a support to NIM, this project follows the regular UNDP procurement rules and regulations.

- Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing project.

The agreed upon monitoring system for this project is similar to all other project managed and implemented by UNDP. As such, the following actions are taken to ensure the proper implementation of the project and the re-alignment to specific objectives if need be:

- Quarterly reports: the project team prepares quarterly progress reports and work plans in addition to annual reports and other reports as required by UNDP and LRF committee in Beirut.

- Periodic meetings: UNDP holds periodic meetings with the project team to substantively assess the progress of the project and advise on future steps and rectification if needed.

All of the above contributed to an in-depth follow up of the project implementation facilitating the corrective measures to be taken if amendment of specific activities is required. This is logged as a lesson learned in the quarterly report submitted to UNDP.

It is worthy to note that given the fact that the project is steered by the Inter-ministerial Committee for Social Issues (which is headed by the Prime Minister), the project is also liable to report on progress achieved and obstacles faced, if any, on regular basis to the Prime Minister’s office.

- Report on any assessments, evaluations or studies undertaken.

The project will deliver three main outputs in the form of reports, yet none so far is fully completed; those reports are:

- A national comprehensive and integrated Social Development Strategy

- A report on duplication in the implementation and social programs and delivery of social services in the ministries of Social Affairs, Public Health and Education and Higher Education.

- An electronic portal on developmental priorities, available institutions and ongoing development projects that are geographically presented.

# Results

- Provide a summary of Programme progress in relation to planned outcomes and outputs; explain any variance in achieved versus planned outputs during the reporting period.

The project is on track for achieving the planned outputs contributing to enhancing the performance of the Social Sector at the three main instances:

- Proper mapping of the social services rendered by different ministries which will reduce the duplication between these various ministries and consequently decrease the public spending

- The development of the first social strategy in Lebanon for better targeting projects, for better development of poverty reduction strategies, and better planning of relevant socio-economic interventions according to the needs and priorities.

- Mapping of local development initiatives for better coordination mechanisms among various actors and donors

- Report on the key outputs achieved in the reporting period including # and nature of the activities (inputs), % of completion and beneficiaries.

| Project Outputs | Activities | Status |
| --- | --- | --- |
| Output 1: A national social strategy and related work plan developed. | Develop the social strategy – conduct desk review and situational analysis | Completed |
|  | Elaborate vision statement, pillars and elements of social strategy and share with technical team | Completed |
|  | Consult with stakeholders including government officials, international organizations, experts, and CSOs on elements, priorities and activities for social strategy | Almost completed |
| Output 2: Provision of Social Services and implementation of programs coordinated between MoSA, MoPH and MEHE | Identify duplicated programs between ministries of Social Affairs, Public Health, and Education and Higher Education | Almost completed |
|  | Organize/coordinate working sessions/ meetings to discuss and reach consensus on actions to reduce duplication | On going |
| Output 3: Implementation of local development initiatives better coordinated and synchronized with needs and priorities | Coordinate/support the establishment of national database of local development initiatives | Completed / Under final revision |
|  | Elaborate a framework of needs and priorities / regional profiles – | Ongoing |

- Explain, if relevant, delays in programme implementation, the nature of the constraints, actions taken to mitigate future delays and lessons learned in the process.

The constraints in implementation are in the component related to eliminating duplication in the delivery and implementation of social services and programs.  Team faced difficulties in obtaining relevant reliable data from concerned ministries; however, a first draft has been developed utilizing available information to be presented to the technical team of inter-ministerial committee.

As for the Social Strategy, it is anticipated that it might face delays in the completion given the importance of national consensus building on the identified priorities and the discussions to be held with the stakeholders and government representatives before the official endorsement by the government.

- List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

MOSA is designated as the National Implementing Agency for this project on behalf of Government of Lebanon; MOSA is responsible for managing the project and provides overall support to enable it to achieve its intended outputs and results. On the other hand, the achievement of project objectives and implementation of activities rely on the collaboration of other ministries particularly in providing relevant and useful information and guidance.  Effective collaboration will ensure a more efficient delivery of activities.

The UNDP country office support to the National execution modality will prevail. In addition to regular technical backstopping and monitoring activities regularly provided, the UNDP country office shall provide the executing agency with support services for the execution of the programme. This will ensure that technical and substantive expertise is available to the programme for coordination, recruitment, and procurement and contracting.

The project execution is carried out by the “Capacity Building for Poverty Reduction”, a joint project between UNDP and MOSA, under the support to NEX modality.

- Other highlights and cross-cutting issues pertinent to the results being reported on.

# Future Work Plan (if applicable)

Future work-plan for 2010:

- Social Strategy:

  - Complete consultation with stakeholders – phase II

  - Develop first draft of social strategy

  - Discuss first draft with major players and stakeholders / Organize national workshop

  - Modify draft based on feedback

  - Ensure Government endorsement on the strategy

  - Prepare working plan

  - Ensure government endorsement on the working plan

- Duplication:

  - Finalize report on duplication and share with technical team of the IMC for social issues.

  - Organize at least one or two bilateral meetings to discuss practical suggestions for reducing duplication

- Framework of development needs and priorities

  - Recruit web developing company

  - Create the relevant website and establish the database/portal of available data and documentation on developmental needs, indicators, information, etc., active organizations and projects under implementation.

# Performance Indicators (optional)

- Fill the table in this section to report on the indicators set at the output level as per the approved results framework in the programme document.

# Abbreviations and Acronyms

- List the main abbreviations and acronyms that are used in the report.

-UNDP: United Nations Development Programme.

- MOSA: Ministry of Social Affairs.

- LRF: Lebanese Recovery Fund.

# Footnotes

The term “programme” is used for programmes, joint programmes and projects.

E.g. Priority Area for the Peacebuilding Fund; Thematic Window for the Millennium Development Goals Fund (MDG-F); etc.

The start date is the date of the first transfer of funds from the MDTF Office as Administrative Agent.

All activities for which a Participating Organization is responsible under an approved MDTF programme have been completed. Agencies to advise the MDTF Office.

E.g. for the UNDG Iraq Trust Fund and the MDG-F.