MDG-F COLOUR CODED ANNUAL WORKPLAN

SEPTEMBER 2009 / SEPTEMBER 2010

Color Legend: green (done), yellow (ongoing), and red (not started)

| JP outcome 1: Management & prevention of children malnutrition is improved at health facility level (nutrition rehabilitation & health centers) |
| --- |
| UN organization-specific Annual targets | UN Organization | Activities | TIME FRAME | Implementing Partner | PLANNED BUDGET |
|  |  |  | Q1 | Q2 | Q3 | Q4 |  | Source of Funds | Budget Description | Amount |
| JP Output 1: 24 nutrition rehabilitation centers and 90 health centres are equipped to effectively prevent and manage child malnutrition |
| 1.1.1. 22 nutrition rehabilitation centers and 14 health centres are equipped to effectively prevent and manage child malnutrition | UNICEF | 1.1.1.1. Procure and distribute to nutrition rehabilitation centres and health centres the annual needs of quantities of supplies (ready-to-use therapeutic foods (RUTF), micro-nutrient supplements and anthropometric materials) |  |  |  |  | Ministry of Health | MDG-F | Supp/equip & commodities | 40,000 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 40,000 |
| 1.1.2. 24 nutrition rehabilitation centres and 90 health centres are provided with needed quantities of take home food supplements and kitchen material cooking demonstration | WFP | 1.1.2.1. Procure 114 kits of kitchen material procured and buckets with cover for food distribution |  |  |  |  | Ministry of Health | MDG-F | Supp/equip & commodities | 47,320 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 47,320 |
|  | WFP | 1.1.2.2. Procure 67.5 Mt of food |  |  |  |  | Ministry of Health | MDG-F | Supp/equip & commodities | 36,750 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 36,750 |
|  | WFP | 1.1.2.3. Ensure transport, handling & storage of foods |  |  |  |  | Ministry of Health |  | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 9,200 |
|  |  |  |  |  |  |  |  |  | Total | 9,200 |
| JP Output 2: 228 Health workers are qualified on and put into practice for effective prevention and management of children malnutrition |
| 1.2.1. 72 Health workers are qualified et equipped to undertake effective prevention and management of children malnutrition | UNICEF | 1.2.1.1. Train 72 health workers on quality management of child malnutrition |  |  |  |  | Ministry of Health | MDG-F | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 18,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 18,000 |
| 1.2.2. 36 health centres and nutritional rehabilitation centres are equipped with transport means to conduct outreach activities and to supervise the community health providers | UNICEF | 1.2.1.2. Procure transport means (motorcycles) for 22 nutrition rehabilitation centers and 14 health centres |  |  |  |  | Ministry of Health | MDG-F | Supp/equip & commodities | 25,000 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 25,000 |
| JP Output 3: 24 nutrition rehabilitation centres and 90 health centres are provided with appropriate information, education and communication material on basic nutrition, health care and hygiene to undertake campaigns at community and school levels |
| 1.3.1. IEC materials on basic nutrition, health care and hygiene are made available for selected health centers and schools | UNICEF | 1.3.1.1. Design and print communication materials on basic nutrition, health care and hygiene and distribute to selected health centers and schools |  |  |  |  | Ministry of Health | MDG-F | Supp/equip & commodities | 20,000 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 20,000 |
|  | UNICEF | 1.3.1.2. Train 72 health workers on IEC techniques |  |  |  |  | Ministry of Health | MDG-F | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 10,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 10,000 |
| JP outcome 2: Community-based nutrition promotion & surveillance established in 150 selected communities |
| JP Output 2.1: 600 community health care providers are knowledgeable and put into practice on basic nutrition monitoring and surveillance practices, such as growth monitoring, identification of signs of malnutrition and timely referral of malnourished children, promotion of exclusive breastfeeding, timely and appropriate complementary feeding and hand washing, etc |
| 2.1.1. Selected 200 community health care providers are trained on basic nutrition monitoring and surveillance, maternal &child nutrition and hygiene | UNICEF | 2.1.1.1. Train 200 community health care providers on basic nutrition monitoring and surveillance, maternal &child nutrition and hygiene |  |  |  |  | Ministry of Health | MDG-F | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 20,850 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 20,850 |
| 2.1.2. Community health providers in 200 selected communities are equipped with transport means to undertake regular outreach activities and home visits | UNICEF | 2.1.2.1. Procure bicycles for 200 community health providers |  |  |  |  | Ministry of Health | MDG-F | Supp/equip & commodities | 12,000 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 12,000 |
| 2.1.3. Community health providers are equipped with anthropometric materials and RUTF to undertake nutrition monitoring activities | UNICEF | 2.1.3.1. Provide field adapted anthropometric materials and RUTF to the community health providers |  |  |  |  | Ministry of Health | MDG-F | Supp/equip & commodities | 20,000 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 20,000 |
| JP Output 2.2: Knowledge and skills among communities and families are built on sound nutrition practices, such as exclusive breastfeeding, timely and appropriate complementary feeding, hand washing, maternal and child nutrition and Prevention of Mother to Child transmission of HIV, etc |
| 2.2.1. Adequate communication materials are developed and provided to community health care providers | UNICEF | 2.2.1.1. Prepare IEC material including a manual in Creole on promotion techniques for community based nutrition promotion and surveillance |  |  |  |  | Ministry of Health | MDG-F | Supp/equip & commodities | 10,000 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 10,000 |
| 2.2.2. Continuous sensitization of families and social mobilization for behaviour change on nutritional foods and cooking practices, exclusive breastfeeding, infant and young child feeding ensured | UNICEF | 2.2.2.1. Organize community educational sessions in communities and schools (including schools parents associations) on nutrition, hygiene and appropriate feeding practices, PMTCT |  |  |  |  | Ministry of Health | MDG-F | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 5,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 10,000 |
|  |  |  |  |  |  |  |  |  | Total | 15,000 |
|  | WHO | 2.2.2.2. Promote communication for behaviour changes vis-à-vis nutrition and appropriate feeding practice through medias activities (radio campaigns) |  |  |  |  | Ministry of Health | MDG-F | Supp/equip & commodities | 5,000 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 5,000 |
|  |  |  |  |  |  |  |  |  | Total | 10,000 |
| JP outcome 3: Sustainable food production established in school communities to improve nutritional status and promote the education of children and their parents on food security and nutrition |
| JP Output 3.1: Nutritional status and dietary habits of school children were evaluated in 150 community Schools |
| 3.1.1. Evaluation of the nutritional status and dietary habits of school children in selected communities schools | FAO | 3.1.1.1. Recruit the national consultants (2) and installation of the team which will carry out the diagnosis |  |  |  |  | Ministry of Agriculture | MDG-F | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 5,000 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 5,000 |
|  | FAO | 3.1.1.2. Purchase of a vehicle for the project |  |  |  |  | Ministry of Agriculture | MDG-F | Supp/equip & commodities | 24,000 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 24,000 |
|  | FAO | 3.1.1.3. Identification of the 150 schools to be supported |  |  |  |  | Ministry of Agriculture | MDG-F | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 5,000 |
|  |  |  |  |  |  |  |  |  | Travel | 1,000 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 6,000 |
|  | FAO | 3.1.1.4. Conduct the evaluation, analyze data and prepare report |  |  |  |  | NGO | MDG-F | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
| JP Output 3.2: School teachers school children, community workers and parents are trained on basic agriculture, nutrition and food security to ensure ownership of knowledge and sustainability of the intervention and maintenance of school gardens |
| 3.2.1. Preparation and validation of new training material on basic nutrition and food security, nutrition and management of school garden | FAO | 3.2.1.1. Establishment of contract with an organization for the preparation of the training materials |  |  |  |  | NGO | MDG-F | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | FAO | 3.2.1.2. Selection of the existing didactic materials which can be used in the schools |  |  |  |  | Ministry of Agriculture | MDG-F | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | FAO | 3.2.1.3. Preparation, validation and distribution of the training materials in the schools |  |  |  |  | Ministry of Education | MDG-F | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
| 3.2.2. Organization of 4 trainings sessions for school teachers , school children, community workers and parents | FAO | 3.2.2.1. Conduct field missions to sensitize the parents for the reinforcement of existing associations and the establishment of new associations |  |  |  |  | Ministry of Agriculture | MDG-F | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 3,000 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 1,000 |
|  |  |  |  |  |  |  |  |  | Total | 4,000 |
|  | FAO | 3.2.2.2. Undertake a baseline evaluation on agricultural matter knowledge, of nutrition, for teachers, community workers and parents to be used as reference to the future evaluation of the impact of the project. |  |  |  |  | Ministry of Agriculture | MDG-F | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 3,000 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 1,000 |
|  |  |  |  |  |  |  |  |  | Total | 4,000 |
|  | FAO | 3.2.2.3. Conduct four training sessions (theory and practices) on topics related to food safety, nutrition and the management of the school gardens |  |  |  |  | Ministry of Agriculture | MDG-F | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 4,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 4,000 |
| JP Output 3.3: School gardens are created and maintained in selected schools |
| 3.3.1. Creation and maintained 50 schools garden | FAO | 3.3.1.1. Identification of the needs for the school gardens |  |  |  |  | Ministry of Agriculture | MDG-F | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 2,000 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 1,000 |
|  |  |  |  |  |  |  |  |  | Total | 3,000 |
|  | FAO | 3..3.1.2. Definition of the technical specifications of the required tools and agricultural inputs |  |  |  |  | Ministry of Agriculture | MDG-F | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 2,000 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 2,000 |
|  | FAO | 3.3.1.3. Launching of the biddings for the purchase of the inputs; analysis of the tenders and attributions |  |  |  |  | Ministry of Agriculture | MDG-F | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 500 |
|  |  |  |  |  |  |  |  |  | Total | 500 |
|  | FAO | 3.3.1.4. Signing of contract with the partners for the support on agricultural aspects of the school gardens, followed by distribution of the tools and agricultural inputs to the recipients and for the preparation of the training materials |  |  |  |  | NGOs | MDG-F | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 4,000 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 4,000 |
|  | FAO | 3.3.1.5. Procure, receive and ensure quality control of the inputs and distribute to the beneficiaries |  |  |  |  | Ministry of Agriculture | MDG-F | Supp/equip & commodities | 154,503 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 10,000 |
|  |  |  |  |  |  |  |  |  | Total | 164,503 |
|  | FAO | 3.3.1.6. Organization of the teams of management of the school gardens in each selected school |  |  |  |  | Ministry of Agriculture | MDG-F | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 500 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 500 |
|  | FAO | 3.3.1.7. Support food production in the school gardens and income generating activities aimed at improving access to and consumption of micronutrient-rich foods through implementation of good practices and new techniques |  |  |  |  | Ministry of Agriculture | MDG-F | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 500 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 500 |
|  | FAO | 3.3.1.8. Planning of the activities with the management team of of the school gardens, the children for the regular maintenance of the school gardens (definition of activities per period and class, etc…) |  |  |  |  | Ministry of Agriculture | MDG-F | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | FAO | 3.3.1.9. Technical follow-up of the consultant in horticulture in the school gardens |  |  |  |  | Ministry of Agriculture | MDG-F | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 500 |
|  |  |  |  |  |  |  |  |  | Total | 500 |
|  | FAO | 3..3.1.10. Planning and realization of the activities of maintenance of the school gardens during the holidays |  |  |  |  | Ministry of Agriculture | MDG-F | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
| JP Output 3.4: School kids in selected schools produce periodically and consume vegetables at least once a day |
| 3.4.1. School kids in selected schools produce periodically and consume vegetables | FAO | 3.4.1.1. Technical monitoring and evaluation of food production at schools |  |  |  |  | Ministry of Agriculture | MDG-F | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | FAO | 3.4.1.2. Development of school proposals of menus with local schools and producers, to promote and sensitize the local public on the purchase of the products prepared by the schools |  |  |  |  | Ministry of Agriculture | MDG-F | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 1,000 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 1,000 |
|  | FAO | 3.4.1.3. Use of the school gardens like site of demonstration practices to allow the children to have an interest for the agricultural work, in the future |  |  |  |  | Ministry of Agriculture | MDG-F | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | FAO | 3.4.1.4. Formulate information messages about right to food to be used in communication strategy and information campaign to promote better food safety quality. A range of media will the used in order to effectively target the groups most risk. |  |  |  |  | Ministry of Agriculture | MDG-F | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
| JP outcome 4: Interventions on children nutrition and food security are effectively monitored and supervised by government counterparts |
| JP Output 4.1: The Nutrition Unit at the Ministry of Health is reinforced in terms of human resources and equipment. |
| 4.1.1. An international Nutritionist and one national nutrition expert are recruited and posted at the Ministry of Health. | UNICEF | 4.1.1.1. Recruit an International nutritionist Specialist and one national nutrition expert |  |  |  |  | Ministry of Health | MDG-F | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 150,000 |
|  |  |  |  |  |  |  |  |  | National staff | 30,000 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 180,000 |
| 4.1.2. The nutrition unit of the Ministry of Health is equipped with a vehicle for filed visits and supervision | UNICEF | 4.1.2.1. Procure a vehicle for the nutrition unit of the Ministry of Health |  |  |  |  | Ministry of Health | MDG-F | Supp/equip & commodities | 25,000 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 25,000 |
| 4.1.3. The national and regional health teams are trained to ensure good implementation and monitoring of the nutrition interventions. | WHO | 4.1.3.1. Preparation of training materials |  |  |  |  | Ministry of Health | MDG-F | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | WHO | 4.1.3.2. Provide training to regional health and agriculture directors, the nutrition team of the Ministry of health, on surveillance and monitoring system on programme monitoring |  |  |  |  | Ministry of Health | MDG-F | Supp/equip & commodities | 1,000 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 2,000 |
|  |  |  |  |  |  |  |  |  | Total | 3,000 |
| 4.1.4. Capacity of health centres and schools is strengthened to ensure monitoring of field activities | WHO | 4.1.4.1. Training of school teachers, health workers on monitoring of programme activities |  |  |  |  | Ministry of Health | MDG-F | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 10,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 10,000 |
|  | WHO | 4.1.4.2. Organize joint regular monitoring visits to health centers, communities and schools in collaboration with health, agriculture and education directorates |  |  |  |  | Ministry of Health | MDG-F | Supp/equip & commodities | 0 |
|  |  |  |  |  |  |  |  |  | International staff | 0 |
|  |  |  |  |  |  |  |  |  | National staff | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 4,000 |
|  |  |  |  |  |  |  |  |  | Total | 4,000 |
| 4.1.5. The JP is well managed | UNICEF | 4.1.5.1. Support the Programme Management Team and ensure visibility of the JP implementation |  |  |  |  | N/A | MDG-F | Supp/equip & commodities | 20,159 |
|  |  |  |  |  |  |  |  |  | International staff | 150,000 |
|  |  |  |  |  |  |  |  |  | National staff | 18,000 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Other Costs | 0 |
|  |  |  |  |  |  |  |  |  | Total | 188,159 |
| Including indirect costs | Total FAO | 239,148 |
|  | Total UNICEF | 624,890 |
|  | Total WFP | 99,799 |
|  | Total WHO | 28,890 |
| Total Planned Budget | 992,727 |