## MDG F
MDG F COLOUR CODED ANNUAL WORKPLAN
JUNE 2009/JUNE 2010
Color Legend: green (done), yellow (ongoing), and red (not started)
EXPECTED OUTPUTS | PLANNED ACTIVITIES | 1 YEAR TIMEFRAME - June 2009/June2010 |  |  |  | RESPONSIBLE PARTY | PLANNED BUDGET
|  | Q3 | Q4 | Q1 | Q2 |  | Funding Source | Budget Description | Amount
| 1.1 Consultative Assessment of the adequacy and existing legislation and policies on gender equality issues of relevant justice and security sector : level of public attendance in the debate of new laws and policies |  |  | X |  | Secretariat of Committee Pilotage (SCP) | MDG F UNDP | 2 international consultants (1 legislative and 1 gender expert) | 25000
MDG F Outcome 1- Judicial and security sector democratic governance improved and citizen´s rights better protected through legislative and normative reform | [5 empty] | UNDP |  | 1 national consultant | 5000
[8 empty] | Travel | 5000
OUTPUT 1
Review of new legislation and regulatory measures in support of JSSR in line with CEDAW
Indicators: | [8 empty] | Total
§ Assessment mission and 2 consultative workshops held: distribution of the findings report until June 2010; level of public attendance ; | [8 empty] | 35000
Baseline data: few intl. Conventions ratified by the Government. Lack of knowledge, application and reporting mechanisms of existing ratified International Conventions.
§ Level of public participation and open discussion on justice and security matters. Baseline data: GVT assessment, and UN interagency mission, led by the DPA of October 2008 assessment on lack of knowledge from the public on SSR Reform process; lack of media coverage. | 1.2 Support participative revision of policy and legislation processes related to JSSR from a gender perspective |  |  | x | X | Technical Secretariat of Committee Pilotage (TSCP) | MDG F UNDP | Internat. Consult | 15000
§ # of women’s organizations included in consultation. Baseline data: about 20 women organisations active and 6 women organisation/ resources persons available. | [5 empty] | UNDP |  | National Cons. | 2000
Input from dialogue processes, particularly related to CEDAW implementation and gender issues, impacts finalized legislation. | [7 empty] | Workshops | 2000
[8 empty] | Travel | 4000
Total
23000
| 1.3 Elaboration and adoption of National Gender Equality Policy based on national Gender Analysis and CEDAW recommendations, and creating partnerships with all major stakeholders and Ministries | X | X | X | X | UNIFEM | MDG F UNIFEM | National Consultants | 2500
Indicators: | [5 empty] | Ministry of Women / Institute of Women and Children |  | Contracts | 30000
1 gender sensitive law proposal presented until June 2010 | [7 empty] | Workshops | 5000
[8 empty] | Travel | 2500
1 gender policy finalized until june 2010 | [7 empty] | Supplies and Misc. | 6000
Total
46000
| 1.4 Support National Assembly to do public debates on progress on the SSR agenda |  |  | x |  |  | UNDP MDG F | Int consults | 21500
[8 empty] | National staff | 5000
[8 empty] | Supplies | 2500
Indicators: | [5 empty] | UNDP |  | Travel | 5000
[6 empty] | NPA |  | contracts | 8000
1 public debate held until June 2010 | [8 empty] | Total
42000
146000
SUBTOTAL 1
OUTPUT 2 |  | X | x |  |  | UNDP |  | 1 SSR expert | 40000
[6 empty] | NPA | MDG F | 1 gender expert | 5000
Parliamentary oversight of justice and security sector reform strengthened | 2.1 Mission for capacity assessment of issues relevant for Parliament role for oversight of SSR (budgetary, legislative and gender equality focus) and formulation of a strategic | [6 empty] | 1 national consultant | 5500
Indicators: | development plan for parliamentary security sector oversight | [6 empty] | travel | 5000
mission for oversight capacity held; until june 2010 the defense and justice comission have a strategy document for oversight on the sector | [7 empty] | workshop& misc | Total
§baseline: Pre-programme interviews with key stakeholders regarding exercise of current oversight function. | [8 empty] | 55500
§ Demonstrated increase in knowledge by parliamentarians trained and gender quota achieved. Baseline data: results of pre-training testing.
| 2.2 Assess specific training needs and provide training for parliamentarians and commissions on SSR oversight, legislative drafting and gender sensitive budgeting (30% women) |  |  | X |  | UNDP | UNDP MDG F | Technical assistance x 3 months | 30000
[6 empty] | NPA |  | Travel | 5000
[8 empty] | Supplies/equipments | 15000
[8 empty] | Misc | 11000
Total
61000
SUBTOTAL 2 | 116500
Output 3 – MDG F | [5 empty] | UNDP | UNDP | 1 international advisor SCP | 40000
Increased capacity of relevant ministries to implement National Strategy for Restructuring and Modernization for the Security Sector | 3.1 Provide technical support to the government trough the Secretary of the Committee de Pilotagem (SCP) and MoJ, MoD, MoI, for the implementation of the National Strategy for Restructuring and Modernization of SS (NSRMSS) |  | X | X | X | SCP | MDG F | 1 intern. Advisor MoJ | 20000
[8 empty] | 1 national assistant SCP | 6000
Indicators: | [5 empty] | MoJ
§ Progress in implementation of the JSSR strategy as per time schedule; until june 2010 key intervenients have their capacity strengthened for implementing SSR reform, trough technical support and training | [5 empty] | MoD |  | supplies/travel | 9500
Total
Baseline data: | [8 empty] | 75500
§ Assessment of pre-programme activities undertaken and adjustments to implementation schedule anticipated through interviews with key stakeholders. | 3.2 Provide on the job training to Ministry of justice and judiciary personnel |  | x | X | X | UNDP | UNDP | intern. Advisor | 30000
[6 empty] | MOJ | MDG F | 1 national | 10000
100 judges and ministry staff trained/mentored until june 2010 | [5 empty] | CENFOJ |  | travel | 6000
[8 empty] | supplies | 10000
Total
56000
Indicators: | 3.3 Support SCP to conduct public awareness activities focusing on SSR and gender in Bissau and 4 regions. |  | X | X | x |  |  | Internat. Staff | 25000
information material disseminated in 3000 beneficiaries; 8 radio transmissions, 4 news articles published, until june 2010; 2 workshops on RSS held | [5 empty] | UNDP | UNDP | National staff | 10000
[6 empty] | SCP | MDG F | Travel | 6000
§ Broader public awareness regarding the national SSR strategy. Baseline data: results of pre-programme legal awareness survey. | [5 empty] | CSOs |  | publications | 10000
[8 empty] | Contracts | 20000
Total
71000
Indicators: | 3.4 To conduct an assessment on the skills, gaps and training needs within law enforcement agencies and Ministries of Justice, Interior and Defence through consultations with senior officials and staff representatives. |  | X | X | X | UNODC |  | Supp, equip and commodities | 14000
Assessement report disseminated until June 2010 | [6 empty] | UNODC | International and national Staff | 19000
MDG F
[8 empty] | Training | 10000
[8 empty] | Contracts | 15000
[8 empty] | Other costs | 1500
Total
59500
| 3.5 Provide training to law enforcement agencies and Ministries of Justice, Interior and Defence on issues related, among others, to administration reform, human resources, crime management, GBV studies, conflict resolution, human rights and international law. |  |  | X | X | UNODC | UNODC MDG F | Supp, equip and commodities | 14000
number of trained personnel | [7 empty] | International and national Staff | 29000
[8 empty] | National Staff | 0
[8 empty] | Travel | 0
[8 empty] | Personnel | 0
[8 empty] | Training | 12000
[8 empty] | Contracts | 3750
[8 empty] | Other costs | 2000
Total
60750
| 3.6 Support the Ministry of Interior to develop a strategy regarding the management of public security, crime and violence including sexual and gender based violence and a public awareness campaign on the strategy covering Bissau and 4 additional regions |  |  | X | X | UNODC | UNODC MDG F | Supp, equip and commodities | 14000
Indicators: | [7 empty] | International and national Staff | 15000
international and national consultancies and equipment provided to the MoI until June 2010
training of prison officers (80) on management of public safety, crime and violence
1 newspaper, 2 radio programmes and 5000 panmflets issued on public safety management strategy
[8 empty] | Training | 19000
[8 empty] | Contracts | 10000
[8 empty] | Other costs | 3000
Total
61000
Indicators | 3.7 Strengthen the capacity of the Ministry of Interior to provide assistance to victims of GBV and train the police on national and international laws that protect women and children | X | X | X | X | UNFPA | UNFPA | personel | 25000
Number of trained staff | [6 empty] | MDG F
GBV strategy approved until june 2010 | 3.8 Train gender focal points of Ministries and NGOS on gender sensitive budgeting |  |  |  |  | UNFPA | UNFPA | travel | 5000
MDG F
| 3.9 Train PPM in sensitizing decision makers on gender quota in governing bodies and train the ETN in drafting the Gender Equality National Plan |  |  |  |  | UNFPA | UNFPA | contracts & training | 18000
MDG F
Total
48000
431750
SUBTOTAL 3
MDG F Outcome 2 | 4.1 Assessment on traditional justice, ADR mechanisms and formal justice regarding legal needs and services for the most vulnerable, in particular women |  | X | X |  | Contract service | UNDP | Internt. Staff | 25000
Access to justice services for the poor improved with special focus on women | [5 empty] | Centro Pesquisa | MDG F | National staff | 10000
[8 empty] | Contractual services | 20000
MDG F Output 4 | [7 empty] | Travel | 6000
Enhanced access to justice services, particularly for vulnerable groups including women | [7 empty] | Publications/mIscel | 10000
Indicators: | [8 empty] | Total
71000
§ # of persons provided with legal services (disaggregated by service, beneficiary and sex). Baseline data: socio-anthropologic studies
study on traditional mechanisms and codification proposal disseminated until June 2010
§ # of women’s legal issues resolved through courts and customary mechanism and quality of case handling.
Baseline data:
§ Pre-programme inspection of court registers, interviews with judges, customary leaders, legal aid centre staff and clients. PAOSED programme assessment study on state of regional courts.
| 4.2 Study and support establishment of one legal aid clinic with Faculty of Law targeting legal counselling and representation for vulnerable groups, in particular women |  | X | X | X | UNDP/ | UNDP MDG F | Internt staff | 30000
Indicators: | [5 empty] | Law Faculty |  | National staff | 10000
[6 empty] | MoJ |  | travel | 10000
§ Increase in # of organizations providing legal services. Baseline data: number of organizations providing legal aid services pre-programme (June 2009-June 2012). | [7 empty] | Contract services | 20000
[8 empty] | Equipment | 20000
§ Demonstrated increased knowledge on the part of beneficiaries trained and quota for women representation met. Baseline data: results of pre-training testing. | [7 empty] | Supplies | 10940
Total
100940
| 4.3 Provide training to CSOs, media, legal authorities, customary and religious leaders on Women’s Human Rights and CEDAW related issues (GBV, family law, harmful practices, etc.) and on gender sensitive approaches to criminal matters, conflict resolution, mediation and negotiation (Min. 30% women) |  | X | X | X | UNIFEM | UNIFEM MDG F | Workshops | 20000
Indicators: | [5 empty] | NGOs
50 persosn trained until June 2010 with 30% of women participation | [5 empty] | MoJ |  | Supp., Equipment and commodities | 5000
M of Women/IMC
[8 empty] | Contracts | 13000
[8 empty] | Consultants | 7500
[8 empty] | Travel | 14000
[8 empty] | Misc. | 2000
Total
61500
Indicators: | 4.4 Support a community legal awareness campaign covering beneficiaries in Bissau and 4 regions focusing on citizens’ and Women’s Human Rights and access to legal aid services through information material (pamphlets, posters, FAQs, T-Shirts), and media (print and radio) |  | X | X | X | UNIFEM | UNIFEM MDG F
information material disseminated through 1000 beneficiaries; 2 radio transmissions; 1 newspaper article published until june 2010 | [5 empty] | NGOs |  | supplies | 6000
MoJ
[6 empty] | M of Women/IMC |  | staff | 19000
[8 empty] | misc | 1000
travel
3000
Total
29000
| 4.5 Strengthen 5 women’s and civil society organizations in Bissau and regions areas in their capacity to provide legal counselling and conflict resolution services and training on SGBV, women’s legal rights, family law, land, criminal matters, trough technical and financial support, namely equipments and training | [6 empty] | Equipments | 33000
financial and equipment support and training delivered to selected CSO | [7 empty] | National Team | 48000
|  | x | x | x | x | UNFPA | MDG F UNFPA | Training | 40000
[8 empty] | Contracts | 37500
[8 empty] | Other costs | 5000
Total
163500
| MONITORING & EVALUATION | X | X | X | X | UNDP | UNDP MDG | CPR Manager | 256000
[8 empty] | reporting | 8110
Total
264110
690050
SUBTOTAL 4
GRAND TOTAL 2009/2010 | [8 empty] | 1384300
| UNDP | 855050
| UNFPA | 211500
| UNIFEM | 136500
| UNODC | 181250
| TOTAL | 1384300

## Summary
Summary of Budget Totals by Agency
Funding Source | Amounts
UNDP | 35000
23000
42000
55500
61000
75500
56000
71000
71000
100940
264110
855050
UNFPA | 25000
5000
18000
33000
48000
40000
37500
5000
211500
UNIFEM | 46000
61500
29000
136500
UNODC | 59500
60750
61000
181250
Grand Total | 1384300